## Sheet1
ECML OHLE RENEWAL WORKS - from 1st April 2006
Disruptive Weekend Possessions
Saturday 1st April - Saturday 10th June 2006
0045SAT - 0415MON | Route via WGC blocked |  | GN Inner services via WGC/Hertford North replaced by buses
Reduced GN inner/outer service via Hertford North only
Sunday 11th June - Sunday 10th September 2006
0045 - 1020SUN | Route between WGC - Peterborough/Letchworth blocked |  | Rail replacement of early morning GN outer services
Saturday 16th September - Saturday 9th December 2006
0010 - 1000SUN | Route between Kings Cross - WGC blocked |  | Rail Replacement of all GN inner services via WGC
(due to unrelated block of Hertford North route all other services rail replaced too)
Saturday 3rd February - Sunday 25th March 2007
0010 - 1000SUN | Route between Kings Cross - Finsbury Park blocked |  | All services start/terminate Finsbury Park
Saturday 31st March - Saturday 19th May 2007
0015SAT - 0415MON | Route via WGC blocked |  | GN Inner services via WGC/Hertford North replaced by buses
Reduced GN outer service via Hertford North only
Saturday 15th September - Saturday 8th December 2007
0010 - 0800SUN | Route between Kings Cross - New Barnet blocked |  | Rail Replacement of all GN inner services to/from New Barnet
(due to unrelated block of Hertford North route all other services rail replaced too)
Disruptive Bank Holiday Possessions
Friday 14th - Monday 17th April 2006 |  | Easter
0430SAT - 1200MON | Route between Kings Cross - WGC - Stevenage blocked |  | No service between Kings Cross - Finsbury Park
GN Inner services via WGC replaced by buses
Reduced GN inner/outer service via Hertford North only
Sunday 30th April - Monday 1st May 2006 |  | May Day
0430SAT - 1200MON | Route between Kings Cross - WGC - Stevenage blocked |  | No service between Kings Cross - Finsbury Park
GN Inner services via WGC replaced by buses
Reduced GN inner/outer service via Hertford North only
Saturday 28th - Monday 29th May 2006 |  | Spring
0100SUN - 0700MON | Route between Kings Cross - WGC - Stevenage blocked |  | No service between Kings Cross - Finsbury Park
GN Inner services via WGC replaced by buses
Reduced GN inner/outer service via Hertford North only
Sunday 27th and Monday 28th August 2006 |  | Late Summer
0100SUN - 0700MON | Route between Kings Cross - WGC - Stevenage blocked |  | No service between Kings Cross - Alexandra Palace
GN Inner services via WGC replaced by buses
Reduced GN inner/outer service via Hertford North only
Saturday 7th - Monday 9th April 2007 |  | Easter
2200SAT - 0900MON | Route between Kings Cross - Finsbury Park blocked |  | All services start/terminate Finsbury Park
Saturday 26th - Monday 28th May 2007 |  | Spring
1515SAT - 1200MON | Route between WGC - Biggleswade/Letchworth blocked |  | Revised service with rail replacement between blocked locations
Sunday 26th and Monday 27th August 2007 |  | Late Summer
0100SUN - 0700MON | Route between WGC - Biggleswade/Letchworth blocked |  | Revised service with rail replacement between blocked locations