## Slide 1
Week 30 Possession Requirements
EE9 Status:
As per the tables below the programme delivered above baseline plan for weeks 18 and 24. Post week 18 a decision was taken to focus on delivering electrical continuity to ensure energisation event EE9 was successfully delivered for week 25. This decision left a shortfall in the final registration and panning programme elements that now need to be delivered in weeks 26 to 32. The requirement to focus on energisation event works was as a result of i) Third party access clashes, ii) Resource availability iii) Weather related issues. A revised registration programme has now been developed to allow Dynamic testing to commence in week 33, this new programme is dependent on a 50hr block being made available in week 30 to undertake works around the Newport Maindee and Ebbw Junction areas
Week 17 EE9 OLE status was -126 items cumulatively behind baseline: Key areas were SPS -85 and registration (Panned) -32
Week 18 the Status was -89 items with recovery to the SPS to -39 however further slippage to the registration (Panned) to -57. Alongside the core OLE items were high volumes of in line items in readiness for final registration plus extensive delivery in off track civils elements and LLATF completions
Week 24 EE9 OLE status was overall -4 items behind baseline: with SPS now fully recovered utilising resource from EE8, however registration (Panned) now stood at -127 with large volumes of final registration points and in-line items outstanding
Week 25 All core commodities were completed and the system energised however registration (Panned) had now slipped to -134. Works required to complete the shortfall now included 382 in line items, 1438 final registration (panned) -145 panning runs to be completed by week 32.
The week 17 -24 detail above illustrateshw the focus on Energisation increased the shortfall in registration (panned) from -32 in week 17 to -145 in week 25.
Week 18 Installations
Week 24 Installations
Week 25 Installations

## Slide 2
Week 30 Possession Requirements
EE9 Week Status: (Cont’d)
Week 27 – current status to go 332 in line items, 1203 final registration points, 137 wire to be Panned. Progress this week is on plan with 3 shifts to go covering another 153 items.
Week 30 currently has 128 in line items, 530 final registration points and 58 panning runs planned to be completed, and is key to meeting the week 32 completion.
Week 27 Installations
Week 30 Forecast

## Slide 3
Week 30 Possession Requirements
EE8 Status:
Between weeks 18 and 24 EE8 resource was reduced and utilised to facilitate critical works in EE9, week 25 provided opportunity to recover the programme as shown in the table below;
Week 17 EE8 OLE status was -11 items cumulatively behind baseline: (SPS)
Week 18 the Status was -32 items (Masts & SPS)
Week 24 EE8 OLE status had slipped to -175 Due to resources being diverted to support EE9
Week 25 blockade reduced the overall delta to -109 (SPS and Wire) this remains the current status as at week 27. Currently In Line Items, Final Registration is running to plan
Week 30 Forecast will provide a vital opportunity to hold the current wiring plan and increase the delivery in final registration elements.
Week 18 Installations
Week 25 Installations