## Wiring Week 30
Rail2019 | Area | CU MoM DR | Commodity | WR: | Str No: London | Mileage - London | Rd: Up- Main Cess Dn Relief Cess | Str No: County | Mileage - Country | Rd:4 | Total Length | Completed: | Team: | Planned Day Shift | Planned Week | Access Points
8 | F | Y13 | CONTENARY | S45 | 201.785 | 150m 42ch | Up Main | 201.884 | 150m 53ch | Up Main | 0.099 |  | Registration Team | Sat Night | 30 | Turners Yard
8 | F | Y14 | CONTENARY | S51 | 202.367 | 150m 77ch | Up Main | 202.411 | 150m 80ch | Up Main | 0.044 |  | Registration Team | Sat Night | 30 | Turners Yard
8 | H4&5 | Y25 | CONTENARY | W49 | 213.433 | 157m 67ch | Dn Relief | 213.735 | 158m 04ch | Dn Relief | 0.302 |  | Trac Double Drum | Sat Night | 30 | East Usk
9 | N1 | T18 | CONTENARY | T126 | 230.168 | 168m 19ch | Sidings | 230.225 | 168m 21ch | Sidings | 0.057 |  | Registration Team | Sat Night | 30 | Pengham
9 | N2 | Z17 | ATF | ATF-N2-4 | 231.636 | 169m 12ch | Up Main | 232.125 | 169m 36ch | Up Main | 0.489 |  | Double Drum | Sat Night | 30 | Brickyard
9 | O | T21 | CONTENARY | T157 | 232.125 | 169m 35ch | Up Relief | 232.175 | 169m 37ch | Up Relief | 0.05 |  | Registration Team | Sat Night | 30 | Ellen Street
9 | O | T22 | CAT | T170 | 233.251 | 170m 12ch | Line D | 234.147 | 170m 56ch | Line D | 0.896 |  | KELTBRAY CBS | Fri night | 30 | Canton
9 | O | T22 | CAT | T169 | 233.251 | 170m 12ch | Line C | 234.175 | 170m 58ch | Line C | 0.924 |  | BBR Wiring Train | Fri Night | 30 | Brickyard
9 | O | T22 | CAT | T171 | 233.251 | 170m 12ch | Line E | 234.175 | 170m 59ch | Line D | 0.924 |  | KELTBRAY CBS | Sat Night | 30 | Canton
9 | O | T22 | CON | T171 | 233.251 | 170m 12ch | Line E | 234.175 | 170m 59ch | Line D | 0.924 |  | KELTBRAY CBS | Sat Night | 30 | Canton
9 | O | T22 | CON | T170 | 233.251 | 170m 12ch | Line D | 234.175 | 170m 59ch | Line D | 0.924 |  | KELTBRAY CBS | Fri Night | 30 | Canton
9 | O | T22 | CON | T169 | 233.251 | 170m 12ch | Line C | 234.232 | 170m 61ch | Line C | 0.981 |  | BBR Wiring Train | Fri Night | 30 | Brickyard
9 | O | T22 | EW | EW-O-4 | 233.251 | 170m 12ch | Line E | 234.81 | 171m 09ch | Line E | 1.559 |  | BBR Wiring | Sat Night | 30 | Canton
9 | O | T23 | CAT/CON | T175 | 233.301 | 170m 14ch | Line C | 233.488 | 170m 24ch | Line B | 0.187 |  | KELTBRAY CBS | Sun Day | 30 | Brickyard
9 | O | T23 | CAT/CON | T176 | 233.301 | 170m 14ch | Line D | 233.488 | 170m 24ch | Line E | 0.187 |  | KELTBRAY CBS | Sat Day | 30 | Canton
9 | O | T23 | CAT/CON | T174 | 233.301 | 170m 14ch | Line A | 234.232 | 170m 60ch | Line A | 0.931 | B | BBR Wiring Train | Sat Day | 30 | Brickyard
9 | O | T23 | CAT/CON | T179 | 233.754 | 170m 37ch | Line B | 233.898 | 170m 44ch | Line C | 0.144 |  | KELTBRAY CBS | Sat Day | 30 | Brickyard
9 | O | T23 | CON | T178 | 233.754 | 170m 37ch | Platform Loop | 233.96 | 170m 47ch | Line C | 0.206 |  | KELTBRAY CBS | Sun Day | 30 | Brickyard
9 | O | T23 | CAT/CON | T183 | 234.175 | 170m 58ch | Line A | 235.08 | 171m 22ch | Line A | 0.905 |  | BBR Wiring Train | Sat Night | 30 | Brickyard
9 | O | T23 | CAT/CON | T184 | 234.341 | 170m 66ch | Line A | 234.982 | 170m 58ch | Brickyard Siding | 0.641 |  | BBR Wiring Train | Sun Day | 30 | Brickyard

## Registration - EE9
ID: | Route Section | Area | CU: | WR: | Str No: | Mileage | Rd: | Task | Task description: | Rework | Comments | Time(min): | Hold Point: | Started: | Completed: | Priority: | Team | Planned Day
ADD | RS8 | E | Y08 | S01, | 197.333 | 15m 45ch | Up Tunnel | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y08 | S04, | 198.137 | 16m 05ch | Dn Tunnel | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y08 | S03, | 198.137 | 16m 05ch | Up Tunnel | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y08 | S05, | 198.137 | 16m 05ch | Up Tunnel Loop | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
80682 | RS8 | E | Y09 | S17, | 198.426 | 16m 19ch | Up Tunnel Loop | F.Reg | Complete TX Final Reg |  | Final Reg Complete Paperwork Missing | 60 | N | N | N |  | STJ Car Park | Friday Night
30337 | RS8 | E | Y09 | S17, | 198.473 | 16m 22ch | Up Tunnel Loop | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N |  | STJ Car Park | Friday Night
30343 | RS8 | E | Y09 | S17, | 198.529 | 16m 25ch | Up Tunnel Loop | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y09 | S11, | 198.529 | 16m 25ch | X/Over | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
30351 | RS8 | E | Y09 | S17, | 198.582 | 16m 27ch | Dn Tunnel | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N |  | STJ Car Park | Friday Night
30356 | RS8 | E | Y09 | S17, | 198.626 | 16m 29ch | Dn Tunnel | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N |  | STJ Car Park | Friday Night
81115 | RS8 | E | Y09 | S17, | 198.665 | 16m 32ch | Dn Tunnel | F.Reg | Complete Fixed Anchor Final Reg |  | Final Reg Complete Paperwork Missing | 60 | N | N | N |  | STJ Car Park | Friday Night
80684 | RS8 | E | Y09 | S17, | 198.665 | 16m 32ch | Dn Tunnel | F.Reg | Complete TX Final Reg |  | Final Reg Complete Paperwork Missing | 60 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y09 | S17, | 198.665 | 16m 32ch | Dn Tunnel | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
30387 | RS8 | E | Y09 | S13, | 198.932 | 16m 45ch | Dn Tunnel | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N | N | STJ Car Park | Friday Night
30395 | RS8 | E | Y09 | S13, | 198.969 | 16m 47ch | Dn Tunnel | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N |  | STJ Car Park | Friday Night
30400 | RS8 | E | Y09 | S13, | 199.009 | 16m 49ch | Dn Tunnel | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N |  | STJ Car Park | Friday Night
30405 | RS8 | E | Y09 | S13, | 199.069 | 16m 52ch | Dn Relief | F.Reg | Complete Final Registration |  | Final Reg Complete Paperwork Missing | 45 | N | N | N |  | STJ Car Park | Friday Night
80691 | RS8 | E | Y09 | S13, | 199.124 | 16m 54ch | Dn Tunnel | F.Reg | Complete TX Final Reg |  | Final Reg Complete Paperwork Missing | 60 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y09 | S16, | 199.124 | 16m 54ch | Dn Relief | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | 0 | Friday Night
ADD | RS8 | E | Y09 | S15, | 199.124 | 16m 54ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | 0 | Friday Night
ADD | RS8 | E | Y09 | S13, | 199.124 | 16m 54ch | Dn Tunnel | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y09 | S12, | 199.124 | 16m 54ch | Up Tunnel | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Car Park | Friday Night
ADD | RS8 | E | Y10 | S24, | 199.285 | 149m 04ch | X/O Tunnel | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | 0 | Friday Night
ADD | RS8 | E | Y10 | S20, | 199.406 | 149m 10ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | 0 | Friday Night
30469 | RS8 | E | Y10 | S22, | 199.595 | 149m 20ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | STJ Reliefs | Friday Night
ADD | RS8 | E | Y11 | S22, | 199.866 | 149m 33ch | Dn Relief | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Reliefs | Friday Night
ADD | RS8 | E | Y11 | S21, | 199.866 | 149m 33ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | STJ Reliefs | Friday Night
ADD | RS8 | E | Y11 | S27, | 199.866 | 149m 33ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | 0 | Friday Night
ADD | RS8 | E | Y11 | S34, | 200.679 | 149m 73ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | 0 | Friday Night
ADD | RS8 | E | Y11 | S33, | 200.679 | 149m 73ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | 0 | Friday Night
71001 | RS8 | F | Y14 | S60, | 203.082 | 151m 33ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Redwick | Sunday Day
70997 | RS8 | F | Y14 | S60, | 203.082 | 151m 33ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Redwick | Sunday Day
80734 | RS8 | F | Y14 | S60, | 203.082 | 151m 33ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Redwick | Sunday Day
71005 | RS8 | F | Y14 | S60, | 203.082 | 151m 33ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Redwick | Sunday Day
19830 | RS8 | F | Y14 | S60, | 203.092 | 151m 36ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Redwick | Sunday Day
19289 | RS8 | F | Y14 | S60, | 203.092 | 151m 36ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Redwick | Sunday Day
30818 | RS8 | F | Y14 | S60, | 203.137 | 151m 36ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30824 | RS8 | F | Y15 | S60, | 203.198 | 151m 39ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30828 | RS8 | F | Y15 | S60, | 203.253 | 151m 41ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30832 | RS8 | F | Y15 | S60, | 203.306 | 151m 44ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30836 | RS8 | F | Y15 | S60, | 203.369 | 151m 47ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30840 | RS8 | F | Y15 | S60, | 203.432 | 151m 50ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30846 | RS8 | F | Y15 | S60, | 203.495 | 151m 53ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30848 | RS8 | F | Y15 | S60, | 203.558 | 151m 57ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30854 | RS8 | F | Y15 | S60, | 203.621 | 151m 60ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30858 | RS8 | F | Y15 | S60, | 203.655 | 151m 61ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30874 | RS8 | F | Y15 | S60, | 203.709 | 151m 64ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30878 | RS8 | F | Y15 | S60, | 203.753 | 151m 66ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
30882 | RS8 | F | Y15 | S60, | 203.811 | 151m 69ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
19838 | RS8 | F | Y15 | S66, | 203.869 | 151m 72ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 1 | Saturday Day
19837 | RS8 | F | Y15 | S65, | 203.869 | 151m 72ch | Up Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 2 | Saturday Day
19297 | RS8 | F | Y15 | S66, | 203.869 | 151m 72ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 1 | Saturday Day
19296 | RS8 | F | Y15 | S65, | 203.869 | 151m 72ch | Up Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 2 | Saturday Day
80742 | RS8 | F | Y15 | S66, | 203.869 | 151m 72ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 1 | Saturday Day
80741 | RS8 | F | Y15 | S65, | 203.869 | 151m 72ch | Up Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 2 | Saturday Day
30886 | RS8 | F | Y15 | S60, | 203.869 | 151m 72ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redwick | Sunday Day
20379 | RS8 | F | Y15 | S66, | 203.869 | 151m 72ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 1 | Saturday Day
20378 | RS8 | F | Y15 | S65, | 203.869 | 151m 72ch | Up Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 2 | Saturday Day
19842 | RS8 | F | Y15 | S60, | 203.924 | 151m 75ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Redwick | Sunday Day
19301 | RS8 | F | Y15 | S60, | 203.924 | 151m 75ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Redwick | Sunday Day
80746 | RS8 | F | Y15 | S60, | 203.924 | 151m 75ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Redwick | Sunday Day
30890 | RS8 | F | Y15 | S66, | 203.924 | 151m 75ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30889 | RS8 | F | Y15 | S65, | 203.924 | 151m 75ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
ADD | RS8 | F | Y15 | S60, | 203.924 | 151m 75ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Redwick | Sunday Day
20383 | RS8 | F | Y15 | S60, | 203.924 | 151m 75ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Redwick | Sunday Day
30895 | RS8 | G | Y16 | S65, | 203.979 | 151m 77ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30892 | RS8 | G | Y16 | S66, | 203.979 | 151m 77ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30899 | RS8 | G | Y16 | S65, | 204.037 | 152m 00ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30896 | RS8 | G | Y16 | S66, | 204.037 | 152m 00ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30902 | RS8 | G | Y16 | S66, | 204.067 | 152m 02ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30901 | RS8 | G | Y16 | S65, | 204.067 | 152m 02ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30907 | RS8 | G | Y16 | S66, | 204.125 | 152m 05ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30906 | RS8 | G | Y16 | S65, | 204.125 | 152m 05ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30910 | RS8 | G | Y16 | S66, | 204.185 | 152m 08ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30909 | RS8 | G | Y16 | S65, | 204.185 | 152m 08ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30915 | RS8 | G | Y16 | S66, | 204.248 | 152m 11ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30914 | RS8 | G | Y16 | S65, | 204.248 | 152m 11ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30920 | RS8 | G | Y16 | S66, | 204.311 | 152m 14ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30919 | RS8 | G | Y16 | S65, | 204.311 | 152m 14ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30925 | RS8 | G | Y16 | S65, | 204.374 | 152m 17ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30923 | RS8 | G | Y16 | S66, | 204.374 | 152m 17ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30928 | RS8 | G | Y16 | S66, | 204.419 | 152m 19ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30927 | RS8 | G | Y16 | S65, | 204.419 | 152m 19ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30934 | RS8 | G | Y16 | S66, | 204.482 | 152m 22ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30933 | RS8 | G | Y16 | S65, | 204.482 | 152m 22ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30937 | RS8 | G | Y16 | S66, | 204.534 | 152m 25ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30936 | RS8 | G | Y16 | S65, | 204.534 | 152m 25ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30940 | RS8 | G | Y16 | S65, | 204.569 | 152m 27ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30941 | RS8 | G | Y16 | S66, | 204.576 | 152m 27ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30946 | RS8 | G | Y16 | S66, | 204.614 | 152m 29ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30948 | RS8 | G | Y16 | S65, | 204.635 | 152m 30ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30951 | RS8 | G | Y16 | S66, | 204.652 | 152m 31ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30954 | RS8 | G | Y16 | S66, | 204.686 | 152m 33ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30953 | RS8 | G | Y16 | S65, | 204.686 | 152m 33ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30959 | RS8 | G | Y16 | S65, | 204.743 | 152m 35ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30958 | RS8 | G | Y16 | S66, | 204.743 | 152m 35ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30963 | RS8 | G | Y16 | S65, | 204.8 | 152m 38ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30962 | RS8 | G | Y16 | S66, | 204.8 | 152m 38ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30967 | RS8 | G | Y16 | S66, | 204.857 | 152m 41ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30966 | RS8 | G | Y16 | S65, | 204.857 | 152m 41ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
30971 | RS8 | G | Y16 | S66, | 204.914 | 152m 44ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Saturday Day
30970 | RS8 | G | Y16 | S65, | 204.914 | 152m 44ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Saturday Day
19849 | RS8 | G | Y16 | S66, | 204.969 | 152m 47ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 1 | Saturday Day
19848 | RS8 | G | Y16 | S65, | 204.969 | 152m 47ch | Up Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 2 | Saturday Day
19308 | RS8 | G | Y16 | S66, | 204.969 | 152m 47ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 1 | Saturday Day
19307 | RS8 | G | Y16 | S65, | 204.969 | 152m 47ch | Up Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 2 | Saturday Day
80753 | RS8 | G | Y16 | S66, | 204.969 | 152m 47ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 1 | Saturday Day
80752 | RS8 | G | Y16 | S65, | 204.969 | 152m 47ch | Up Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 2 | Saturday Day
ADD | RS8 | G | Y16 | S66, | 204.969 | 152m 47ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 1 | Saturday Day
ADD | RS8 | G | Y16 | S65, | 204.969 | 152m 47ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 2 | Saturday Day
20390 | RS8 | G | Y16 | S66, | 204.969 | 152m 47ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 1 | Saturday Day
20389 | RS8 | G | Y16 | S65, | 204.969 | 152m 47ch | Up Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 2 | Saturday Day
ADD | RS8 | H1 | Y18 | S78, | 207.125 | 153m 74ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 3 | Mon
19873 | RS8 | H1 | Y19 | S91, | 208.115 | 154m 43ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 2 | Mon
20414 | RS8 | H1 | Y19 | S91, | 208.115 | 154m 43ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 2 | Mon
ADD | RS8 | H1 | Y19 | S85, | 208.17 | 154m 46ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 2 | Wed
ADD | RS8 | H1 | Y19 | S84, | 208.17 | 154m 46ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 3 | Tue
31289 | RS8 | H1 | Y20 | S91, | 209.097 | 155m 12ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Mon
31293 | RS8 | H1 | Y20 | S91, | 209.16 | 155m 15ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Mon
19885 | RS8 | H1 | Y20 | S91, | 209.215 | 155m 18ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 2 | Mon
19344 | RS8 | H1 | Y20 | S91, | 209.215 | 155m 18ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 2 | Mon
80785 | RS8 | H1 | Y20 | S91, | 209.215 | 155m 18ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 2 | Mon
ADD | RS8 | H1 | Y20 | S91, | 209.215 | 155m 18ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 2 | Mon
20426 | RS8 | H1 | Y20 | S91, | 209.215 | 155m 18ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 2 | Mon
ADD | RS8 | H1 | Y21 | S96, | 210.255 | 155m 69ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 3 | Tue
19922 | RS8 | H2/3 | Y24 | S126, | 212.158 | 157m 04ch | Up Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 2 | Sunday Day
80816 | RS8 | H2/3 | Y24 | S126, | 212.158 | 157m 04ch | Up Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 2 | Sunday Day
20463 | RS8 | H2/3 | Y24 | S126, | 212.158 | 157m 04ch | Up Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 2 | Sunday Day
31581 | RS8 | H2/3 | Y24 | S126, | 212.215 | 157m 07ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31586 | RS8 | H4/5 | Y25 | S126, | 212.263 | 157m 09ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31592 | RS8 | H4/5 | Y25 | S126, | 212.303 | 157m 11ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
58077 | RS8 | H4/5 | Y25 | S126, | 212.347 | 157m 14ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
28167 | RS8 | H4/5 | Y25 | S126, | 212.4 | 157m 16ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31609 | RS8 | H4/5 | Y25 | S126, | 212.463 | 157m 19ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31614 | RS8 | H4/5 | Y25 | S126, | 212.526 | 157m 22ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31619 | RS8 | H4/5 | Y25 | S126, | 212.589 | 157m 25ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31625 | RS8 | H4/5 | Y25 | S126, | 212.652 | 157m 28ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31629 | RS8 | H4/5 | Y25 | S126, | 212.715 | 157m 32ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31634 | RS8 | H4/5 | Y25 | S126, | 212.778 | 157m 35ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31639 | RS8 | H4/5 | Y25 | S126, | 212.841 | 157m 38ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31644 | RS8 | H4/5 | Y25 | S126, | 212.904 | 157m 41ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31649 | RS8 | H4/5 | Y25 | S126, | 212.957 | 157m 44ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31654 | RS8 | H4/5 | Y25 | S126, | 213.02 | 157m 47ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
19933 | RS8 | H4/5 | Y25 | W39, | 213.076 | 157m 50ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
19932 | RS8 | H4/5 | Y25 | W38, | 213.076 | 157m 50ch | Up Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 2 | Sunday Day
19392 | RS8 | H4/5 | Y25 | W39, | 213.076 | 157m 50ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
19391 | RS8 | H4/5 | Y25 | W38, | 213.076 | 157m 50ch | Up Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 2 | Sunday Day
80822 | RS8 | H4/5 | Y25 | W39, | 213.076 | 157m 50ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 1 | Sunday Day
80821 | RS8 | H4/5 | Y25 | W38, | 213.076 | 157m 50ch | Up Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 2 | Sunday Day
31659 | RS8 | H4/5 | Y25 | S126, | 213.076 | 157m 50ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
20474 | RS8 | H4/5 | Y25 | W39, | 213.076 | 157m 50ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 1 | Sunday Day
20473 | RS8 | H4/5 | Y25 | W38, | 213.076 | 157m 50ch | Up Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 2 | Sunday Day
19936 | RS8 | H4/5 | Y25 | S126, | 213.135 | 157m 52ch | Up Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 2 | Sunday Day
19395 | RS8 | H4/5 | Y25 | S126, | 213.135 | 157m 52ch | Up Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 2 | Sunday Day
80826 | RS8 | H4/5 | Y25 | S126, | 213.135 | 157m 52ch | Up Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 2 | Sunday Day
31665 | RS8 | H4/5 | Y25 | W39, | 213.135 | 157m 52ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31664 | RS8 | H4/5 | Y25 | W38, | 213.135 | 157m 52ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
ADD | RS8 | H4/5 | Y25 | S126, | 213.135 | 157m 52ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 2 | Sunday Day
20477 | RS8 | H4/5 | Y25 | S126, | 213.135 | 157m 52ch | Up Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 2 | Sunday Day
31670 | RS8 | H4/5 | Y25 | W39, | 213.173 | 157m 54ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31669 | RS8 | H4/5 | Y25 | W38, | 213.173 | 157m 54ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31676 | RS8 | H4/5 | Y25 | W39, | 213.223 | 157m 57ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31675 | RS8 | H4/5 | Y25 | W38, | 213.223 | 157m 57ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
58197 | RS8 | H4/5 | Y25 | W39, | 213.273 | 157m 59ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
58196 | RS8 | H4/5 | Y25 | W38, | 213.273 | 157m 59ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
67309 | RS8 | H4/5 | Y25 | W39, | 213.308 | 157m 61ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
67308 | RS8 | H4/5 | Y25 | W38, | 213.308 | 157m 61ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
67359 | RS8 | H4/5 | Y25 | W39, | 213.338 | 157m 62ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
67358 | RS8 | H4/5 | Y25 | W38, | 213.338 | 157m 62ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
49549 | RS8 | H4/5 | Y25 | W44, | 213.378 | 157m 74ch | X/Over Main-Relief | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | East USK | Saturday Night
49543 | RS8 | H4/5 | Y25 | W40/W44 | 213.378 | 157m 64ch | Up Relief | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | East USK | Saturday Night
19943 | RS8 | H4/5 | Y25 | W45, | 213.378 | 157m 64ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
19402 | RS8 | H4/5 | Y25 | W45, | 213.378 | 157m 64ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
31694 | RS8 | H4/5 | Y25 | W44, | 213.378 | 157m 64ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | East USK | Saturday Night
31693 | RS8 | H4/5 | Y25 | W39, | 213.378 | 157m 64ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31692 | RS8 | H4/5 | Y25 | W38, | 213.378 | 157m 64ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
80832 | RS8 | H4/5 | Y25 | W45, | 213.378 | 157m 64ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 1 | Sunday Day
20484 | RS8 | H4/5 | Y25 | W45, | 213.378 | 157m 64ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 1 | Sunday Day
85144 | RS8 | H4/5 | Y25 | W39/W44 | 213.433 | 157m 67ch | Dn Main | In Span | Install Cross Dropper x2 |  |  | 30 | N | N | N |  | East USK | Saturday Night
31700 | RS8 | H4/5 | Y25 | W44, | 213.433 | 157m 67ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | East USK | Saturday Night
31699 | RS8 | H4/5 | Y25 | W39, | 213.433 | 157m 67ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31697 | RS8 | H4/5 | Y25 | W38, | 213.433 | 157m 67ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31698 | RS8 | H4/5 | Y25 | W45, | 213.433 | 157m 67ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
58217 | RS8 | H4/5 | Y25 | W44, | 213.479 | 157m 70ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | East USK | Saturday Night
58216 | RS8 | H4/5 | Y25 | W39, | 213.479 | 157m 70ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
58214 | RS8 | H4/5 | Y25 | W38, | 213.479 | 157m 70ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
58215 | RS8 | H4/5 | Y25 | W45, | 213.479 | 157m 70ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
85146 | RS8 | H4/5 | Y25 | W45/W39 | 213.523 | 157m 72ch | Dn Main | In Span | Install Cross Dropper x2 |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
84945 | RS8 | H4/5 | Y25 | W45, | 213.523 | 157m 72ch | X/Over Main | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Biston Team 1 | Sunday Day
31718 | RS8 | H4/5 | Y25 | W44, | 213.523 | 157m 72ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | East USK | Saturday Night
31717 | RS8 | H4/5 | Y25 | W39, | 213.523 | 157m 72ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31715 | RS8 | H4/5 | Y25 | W38, | 213.523 | 157m 72ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31716 | RS8 | H4/5 | Y25 | W45, | 213.523 | 157m 72ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
67402 | RS8 | H4/5 | Y25 | W44, | 213.546 | 157m 73ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | East USK | Saturday Night
67401 | RS8 | H4/5 | Y25 | W39, | 213.546 | 157m 73ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
67399 | RS8 | H4/5 | Y25 | W38, | 213.546 | 157m 73ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
67400 | RS8 | H4/5 | Y25 | W45, | 213.546 | 157m 73ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
49550 | RS8 | H4/5 | Y25 | W38/W45 | 213.568 | 157m 74ch | Up Main | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | Biston Team 2 | Sunday Day
31727 | RS8 | H4/5 | Y25 | W39, | 213.568 | 157m 74ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31725 | RS8 | H4/5 | Y25 | W38, | 213.568 | 157m 74ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31726 | RS8 | H4/5 | Y25 | W45, | 213.568 | 157m 74ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
58289 | RS8 | H4/5 | Y25 | W39, | 213.599 | 157m 76ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
58288 | RS8 | H4/5 | Y25 | W38, | 213.599 | 157m 76ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
67456 | RS8 | H4/5 | Y25 | W39, | 213.639 | 157m 77ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
67454 | RS8 | H4/5 | Y25 | W38, | 213.639 | 157m 77ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
67455 | RS8 | H4/5 | Y25 | W45, | 213.639 | 157m 77ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
19946 | RS8 | I | Y26 | S145, | 213.668 | 40m 73ch | Dn Hereford | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Team 1 Maindee | Sunday Day
19405 | RS8 | I | Y26 | S145, | 213.668 | 40m 73ch | Dn Hereford | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Team 1 Maindee | Sunday Day
19944 | RS8 | I | Y26 | S144, | 213.668 | 40m 73ch | Up Hereford | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Team 1 Maindee | Saturday Day
19403 | RS8 | I | Y26 | S144, | 213.668 | 40m 73ch | Dn | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Team 1 Maindee | Saturday Day
80834 | RS8 | I | Y26 | S145, | 213.668 | 40m 73ch | Dn Hereford | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Team 1 Maindee | Sunday Day
80833 | RS8 | I | Y26 | S144, | 213.668 | 40m 73ch | Up Hereford | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Team 1 Maindee | Saturday Day
20487 | RS8 | I | Y26 | S145, | 213.668 | 40m 73ch | Dn Hereford | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Team 1 Maindee | Sunday Day
20485 | RS8 | I | Y26 | S144, | 213.668 | 40m 73ch | Up Hereford | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Team 1 Maindee | Saturday Day
81142 | RS8 | H4/5 | Y25 | W45, | 213.669 | 157m 79ch | Up Main | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | Biston Team 1 | Sunday Day
31744 | RS8 | H4/5 | Y25 | W39, | 213.669 | 157m 79ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31743 | RS8 | H4/5 | Y25 | W38, | 213.669 | 157m 79ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31749 | RS8 | I | Y26 | S145, | 213.691 | 40m 73ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31747 | RS8 | I | Y26 | S144, | 213.691 | 40m 73ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31751 | RS8 | H4/5 | Y25 | W39, | 213.704 | 158m 01ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31750 | RS8 | H4/5 | Y25 | W38, | 213.704 | 158m 01ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31756 | RS8 | I | Y26 | S145, | 213.714 | 40m 73ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31754 | RS8 | I | Y26 | S144, | 213.714 | 40m 73ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31758 | RS8 | H4/5 | Y25 | W39, | 213.735 | 158m 02ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31757 | RS8 | H4/5 | Y25 | W38, | 213.735 | 158m 02ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31763 | RS8 | I | Y26 | S145, | 213.737 | 40m 73ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31761 | RS8 | I | Y26 | S144, | 213.737 | 40m 73ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31766 | RS8 | I | Y26 | S145, | 213.764 | 41m 56ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31764 | RS8 | I | Y26 | S144, | 213.764 | 41m 56ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
58359 | RS8 | H4/5 | Y25 | W39, | 213.768 | 158m 04ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
58358 | RS8 | H4/5 | Y25 | W38, | 213.768 | 158m 04ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31773 | RS8 | I | Y26 | S145, | 213.788 | 41m 58ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31771 | RS8 | I | Y26 | S144, | 213.788 | 41m 58ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31778 | RS8 | I | Y26 | S145, | 213.803 | 41m 60ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31776 | RS8 | I | Y26 | S144, | 213.803 | 41m 60ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
58399 | RS8 | H4/5 | Y25 | W39, | 213.808 | 157m 72ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
58398 | RS8 | H4/5 | Y25 | W38, | 213.808 | 157m 72ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 2 | Sunday Day
31783 | RS8 | I | Y26 | S145, | 213.833 | 41m 62ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31781 | RS8 | I | Y26 | S144, | 213.833 | 41m 62ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31785 | RS8 | I | Y26 | W39, | 213.838 | 158m 07ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31790 | RS8 | I | Y26 | S145, | 213.849 | 40m 73ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31788 | RS8 | I | Y26 | S144, | 213.849 | 40m 73ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31793 | RS8 | I | Y26 | S145, | 213.872 | 41m 65ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31791 | RS8 | I | Y26 | S144, | 213.872 | 41m 65ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31796 | RS8 | I | Y26 | W39, | 213.881 | 158m 09ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31803 | RS8 | I | Y26 | S145, | 213.897 | 40m 73ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31802 | RS8 | I | Y26 | S144, | 213.897 | 40m 73ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31806 | RS8 | I | Y26 | S145, | 213.916 | 40m 73ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31805 | RS8 | I | Y26 | S144, | 213.916 | 40m 73ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31809 | RS8 | I | Y26 | W39, | 213.923 | 158m 11ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Biston Team 1 | Sunday Day
31816 | RS8 | I | Y26 | S145, | 213.936 | 158m 12ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31815 | RS8 | I | Y26 | S144, | 213.936 | 158m 12ch | Up Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
49569 | RS8 | I | Y26 | S145 | 213.961 | 158m 13ch | Dn Hereford | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Team 1 Maindee | Sunday Day
19955 | RS8 | I | Y26 | W39, | 213.961 | 158m 13ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
19414 | RS8 | I | Y26 | W39, | 213.961 | 158m 13ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
80841 | RS8 | I | Y26 | W39, | 213.961 | 158m 13ch | Dn Main | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Biston Team 1 | Sunday Day
31819 | RS8 | I | Y26 | S145, | 213.961 | 158m 13ch | Dn Hereford | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31817 | RS8 | I | Y26 | S144, | 213.961 | 158m 13ch | Up Hereford (Mains) | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
ADD | RS8 | I | Y26 | W39, | 213.961 | 158m 13ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Biston Team 1 | Sunday Day
20496 | RS8 | I | Y26 | W39, | 213.961 | 158m 13ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Biston Team 1 | Sunday Day
31826 | RS8 | I | Y26 | S145, | 213.981 | 158m 14ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31823 | RS8 | I | Y26 | S144, | 213.981 | 158m 14ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31833 | RS8 | I | Y26 | S145, | 213.997 | 158m 15ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31830 | RS8 | I | Y26 | S144, | 213.997 | 158m 15ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31840 | RS8 | I | Y26 | S145, | 214.022 | 158m 16ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31837 | RS8 | I | Y26 | S144, | 214.022 | 158m 16ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
31848 | RS8 | I | Y26 | S147, | 214.049 | 158m 18ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redstar / Godfrey | Saturday Night
31847 | RS8 | I | Y26 | S145, | 214.049 | 158m 18ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Sunday Day
31844 | RS8 | I | Y26 | S144, | 214.049 | 158m 18ch | Up Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Maindee | Saturday Day
19959 | RS8 | I | Y26 | S152, | 214.076 | 158m 19ch | Dn Main | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Redstar / Godfrey | Saturday Night
19418 | RS8 | I | Y26 | S152, | 214.076 | 158m 19ch | Dn Main | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Redstar / Godfrey | Saturday Night
81144 | RS8 | I | Y26 | S145, | 214.076 | 158m 19ch | Dn Main | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | Team 1 Maindee | Sunday Day
81143 | RS8 | I | Y26 | S144, | 214.076 | 158m 19ch | Up Main | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | Team 1 Maindee | Saturday Day
31851 | RS8 | I | Y26 | S147, | 214.076 | 158m 19ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redstar / Godfrey | Saturday Night
ADD | RS8 | I | Y26 | S144, | 214.076 | 158m 19ch | Up Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Team 1 Maindee | Saturday Day
ADD | RS8 | I | Y26 | S152, | 214.076 | 158m 19ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Redstar / Godfrey | Saturday Night
ADD | RS8 | I | Y26 | S145, | 214.076 | 158m 19ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Team 1 Maindee | Sunday Day
20500 | RS8 | I | Y26 | S152, | 214.076 | 158m 19ch | Dn Main | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Redstar / Godfrey | Saturday Night
19962 | RS8 | I | Y26 | S158, | 214.388 | 158m 35ch | X/Over Mains | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Team 1 Godfrey | Saturday Day
19421 | RS8 | I | Y26 | S158, | 214.388 | 158m 35ch | X/Over Mains | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Team 1 Godfrey | Saturday Day
80848 | RS8 | I | Y26 | S158, | 214.388 | 158m 35ch | X/Over Mains | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Team 1 Godfrey | Saturday Day
ADD | RS8 | I | Y26 | S158, | 214.388 | 158m 35ch | X/Over Mains | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Team 1 Godfrey | Saturday Day
20503 | RS8 | I | Y26 | S158, | 214.388 | 158m 35ch | X/Over Mains | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Team 1 Godfrey | Saturday Day
31948 | RS8 | I | Y26 | S158, | 214.433 | 158m 37ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
31966 | RS8 | I | Y26 | S158, | 214.461 | 158m 38ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
49580 | RS8 | I | Y26 | S158, | 214.482 | 158m 39ch | Dn Main | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Team 1 Godfrey | Saturday Day
31984 | RS8 | I | Y26 | S158, | 214.496 | 158m 40ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
31993 | RS8 | I | Y26 | S158, | 214.533 | 158m 42ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32007 | RS8 | I | Y26 | S158, | 214.59 | 158m 45ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32015 | RS8 | I | Y26 | S158, | 214.647 | 158m 48ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32019 | RS8 | I | Y26 | S158, | 214.682 | 158m 49ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32025 | RS8 | I | Y27 | S158, | 214.721 | 158m 51ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32031 | RS8 | I | Y27 | S158, | 214.748 | 158m 53ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32037 | RS8 | I | Y27 | S158, | 214.784 | 158m 54ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32045 | RS8 | I | Y27 | S158, | 214.818 | 158m 56ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32051 | RS8 | I | Y27 | S158, | 214.86 | 158m 58ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32059 | RS8 | I | Y27 | S158, | 214.891 | 158m 60ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32065 | RS8 | I | Y27 | S158, | 214.914 | 158m 61ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
58039 | RS8 | I | Y27 | S158, | 214.965 | 158m 63ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32079 | RS8 | I | Y27 | S162, | 214.969 | 158m 64ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Redstar / Godfrey | Saturday Night
32084 | RS8 | I | Y27 | S158, | 214.976 | 158m 64ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32085 | RS8 | I | Y27 | S158, | 214.995 | 158m 65ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32094 | RS8 | I | Y27 | S158, | 215.021 | 158m 66ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
49591 | RS8 | I | Y27 | S158, | 215.028 | 158m 66ch | X/Over Main-Relief | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Team 1 Godfrey | Saturday Day
32120 | RS8 | I | Y27 | S158, | 215.046 | 158m 67ch | Down Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32125 | RS8 | I | Y27 | S158, | 215.086 | 158m 69ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
84933 | RS9 | K | Z01 | T10, | 215.839 | 159m 27ch | X/Over Main | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Team 1 Godfrey | Saturday Day
32135 | RS9 | K | Z01 | T10, | 215.839 | 159m 27ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32141 | RS9 | K | Z01 | T10, | 215.883 | 159m 29ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
32148 | RS9 | K | Z01 | T10, | 215.937 | 159m 32ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
19977 | RS9 | K | Z01 | T10, | 215.972 | 159m 33ch | Gaer Branch | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Team 1 Godfrey | Saturday Day
19436 | RS9 | K | Z01 | T10, | 215.972 | 159m 33ch | Gaer Branch | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Team 1 Godfrey | Saturday Day
80865 | RS9 | K | Z01 | T10, | 215.972 | 159m 33ch | Gaer Branch | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Team 1 Godfrey | Saturday Day
ADD | RS9 | K | Z01 | T10, | 215.972 | 159m 33ch | Gaer Branch | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Team 1 Godfrey | Saturday Day
20518 | RS9 | K | Z01 | T10, | 215.972 | 159m 33ch | Gaer Branch | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Team 1 Godfrey | Saturday Day
49615 | RS9 | K | Z01 | T12, | 216.021 | 159m 36ch | Dn Main | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Monsbank Team 1 | Saturday Night
84935 | RS9 | K | Z01 | T12, | 216.021 | 159m 36ch | Dn Main | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Monsbank Team 1 | Saturday Night
32170 | RS9 | K | Z01 | T12, | 216.021 | 159m 36ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Night
32161 | RS9 | K | Z01 | T12, | 216.021 | 159m 36ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Night
ADD | RS9 | K | Z01 | T06, | 216.075 | 159m 38ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Team 1 Godfrey | Saturday Day
32179 | RS9 | K | Z01 | T12, | 216.13 | 159m 41ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Night
32191 | RS9 | K | Z01 | T12, | 216.171 | 159m 43ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Night
32200 | RS9 | K | Z01 | T12, | 216.193 | 159m 44ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Night
81155 | RS9 | K | Z01 | T12, | 216.229 | 159m 46ch | Up Relief | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 1 | Saturday Night
32240 | RS9 | K | Z01 | T06, | 216.422 | 159m 56ch | Dn Main | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Team 1 Godfrey | Saturday Day
19992 | RS9 | K | Z01 | W06, | 216.639 | 159m 66ch | UDG | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
19451 | RS9 | K | Z01 | W06, | 216.639 | 159m 66ch | UDG | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
80879 | RS9 | K | Z01 | W06, | 216.639 | 159m 66ch | UDG | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 1 | Saturday Day
ADD | RS9 | K | Z01 | W06, | 216.639 | 159m 66ch | UDG | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
20533 | RS9 | K | Z01 | W06, | 216.639 | 159m 66ch | UDG | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Monsbank Team 1 | Saturday Day
19996 | RS9 | K | Z01 | W10, | 216.694 | 159m 69ch | Dn Relief | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
19995 | RS9 | K | Z01 | W09, | 216.694 | 159m 69ch | Up Relief | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day
19455 | RS9 | K | Z01 | W10, | 216.694 | 159m 69ch | Dn Relief | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
19454 | RS9 | K | Z01 | W09, | 216.694 | 159m 69ch | Up Relief | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day
80883 | RS9 | K | Z01 | W10, | 216.694 | 159m 69ch | Dn Relief | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 1 | Saturday Day
80882 | RS9 | K | Z01 | W09, | 216.694 | 159m 69ch | Up Relief | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 2 | Saturday Day
32270 | RS9 | K | Z01 | W06, | 216.694 | 159m 69ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
ADD | RS9 | K | Z01 | W10, | 216.694 | 159m 69ch | Dn Relief | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
ADD | RS9 | K | Z01 | W09, | 216.694 | 159m 69ch | Up Relief | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day
20537 | RS9 | K | Z01 | W10, | 216.694 | 159m 69ch | Dn Relief | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Monsbank Team 1 | Saturday Day
20536 | RS9 | K | Z01 | W09, | 216.694 | 159m 69ch | Up Relief | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Monsbank Team 2 | Saturday Day
32275 | RS9 | K | Z01 | W06, | 216.749 | 159m 72ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32274 | RS9 | K | Z01 | W10, | 216.749 | 159m 72ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32273 | RS9 | K | Z01 | W09, | 216.749 | 159m 72ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32280 | RS9 | L | Z02 | W06, | 216.811 | 159m 75ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32279 | RS9 | L | Z02 | W10, | 216.811 | 159m 75ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32278 | RS9 | L | Z02 | W09, | 216.811 | 159m 75ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32285 | RS9 | L | Z02 | W06, | 216.874 | 159m 78ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32284 | RS9 | L | Z02 | W10, | 216.874 | 159m 78ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32283 | RS9 | L | Z02 | W09, | 216.874 | 159m 78ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32294 | RS9 | L | Z02 | W06, | 216.937 | 160m 01ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32293 | RS9 | L | Z02 | W10, | 216.937 | 160m 01ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32292 | RS9 | L | Z02 | W09, | 216.937 | 160m 01ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32303 | RS9 | L | Z02 | W06, | 216.994 | 160m 04ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32302 | RS9 | L | Z02 | W10, | 216.994 | 160m 04ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32301 | RS9 | L | Z02 | W09, | 216.994 | 160m 04ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32310 | RS9 | L | Z02 | W06, | 217.032 | 160m 06ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32309 | RS9 | L | Z02 | W10, | 217.032 | 160m 06ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32308 | RS9 | L | Z02 | W09, | 217.032 | 160m 06ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32319 | RS9 | L | Z02 | W06, | 217.079 | 160m 08ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32318 | RS9 | L | Z02 | W10, | 217.079 | 160m 08ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32317 | RS9 | L | Z02 | W09, | 217.079 | 160m 08ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
85106 | RS9 | L | Z02 | W15/W09 | 217.119 | 160m 10ch | UDG | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
49650 | RS9 | L | Z02 | W14 | 217.119 | 160m 10ch | X/Over Mains | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Ebbw Junction | Saturday Night
81163 | RS9 | L | Z02 | W15, | 217.119 | 160m 10ch | Up Relief | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
81162 | RS9 | L | Z02 | W14, | 217.119 | 160m 10ch | Dn Main | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | Ebbw Junction | Saturday Night
81161 | RS9 | L | Z02 | W05, | 217.119 | 160m 10ch | Up Main | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | EBBW Team 1 | Saturday Day
81160 | RS9 | L | Z02 | W11, | 217.119 | 160m 10ch | Up Main | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | EBBW Team 1 | Saturday Day
32329 | RS9 | L | Z02 | W10, | 217.119 | 160m 10ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32328 | RS9 | L | Z02 | W09, | 217.119 | 160m 10ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32325 | RS9 | L | Z02 | W06, | 217.119 | 160m 10ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
ADD | RS9 | L | Z02 | W15, | 217.119 | 160m 10ch | Up Relief | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
ADD | RS9 | L | Z02 | W14, | 217.119 | 160m 10ch | Dn Main | Panning | Panning Wire Run+FormE+Panning QCS |  |  | 30 | N | N | N |  | Ebbw Junction | Saturday Night
84937 | RS9 | L | Z02 | W06, | 217.139 | 160m 11ch | UDG | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Monsbank Team 1 | Saturday Day
32330 | RS9 | L | Z02 | W06, | 217.139 | 160m 11ch | UDG | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
49652 | RS9 | L | Z02 | W13/W09 | 217.161 | 160m 12ch | Up Relief | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | EBBW Junction | Saturday Night
32337 | RS9 | L | Z02 | W15, | 217.161 | 160m 12ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32336 | RS9 | L | Z02 | W09, | 217.161 | 160m 12ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32339 | RS9 | L | Z02 | W06, | 217.164 | 160m 13ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32338 | RS9 | L | Z02 | W10, | 217.164 | 160m 13ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
49661 | RS9 | L | Z02 | W09/W15 | 217.212 | 160m 15ch | Up Relief | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
49659 | RS9 | L | Z02 | W15, | 217.212 | 160m 15ch | X/Over Relief | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
81166 | RS9 | L | Z02 | W06, | 217.212 | 160m 15ch | Dn Relief | F.Reg | Complete Fixed Anchor Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 1 | Saturday Day
32345 | RS9 | L | Z02 | W10, | 217.212 | 160m 15ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32344 | RS9 | L | Z02 | W15, | 217.212 | 160m 15ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32343 | RS9 | L | Z02 | W09, | 217.212 | 160m 15ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
49663 | RS9 | L | Z02 | W14/W09 | 217.252 | 160m 17ch | Up Relief | In Span | Install Cross Dropper x2 |  |  | 20 | N | N | N |  | Ebbw Junction | Saturday Night
49662 | RS9 | L | Z02 | W10/W15 | 217.252 | 160m 17ch | X/Over Relief | In Span | Install Cross Dropper x2 |  |  | 20 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32351 | RS9 | L | Z02 | W10, | 217.252 | 160m 17ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32350 | RS9 | L | Z02 | W15, | 217.252 | 160m 17ch | X/Over Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32349 | RS9 | L | Z02 | W09, | 217.252 | 160m 17ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32353 | RS9 | L | Z02 | W09, | 217.275 | 160m 18ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32354 | RS9 | L | Z02 | W10, | 217.276 | 160m 18ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32355 | RS9 | L | Z02 | W15, | 217.278 | 160m 18ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32358 | RS9 | L | Z02 | W10, | 217.292 | 160m 19ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32359 | RS9 | L | Z02 | W15, | 217.293 | 160m 19ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32360 | RS9 | L | Z02 | W09, | 217.299 | 160m 19ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32365 | RS9 | L | Z02 | W10, | 217.321 | 160m 20ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32364 | RS9 | L | Z02 | W15, | 217.321 | 160m 20ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32363 | RS9 | L | Z02 | W09, | 217.321 | 160m 20ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32371 | RS9 | L | Z02 | W10, | 217.36 | 160m 22ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32370 | RS9 | L | Z02 | W15, | 217.36 | 160m 22ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32369 | RS9 | L | Z02 | W09, | 217.36 | 160m 22ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
49668 | RS9 | L | Z02 | W15/W10 | 217.397 | 160m 24ch | Up Relief | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32377 | RS9 | L | Z02 | W10, | 217.397 | 160m 24ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32376 | RS9 | L | Z02 | W15, | 217.397 | 160m 24ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32375 | RS9 | L | Z02 | W09, | 217.397 | 160m 24ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
49672 | RS9 | L | Z02 | W15, | 217.425 | 160m 26ch | X/Over | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
49670 | RS9 | L | Z02 | W09/W15 | 217.425 | 160m 26ch | Up Relief | In Span | Install Cross Dropper x2 |  |  | 20 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32382 | RS9 | L | Z02 | W10, | 217.425 | 160m 26ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32381 | RS9 | L | Z02 | W15, | 217.425 | 160m 26ch | X/Over Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32380 | RS9 | L | Z02 | W09, | 217.425 | 160m 26ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32388 | RS9 | L | Z02 | W10, | 217.467 | 160m 28ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32387 | RS9 | L | Z02 | W15, | 217.467 | 160m 28ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32386 | RS9 | L | Z02 | W09, | 217.467 | 160m 28ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
71797 | RS9 | L | Z02 | W15, | 217.527 | 160m 31ch | Up Relief | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
71796 | RS9 | L | Z02 | W15, | 217.527 | 160m 31ch | Up Relief | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
49673 | RS9 | L | Z02 | W09/W18 | 217.527 | 160m 31ch | Up Relief | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | EBBW | Saturday Night
80899 | RS9 | L | Z02 | W15, | 217.527 | 160m 31ch | Up Relief | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
32394 | RS9 | L | Z02 | W10, | 217.527 | 160m 31ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32392 | RS9 | L | Z02 | W09, | 217.527 | 160m 31ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
32391 | RS9 | L | Z02 | W18, | 217.527 | 160m 31ch | Up Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | EBBW | Saturday Night
71798 | RS9 | L | Z02 | W15, | 217.527 | 160m 31ch | Up Relief | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Monsbank Team 2 | Saturday Day/Sunday Day
49675 | RS9 | L | Z02 | W18, | 217.569 | 160m 33ch | X/Over Main-Relief | SI | Install Section Insulator + Register+Complete QCS |  |  | 120 | N | N | N |  | EBBW | Saturday Night
32399 | RS9 | L | Z02 | W10, | 217.569 | 160m 33ch | Dn Relief | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 1 | Saturday Day
32398 | RS9 | L | Z02 | W09, | 217.569 | 160m 33ch | X/Over | F.Reg | Complete Final Registration |  |  | 45 | N | N | N |  | Monsbank Team 2 | Saturday Day
49676 | RS9 | L | Z02 | W06/W10 | 217.594 | 160m 34ch | Goods Loop | In Span | Install Cross Dropper x2 |  |  | 15 | N | N | N |  | Monsbank Team 1 | Saturday Day
20017 | RS9 | L | Z02 | W10, | 217.624 | 160m 35ch | Dn Relief | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
20016 | RS9 | L | Z02 | W09, | 217.624 | 160m 35ch | Up Relief | Set TX - Cat | Install DEAD Section & Set TX to Temp (Catenary) |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day
19476 | RS9 | L | Z02 | W10, | 217.624 | 160m 35ch | Dn Relief | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Monsbank Team 1 | Saturday Day
19475 | RS9 | L | Z02 | W09, | 217.624 | 160m 35ch | Up Relief | Set TX - Con | Install DEAD Section & Set TX to Temp (Contact) |  |  | 30 | N | N | N |  | Monsbank Team 2 | Saturday Day
80904 | RS9 | L | Z02 | W10, | 217.624 | 160m 35ch | Dn Relief | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 1 | Saturday Day
80903 | RS9 | L | Z02 | W09, | 217.624 | 160m 35ch | Up Relief | F.Reg | Complete TX Final Reg |  |  | 60 | N | N | N |  | Monsbank Team 2 | Saturday Day
20558 | RS9 | L | Z02 | W10, | 217.624 | 160m 35ch | Dn Relief | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Monsbank Team 1 | Saturday Day
20557 | RS9 | L | Z02 | W09, | 217.624 | 160m 35ch | Up Relief | ESC - Cat/Con | Install and Crimp TX Bond to Cat/Con |  |  | 15 | N | N | N |  | Monsbank Team 2 | Saturday Day

## Registration - EE8
ID: | Route Section | Area | CU: | WR: | Str No: | Mileage | Rd: | Task | Task description: | Time(min): | Hold Point: | Started: | Completed: | Priority: | Team | Installation Method | Planned Day: | Planned Week | Jobsheet Comments: | Workbank Comments: | Commodity
52346 | RS9 | O | Z21 | T165, |  |  |  | WR - Cat/Con | Straighten all droppers & Registration working from MPA outwards | 45 | N | N | N | [7 empty] | 26 - In-Line Items
52299 | RS9 | O | Z21 | T156, |  |  |  | WR - Cat/Con | Straighten all droppers & Registration working from MPA outwards | 45 | N | N | N | [7 empty] | 26 - In-Line Items
52037 | RS9 | O | Z21 | T165, |  |  |  | WR - Cat/Con | Install Droppers | 45 | N | N | N | [7 empty] | 26 - In-Line Items
80245 | RS9 | P | Z22 | T165, | 234.232 | 170m 60ch | Line B | In Span | Land Contact to tensorex (With Insulator to Equalising Plate) | 60 | N | N | N | [7 empty] | 26 - In-Line Items
80244 | RS9 | P | Z22 | T165, | 234.232 | 170m 60ch | Line B | In Span | Land Catenary to tensorex (With Insulator to Equalising Plate) | 60 | N | N | N | [7 empty] | 26 - In-Line Items
80242 | RS9 | P | Z22 | T165, | 234.232 | 170m 60ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Catenary) | 20 | N | N | N | [7 empty] | 26 - In-Line Items
80241 | RS9 | P | Z22 | T165, | 234.232 | 170m 60ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Contact) | 20 | N | N | N | [7 empty] | 26 - In-Line Items
20185 | RS9 | O | Z22 | T165, | 234.147 | 170m 56ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Catenary) | 20 | N | N | N | NO LONGER REQUIRED CHANGE IN DESIGN RM 08/05/2019 | [6 empty] | 26 - In-Line Items
19644 | RS9 | O | Z22 | T165, | 234.147 | 170m 56ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Contact) | 20 | N | N | N | NO LONGER REQUIRED CHANGE IN DESIGN RM 08/05/2019 | [6 empty] | 26 - In-Line Items
77216 | RS9 | O | Z22 | T165, | 234.079 | 170m 53ch | Line B | In Span - Con | Land Contact to tensorex (With Insulator to Equalising Plate) | 60 | N | N | N | NO LONGER REQUIRED CHANGE IN DESIGN RM 08/05/2019 | [6 empty] | 26 - In-Line Items
77215 | RS9 | O | Z22 | T165, | 234.079 | 170m 53ch | Line B | In Span - Cat | Land Catenary to tensorex (With Insulator to Equalising Plate) | 60 | N | N | N | NO LONGER REQUIRED CHANGE IN DESIGN RM 08/05/2019 | [6 empty] | 26 - In-Line Items
77213 | RS9 | O | Z22 | T165, | 234.079 | 170m 53ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Catenary) | 20 | N | N | N | NO LONGER REQUIRED CHANGE IN DESIGN RM 08/05/2019 | [6 empty] | 26 - In-Line Items
77212 | RS9 | O | Z22 | T165, | 234.079 | 170m 53ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Contact) | 20 | N | N | N | NO LONGER REQUIRED CHANGE IN DESIGN RM 08/05/2019 | [6 empty] | 26 - In-Line Items
49896 | RS9 | O | Z22 | WR-T-165 | 233.999 | 170m 48ch | Line C/Line B | SI | Install Section Insulator | 180 | N | N | N | [7 empty] | 26 - In-Line Items
49884 | RS9 | O | Z22 | WR-T-165 | 233.841 | 170m 41ch | Line C | SI | Install Section Insulator | 180 | N | N | N | [7 empty] | 26 - In-Line Items
49882 | RS9 | O | Z22 | WR-T-165/WR-T-178 | 233.834 | 170m 41ch | Line B | In Span | Single Drape to be installed | 10 | N | N | N | [7 empty] | 26 - In-Line Items
53112 | RS9 | O | Z21 | T165, | 233.488 | 170m 24ch | Line B | WR - Cat | Land Catenary to MPA | 45 | N | N | N | [5 empty] | Cardiff Station | Station Structure | 26 - In-Line Items
49875 | RS9 | O | Z21 | WR-T-165/WR-T-178 | 233.413 | 170m 20ch | Line B | In Span | Single Drape to be installed | 10 | N | N | N | [7 empty] | 26 - In-Line Items
49859 | RS9 | O | Z20 | WR-T-165/WR-T-162 | 232.957 | 169m 77ch | Line B | In Span | Single Drape to be installed | 10 | N | N | N | [7 empty] | 26 - In-Line Items
52858 | RS9 | O | Z20 | T165, | 232.909 | 169m 75ch | Line B | In Span - Con | Land Contact to tensorex (With Insulator to Equalising Plate) | 60 | N | N | N | [7 empty] | 26 - In-Line Items
21246 | RS9 | O | Z20 | T165, | 232.909 | 169m 75ch | Line B | In Span - Cat | Land Catenary to tensorex (With Insulator to Equalising Plate) | 60 | N | N | N | [7 empty] | 26 - In-Line Items
20164 | RS9 | O | Z20 | T165, | 232.909 | 169m 75ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Catenary) | 20 | N | N | N | [7 empty] | 26 - In-Line Items
19623 | RS9 | O | Z20 | T165, | 232.909 | 169m 75ch | Line B | Set TX | Install DEAD Section & Set TX to Temp (Contact) | 20 | N | N | N | [7 empty] | 26 - In-Line Items
49851 | RS9 | O | Z20 | WR-T-156/WR-T-161 | 232.463 | 169m 53ch | Dn Relief | In Span | Double Drapes to be installed | 20 | N | N | N | [7 empty] | 26 - In-Line Items
20153 | RS9 | N2 | Z18 | T156, | 231.959 | 169m 28ch | Dn Relief | Set TX | Install DEAD Section & Set TX to Temp (Catenary) | 20 | N | N | N | [7 empty] | 26 - In-Line Items
19612 | RS9 | N2 | Z18 | T156, | 231.959 | 169m 28ch | Dn Relief | Set TX | Install DEAD Section & Set TX to Temp (Contact) | 20 | N | N | N | [7 empty] | 26 - In-Line Items
81080 | RS9 | P | Z22 | T165, | 234.232 | 170m 60ch | Line B | F.Reg | Complete TX Final Reg | 30 | N | N | N | [7 empty] | 28 - Final Reg
34101 | RS9 | P | Z22 | T165, | 234.175 | 170m 58ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
34090 | RS9 | O | Z22 | T165, | 234.112 | 170m 55ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | NO DESING FOR MAIN STEEL OR SPS. DO NOT PLAN | [6 empty] | 28 - Final Reg
81069 | RS9 | O | Z22 | T165, | 234.079 | 170m 53ch | Line B | F.Reg | Complete Final Reg | 30 | N | N | N | [7 empty] | 28 - Final Reg
34065 | RS9 | O | Z22 | T165, | 234.044 | 170m 51ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
34045 | RS9 | O | Z22 | T165, | 234.006 | 170m 49ch | X/Over | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
34035 | RS9 | O | Z22 | T165, | 233.978 | 170m 48ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | NO DESING FOR MAIN STEEL OR SPS. DO NOT PLAN | [6 empty] | 28 - Final Reg
34023 | RS9 | O | Z22 | T165, | 233.96 | 170m 47ch | X/Over | F.Reg | Complete Final Registration | 40 | N | N | N | NO LONGER REQUIRED CHANGE IN DESIGN RM 08/05/2019 | [6 empty] | 28 - Final Reg
34007 | RS9 | O | Z22 | T165, | 233.921 | 170m 45ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33975 | RS9 | O | Z22 | T165, | 233.863 | 170m 42ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33964 | RS9 | O | Z22 | T165, | 233.837 | 170m 41ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33960 | RS9 | O | Z22 | T165, | 233.827 | 170m 41ch | X/Over | F.Reg | Complete Final Registration | 40 | N | N | N | NO LONGER REQUIRED CHANGE TO DESIGN RM 07/05/2019 | [6 empty] | 28 - Final Reg
33947 | RS9 | O | Z22 | T165, | 233.808 | 170m 40ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33937 | RS9 | O | Z21 | T165, | 233.754 | 170m 37ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | NO DESING FOR MAIN STEEL OR SPS. DO NOT PLAN |  |  |  |  | Cardiff Station | Station Structure | 28 - Final Reg
33926 | RS9 | O | Z21 | T165, | 233.695 | 170m 34ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Cardiff Station | Station Structure | 28 - Final Reg
33916 | RS9 | O | Z21 | T165, | 233.641 | 170m 31ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Cardiff Station | Station Structure | 28 - Final Reg
33909 | RS9 | O | Z21 | T165, | 233.582 | 170m 28ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Cardiff Station | Station Structure | 28 - Final Reg
33902 | RS9 | O | Z21 | T165, | 233.526 | 170m 26ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Cardiff Station | Station Structure | 28 - Final Reg
33896 | RS9 | O | Z21 | T165, | 233.488 | 170m 24ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Cardiff Station | Station Structure | 28 - Final Reg
33887 | RS9 | O | Z21 | T165, | 233.465 | 170m 23ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Cardiff Station | Station Structure | 28 - Final Reg
33877 | RS9 | O | Z21 | T165, | 233.434 | 170m 21ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33870 | RS9 | O | Z21 | T165, | 233.423 | 170m 20ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33863 | RS9 | O | Z21 | T165, | 233.413 | 170m 20ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
67566 | RS9 | O | Z21 | T165, | 233.395 | 170m 19ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33846 | RS9 | O | Z21 | T165, | 233.377 | 170m 18ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33834 | RS9 | O | Z21 | T165, | 233.362 | 170m 17ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33822 | RS9 | O | Z21 | T165, | 233.34 | 170m 16ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33819 | RS9 | O | Z21 | T165, | 233.321 | 170m 15ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33813 | RS9 | O | Z21 | T165, | 233.301 | 170m 14ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33808 | RS9 | O | Z21 | T165, | 233.251 | 170m 12ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [6 empty] | Bespoke Structure | 28 - Final Reg
33803 | RS9 | O | Z21 | T165, | 233.208 | 170m 10ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [6 empty] | Bespoke Structure | 28 - Final Reg
33798 | RS9 | O | Z21 | T165, | 233.157 | 170m 07ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [6 empty] | Bespoke Structure | 28 - Final Reg
33793 | RS9 | O | Z21 | T165, | 233.109 | 170m 05ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [6 empty] | Bespoke Structure | 28 - Final Reg
33788 | RS9 | O | Z21 | T165, | 233.063 | 170m 03ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33779 | RS9 | O | Z21 | T165, | 233.024 | 170m 01ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Bridges | No. 50/51 Intersection Bridge CEJ/ CAM | 28 - Final Reg
33774 | RS9 | O | Z21 | T165, | 233.013 | 170m 00ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Bridges | No. 50/51 Intersection Bridge CEJ/ CAM | 28 - Final Reg
33770 | RS9 | O | Z21 | T165, | 233.002 | 169m 80ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Bridges | No. 50/51 Intersection Bridge CEJ/ CAM | 28 - Final Reg
33767 | RS9 | O | Z21 | T165, | 232.992 | 169m 79ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [5 empty] | Bridges | No. 50/51 Intersection Bridge CEJ/ CAM | 28 - Final Reg
33763 | RS9 | O | Z21 | T165, | 232.965 | 169m 78ch | Line B | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
81050 | RS9 | O | Z20 | T165, | 232.909 | 169m 75ch | Line B | F.Reg | Complete TX Final Reg | 30 | N | N | N | [7 empty] | 28 - Final Reg
81197 | RS9 | O | Z20 | T156, | 232.518 | 169m 55ch | Dn Relief | F.Reg | Complete Fixed Anchor Final Reg | 60 | N | N | N | [7 empty] | 28 - Final Reg
33712 | RS9 | O | Z20 | T156, | 232.463 | 169m 53ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33707 | RS9 | O | Z20 | T156, | 232.408 | 169m 50ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33702 | RS9 | O | Z20 | T156, | 232.351 | 169m 47ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33697 | RS9 | O | Z20 | T156, | 232.311 | 169m 45ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33692 | RS9 | O | Z20 | T156, | 232.286 | 169m 44ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33688 | RS9 | O | Z20 | T156, | 232.261 | 169m 43ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33684 | RS9 | O | Z20 | T156, | 232.23 | 169m 41ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33680 | RS9 | O | Z20 | T156, | 232.175 | 169m 38ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33675 | RS9 | O | Z20 | T156, | 232.125 | 169m 36ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33670 | RS9 | O | Z20 | T156, | 232.069 | 169m 33ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
33665 | RS9 | O | Z20 | T156, | 232.014 | 169m 30ch | Dn Relief | F.Reg | Complete Final Registration | 40 | N | N | N | [7 empty] | 28 - Final Reg
81040 | RS9 | N2 | Z18 | T156, | 231.959 | 169m 28ch | Dn Relief | F.Reg | Complete TX Final Reg | 30 | N | N | N | [7 empty] | 28 - Final Reg