TTP1708 - Freightliner Limited and Freightliner Heavy Haul Ltd Sole Reference Document

- Details of parties

  - The names and addresses of the parties to the reference are as follows:-

- Freightliner Limited, (Company number 03118392) whose Registered Office is at 90 Whitfield Street, London, W1T 4EZ

- Freightliner Heavy Haul Limited (Company number 3831229), whose Registered Office is at 90 Whitfield Street, London, W1T 4EZ.

- Collectively referred to as (“Freightliner”) or ("the Claimant");

- and;

- Network Rail Infrastructure Limited, whose Registered Office is at 1 Eversholt Street, London NW1 2DN (“Network Rail") or ("the Defendant").

- The Claimant’s’ right to bring this reference

  - This matter is referred to a Timetabling Panel ("the Panel") for determination in accordance with Condition D5.1 of the Network Code.

- Contents of reference

- This Sole Reference includes:-

    - The subject matter of the dispute in Section 4;

    - A detailed explanation of the issues in dispute in Section 5;

    - In Section 6, the decisions sought from the Panel in respect of

      - legal entitlement, and

      - remedies;

    - Appendices and other supporting material.

- subject matter of dispute

- 4.1 This is a dispute relating to the Decisions made by Network Rail regarding a package of Restrictions of Use (RoU) between Ely North Junction and Peterborough in weeks 23-27 of 2020.

- 4.2 Network Rail approached Freightliner informally in advance of issuing any formal request relating to these RoU, and Freightliner engaged with Network Rail to support this access, providing all train services could be accommodated and a capacity study was carried out to confirm paths were available from origin to destination. It was generally agreed that the possession strategy would be devised once the capacity study had been completed.

- 4.3 On 11th June, Network Rail held a meeting with timetable participants to discuss access between Ely North Junction and Peterborough to replace bridge timbers at Manea, removing a temporary speed restriction that has been in place for some time. The output of this meeting was a ‘box plan’ (See appendix 1 – Manea Status Report) outlining access requirements, including elements of all lines being closed overnight, and single line working past the worksite.

- 4.4 Following the meeting referenced in paragraph 4.3, Network Rail contacted Freightliner to ascertain which services required timing through the RoU. Freightliner duly responded to this on 12th June, providing a high-level overview of which trains needed to run via single line working and which trains could be diverted via alternative routes. (See appendix 2 – email)

- 4.5 On 2nd July Network Rail confirmed paths were available for certain trains, but not all, and that no work had been completed on looking at these paths beyond the area of the possession, as had been requested initially by Freightliner. Freightliner responded to this, requesting variations on timings on the 3rd July, to which Network Rail responded on 9th July, advising that paths beyond the area of the possession had still not been completed.

- 4.6 On 3rd July, Network Rail issued a formal request for access. On the 6th July Freightliner declined this request on the basis of the times for single line working having changed since originally discussed (later confirmed as acceptable), and that Network Rail had not presented sufficient detail on whether capacity was available or not. (see appendix 3 – Proposal: Weeks 23-27 and responses)

- 4.7 Network Rail issued a Decision Notice for this RoU on 15th July, with some significant changes from the original proposal, (see appendix 4 – Decision: Weeks 23-27 and responses) supported by their opinions of the application of the Decision Criteria. (See appendix 5)

- 4.8 A subsequent meeting took place on 29th July between Freightliner and Network Rail, where it was confirmed numerous trains still do not have paths through this RoU. Network Rail are yet to resolve those trains identified as needing further work. (See appendix 6)

- explanation of each issue in dispute and the Claimant’s Arguments to support its Case

- 5.1 Freightliner are generally supportive of Network Rail improving the capability of the railway and removing defects which may present a barrier to being able to run trains in the future or present safety concerns. However, deterioration of the bridge timbers at Manea is a long-standing issue, and Network Rail have failed to address rectification of these in a timely manner, instead only acting when they believe the defect has become a ‘safety critical matter’ (see Network Rail Decision Criteria, and Freightliner comments in paragraph 5.5)

- 5.2 Taking into account paragraph 5.1, Freightliner believe this RoU should have been planned through the Engineering Access Statement at the timescales outlined in D2.2.3, thereby giving sufficient opportunity to work through capacity allocation in a thorough manner, and ensuring all operator queries could be dealt with before the CPPP was published.

- 5.3 As a result of Network Rail not planning to rectify these defects at the correct timescales, instead following the late notice process, it has been necessary for Network Rail to issue a Decision document for these RoU before all queries could be resolved, leaving Freightliner in a position where we will be in breach of commercial contracts with our customers, and an escalation of proceedings is necessary to protect our commercial interests.

- 5.4 Despite requesting information on train service alterations since discussions on these restrictions of use commenced (before any formal request was issued), and having continued to do so since, Network Rail have, to date, been unable to provide details of paths available for all required services for the duration of this restriction of use. Freightliner believe that, in part, this is due to Network Rail not being able to ‘flex’ other operators services on diversionary routes (where a diversion is a possible alternative) as these had already been offered, resulting in less trains being accommodated than would have been the case if planned at the correct timescales.

- 5.5 Freightliner believe that the Decision Criteria table issued by Network Rail to support their Decision document in line with D4.6.2 fails to correctly assess the impact of this RoU on operators, instead focussing on Network Rail’s priorities. These are commented on in more detail below:

- (a) Maintaining, developing and improving the capability of the network: While Freightliner agree with Network Rail that the outcome of this RoU will be beneficial, Network Rail evidence that this is ‘a safety critical issue and a threat to the continued delivery of the timetable.’ however, as per paragraph 5.1, this is a long standing issue accompanied by a long standing temporary speed restriction. Network Rail opinion is that this continues to be a threat to timetable sustainability, but does not make mention of, or imply, any worsening in the condition of these structures to force this short notice possession, which does not align with the evidence. If this is a safety critical issue, Freighliner would have expected a resolution to have been sought before now.

- (b) That the spread of services reflects demand: Network Rail claim a capacity study has been undertaken that seeks to accommodate as many operator aspirations as possible. Network Rail approached Freightliner on 11th June to confirm which services there was demand for, and Freightliner duly informed Network Rail of these requirements. However a number of these services are still not accounted for in the capacity study, and as such the spread of services clearly do not reflect demand. Network Rail have also weighted this as ‘low’ – from Freightliner’s perspective, this is the most important criteria given commercial decisions had already been made based on services previously offered, and it is difficult to see how Network Rail have come to the conclusion that this supports taking the access.

- (e) Maintaining and improving an integrated system of transport for passengers and goods: In their evidence and opinion, Network Rail have failed to account for the need to take account of this criteria during, as well as after, the restriction of use has taken place. No evidence is provided to show that maintaining an integrated system of transport through the restriction of use has been considered.

- (f) The commercial interests of Network Rail (apart from the terms of any maintenance contract entered into or proposed by Network Rail) or any Timetable Participant of which Network Rail is aware: Network Rail acknowledge that timetable participants may have a different opinion to themselves here, but this should be given a higher weighting. As Network Rail are aware that they have been unable to accommodate all services Freightliner require to run (through the findings of the capacity study) it should be clear that proceeding with this RoU will have a negative impact on the commercial interests of the timetable participant. As related to in paragraph 5.3, this will leave Freightliner in breach of customer contracts, and therefore we do not believe this should be weighted towards taking the access. As with (b), Freightliner believe this should be weighted more significantly than ‘Low’ in reaching a conclusion.

- (i) Mitigating the effect on the environment: While Freightliner agree with the evidence provided by Network Rail here, this does not provide reasoning for the possession being taken outside of timescales that should be followed for significant disruptive access such as this. In proposing the restriction of use after T14, Network Rail have been unable to apply flex to other operators’ services on diversionary routes in order to accommodate trains that cannot run via their booked route, instead concluding the trains cannot run. While not acceptable to Freightliner, this will also result in a move to road haulage for traffic that should have been on these trains. Therefore, Network Rail’s failure to plan to the correct timescales will unnecessarily increase the impact on the environment.

- (j) Enabling operators of trains to utilise their asses efficiently: Network Rail have again failed to apply this Criteria to the duration of the restriction of use, instead only looking at possible scenarios that could take place if access is not taken. Given there is no firm evidence to support this opinion, this appears remiss. This RoU takes place over a significant period of time, and, by way of not having had train slots accommodated within the capacity study, Freightliner will be unable to utilise the assets associated with these train slots during this time, which is clearly not efficient.

- 5.6 In compiling the capacity study to support this RoU, Network Rail has provided no evidence as to how it has applied the Decision Criteria in allocating available train slots. It appears that trains have been worked through and allocated capacity in no particular order, and that options for diverting via alternative routes have not necessarily been investigated.

- decision sought from the PANEL

- 6.1 Freightliner asks that the Panel confirm that Restrictions of Use with such a significant impact on timetable participants, where they can reasonably be planned to do so (as we believe is the case here) should be planned through the Engineering Access Statement, and should not be the subject of late notice requests.

- 6.2 Freightliner asks that the Panel should confirm that Network Rail have not applied the decision criteria outlined in D4.6.2 correctly, failing to properly consider the interests of timetable participants, and incorrectly weighting criteria. The outcome of this has been the reaching of a decision to take the RoU.

- 6.3 Freightliner asks that the Panel should confirm that, having failed to accommodate all train services as requested by operators, Network Rail should have reconsidered their proposals for this RoU, and looked at alternative options to complete this work.

- 6.4 Taking into consideration the outcomes of paragraphs 6.1 - 6.3, Freightliner asks the panel to confirm that Network Rail should withdraw it’s Decision document for this RoU, and re-plan this work to take place in line with Engineering Access Statement timescales as per D2.2.3, thereby allowing greater flexibility in altering and diverting services, leading to a reduced impact on the railway.

- Appendices

The Claimant confirms that it has complied with Access Dispute Resolution Rule H21, and that the following attachments are provided with this document:

-Microsoft Excel document (TTP1708 Appendix 1- Manea Status Report) containing initial plan for access

-Microsoft Word document (TTP1708 Appendix 2,3,4,6- Emails) containing email correspondence relating to Appendix 2,3,4 and 6.

-Microsoft Excel document (TTP1708 Appendix 5- Decision Criteria Table) containing Decision Criteria as applied by Network Rail.

Any information only made available after the main submission has been submitted to the Panel will be consecutively numbered, so as to follow on at the conclusion of the previous submission.

- signature

For and on behalf of Freightliner Limited and Freightliner Heavy Haul Limited Signed Print Name Chris Matthews Position Track Access Manager