## Infrastructure Assement Links
1 | Link to Maintenance Schedule | Maintenance Plan'!A1

## Activity Summary
Work type | Amount | Amount of Hours | Assumptions
Procurement of Timber | 100 timbers | 10-12 weeks delivery from the order | Includes drilling of timbers and notching timbers to be pre built in March yard
Build up of panels | 50 pairs | 150 | Building the panels at March 3 hours per panel
Scaffolding | 258 up and 183 down =441 bays | 2205 | 5 hours per bay per team, first 56 hour bock for the install of scaffolding before the works start.
Cable removal from troughing | 594y per road x2= 1188y | 42 | 1x team working on each bridge concurrently, removed in first possession at same time of scaffolding.
Remove GRP | 300 panels to be removed | 50 | 6 panels per timber
Remove Gard-rail | 50 pairs | 50 | 2 x Guard-rail per timber
Remove screws | 51 pairs | 75 | 1h 30mins per pair
Remove Rail | 50 pairs | 50 | Some have a section of 3 pairs of timbers
Cut HDR | 12 per Bay x 50 =600 | 18 | Some have less but work on max 30mins per bay
Remove Timber | 50 pairs | 25 | 30 mins per pair
Steel work repairs | 19 timbers | 19 | Based on not all needing repairs 1813 was the worse bridge
Drill new HDR | 8 extra holes per timber | 50 | 1 hour per pair
Install new timber | 50 pairs | 25 | 30 mins per pair
Drill timber for HDR | 50 pairs | 100 | 2 hours per timber
Bolt down HDR | 50 pairs | 50 | 1 hour per pair
Installion of rail | 50 pairs | 50 | 1 hour per pair
Install GRP | 300 pannels | 50 | 6 panels per timber
Screw down rail | 50 pannels | 150 | 3 hours per pannel
Welding | 80 welds max | 120 | Welds could decrease in blockade
Installion of guard rail | 50 pairs | 50 | 2 x Guard-rail per timber
Stressing | all bridges | 168 | Based on stressing programme
| Total | 3497
Options |  |  |  | Amount of teams
1. 2 x 56 hour blocks to start scaffolding then 14 Day Blockade with 27 hour blocks to finish this also requires 20mph speed until all works are completed, due to works taking place July to Oct and this will be a heat speed due to low CRT |  |  |  | 1x contractor 3xteams
2. 12x 56 hours blocks plus ROTR possessions in between each weekend x8 hours to finish this also requires 20mph speed until all works are completed , due to works taking place July to Oct and this will be a heat speed due to low CRT |  |  |  | 1x contractor 2xteams
3. 5 x 56 hour blocks and 14x 27 hour blocks plus ROTR possessions in between each weekend x8 hours to finish this also requires 20mph speed until all works are completed, due to works taking place July to Oct and this will be a heat speed due to low CRT |  |  |  | 1x contractor 1xteams

## All Forecast
|  | Critical Path |  |  |  | Road Rail Vehicle Volume Calc
Activity | NUOM | Volume | Minimum | Most Likely | Maximum | No. of WT | NUOM | Trailer Load | No. of Trailer | No. of RRV |  | Timing Assumptions
Possession Mobilisation Activities |  | (Rounded)
Take Possession (ML = 25 minutes) |  |  | 15 | 25 | 35
Site 4 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 0 | 0 | 0 | 0 | 0 | Pair | 2 | 0 | 0 |  |  | Use Third Drove as L/E RRAP
Site 4 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2mph travelling time to site) | Miles | 1.8 | 16.2 | 21.6 | 32.4 | 0 | Mile | [5 empty] | Drop to 3 miles per hour walking pace
Site 3 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 5 | 45 | 90 | 187.5 | 0 | Pair | 2 | 0 | 0
Site 3 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2 miles travelling from nearest access) | Miles | 2.3 | 20.7 | 27.6 | 41.4 | 2.3 | Mile
Site 2 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 1.5 | 13.5 | 27 | 56.25 | 6 | Pair | 2 | 3 | 1.5
Site 2 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Site 1 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 1.1 | 9.9 | 19.8 | 41.25 | 2 | Pair | 2 | 1 | 0.5
Site 1 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Volumes Calc
[6 empty] | No. WT | L | Extra | Total
Work Site 1 Down Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 68 | 30.2222 | 30.2222 | 30.2222 | 2 | 9 | 50 | 68 |  |  |  | Assumed 25m either side for Blue Netlon | Includes a contribution for travelling time of RRV
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 60 | 26.6667 | 26.6667 | 26.6667 | 4 | 9 | 0.6 | 60 |  |  | 2 X Rails | Assumes WT L + 20m of Guard Rail
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 18 | 38 | 45 | 70 | 2 | 9 | 1 | 18
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 72 | 12 | 24 | 48 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 72 | 80 | 120 | 144.8 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 18 | 24 | 30 | 50 | 2 | 9 | 1 | 18 |  |  |  | Increase time to reflect 9m timber
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 72 | 120 | 240 | 280 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 18 | 17 | 25 | 44 | 2 | 9 | 1 | 18
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  |  | 2 x Rails | Total of baseplate activity
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 72 | 344 | 432 | 512 | 4 | 9 | 2 | 72 |  |  | 2 x Rails | 20m each side to be unkeyed
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 72 | 344 | 432 | 512 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 68 | 30.2222 | 30.2222 | 30.2222 | 2 | 9 | 50 | 68
Number of Hours required |  |  | 31.5463 | 39.9185 | 49.1319 | [6 empty] | Total mins / 60
Number of days access required |  |  | 1.3144 | 1.6633 | 2.0472 | [6 empty] | Total hrs / 24
Work Site 1 Up Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 180 | 80 | 80 | 80 | 12 | 9 | 0.6 | 180 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 54 | 114 | 135 | 210 | 6 | 9 | 1 | 54
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 216 | 36 | 72 | 144 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 216 | 240 | 360 | 434.4 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 54 | 72 | 90 | 150 | 6 | 9 | 1 | 54
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 216 | 360 | 720 | 840 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 54 | 51 | 75 | 132 | 6 | 9 | 1 | 54
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Number of Hours required |  |  | 93.1574 | 118.2741 | 145.9141
Number of days access required |  |  | 3.8816 | 4.9281 | 6.0798
Work Site 2 Down Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 86 | 38.2222 | 38.2222 | 38.2222 | 4 | 9 | 50 | 86
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 120 | 53.3333 | 53.3333 | 53.3333 | 8 | 9 | 0.6 | 120 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 36 | 76 | 90 | 140 | 4 | 9 | 1 | 36
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 144 | 24 | 48 | 96 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 144 | 160 | 240 | 289.6 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 36 | 48 | 60 | 100 | 4 | 9 | 1 | 36
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 144 | 240 | 480 | 560 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 36 | 34 | 50 | 88 | 4 | 9 | 1 | 36
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 120 | 826.6667 | 960 | 1200 | 8 | 9 | 0.6 | 120 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 120 | 826.6667 | 960 | 1200 | 8 | 9 | 0.6 | 120 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 144 | 688 | 864 | 1024 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 144 | 688 | 864 | 1024 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 86 | 38.2222 | 38.2222 | 38.2222 | 4 | 9 | 50 | 86
Number of Hours required |  |  | 62.3519 | 79.0963 | 97.523
Number of days access required |  |  | 2.598 | 3.2957 | 4.0635
Work Site 2 Up Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 180 | 80 | 80 | 80 | 12 | 9 | 0.6 | 180 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 54 | 114 | 135 | 210 | 6 | 9 | 1 | 54
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 216 | 36 | 72 | 144 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 216 | 240 | 360 | 434.4 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 54 | 72 | 90 | 150 | 6 | 9 | 1 | 54
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 216 | 360 | 720 | 840 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 54 | 51 | 75 | 132 | 6 | 9 | 1 | 54
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Number of Hours required |  |  | 93.1574 | 118.2741 | 145.9141
Number of days access required |  |  | 3.8816 | 4.9281 | 6.0798
Work Site 3 Down Road 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 257 | 114.2222 | 114.2222 | 114.2222 | 23 | 9 | 50 | 257
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 690 | 306.6667 | 306.6667 | 306.6667 | 46 | 9 | 0.6 | 690 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 207 | 437 | 517.5 | 805 | 23 | 9 | 1 | 207
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 828 | 138 | 276 | 552 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 828 | 920 | 1380 | 1665.2 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 207 | 276 | 345 | 575 | 23 | 9 | 1 | 207
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 828 | 1380 | 2760 | 3220 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 207 | 195.5 | 287.5 | 506 | 23 | 9 | 1 | 207
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 690 | 4753.3333 | 5520 | 6900 | 46 | 9 | 0.6 | 690 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 690 | 4753.3333 | 5520 | 6900 | 46 | 9 | 0.6 | 690 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 828 | 3956 | 4968 | 5888 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 828 | 3956 | 4968 | 5888 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 257 | 114.2222 | 114.2222 | 114.2222 | 23 | 9 | 50 | 257
Number of Hours required |  |  | 355.0046 | 451.2852 | 557.2385
Number of days access required |  |  | 14.7919 | 18.8035 | 23.2183
Work Site 3 Up Road Br 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 248 | 110.2222 | 110.2222 | 110.2222 | 22 | 9 | 50 | 248
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 330 | 146.6667 | 146.6667 | 146.6667 | 22 | 9 | 0.6 | 330 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 198 | 418 | 495 | 770 | 22 | 9 | 1 | 198
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 396 | 66 | 132 | 264 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 45mins/m) | M | 396 | 440 | 660 | 796.4 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 198 | 264 | 330 | 550 | 22 | 9 | 1 | 198
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 396 | 660 | 1320 | 1540 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 198 | 187 | 275 | 484 | 22 | 9 | 1 | 198
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 330 | 2273.3333 | 2640 | 3300 | 22 | 9 | 0.6 | 330 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 330 | 2273.3333 | 2640 | 3300 | 22 | 9 | 0.6 | 330 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 396 | 1892 | 2376 | 2816 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 396 | 1892 | 2376 | 2816 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 248 | 110.2222 | 110.2222 | 110.2222 | 22 | 9 | 50 | 248
Number of Hours required |  |  | 178.8796 | 226.8519 | 283.3919
Number of days access required |  |  | 7.4533 | 9.4522 | 11.808
Work Site 4 Down Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 375 | 166.6667 | 166.6667 | 166.6667 | 25 | 9 | 0.6 | 375 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 225 | 475 | 562.5 | 875 | 25 | 9 | 1 | 225
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 450 | 75 | 150 | 300 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 450 | 500 | 750 | 905 | 25 | 9 | 2 | 450 |  |  | 2 x Rails | Assumes 80% of top flange requires repairs
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 45 minutes / Pair) | M | 225 | 300 | 375 | 625 | 25 | 9 | 1 | 225
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 450 | 750 | 1500 | 1750 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 225 | 212.5 | 312.5 | 550 | 25 | 9 | 1 | 225
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  | 108 | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Number of Hours required |  |  | 203.1713 | 257.6852 | 321.9352
Number of days access required |  |  | 8.4655 | 10.7369 | 13.414
Work Site 4 Up Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 375 | 166.6667 | 166.6667 | 166.6667 | 25 | 9 | 0.6 | 375 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 225 | 475 | 562.5 | 875 | 25 | 9 | 1 | 225
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 450 | 500 | 750 | 905 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Number of Hours required |  |  | 180.8796 | 218.7269 | 268.1852
Number of days access required |  |  | 7.5367 | 9.1136 | 11.1744
Clear Site 3 & 4 of RRV's |  | 8 | 120 | 240 | 360
Hand back Worksite to PICOP |  |  | 10 | 15 | 15
Possession Handed Back |  |  | 3 | 5 | 5

## Red Forecast
|  | Critical Path |  |  |  | Road Rail Vehicle Volume Calc
Activity | NUOM | Volume | Minimum | Most Likely | Maximum | No. of WT | NUOM | Trailer Load | No. of Trailer | No. of RRV | Timing Assumptions
Possession Mobilisation Activities |  | (Rounded)
Take Possession (ML = 25 minutes) |  |  | 15 | 25 | 35
Site 4 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 0 | 0 | 0 | 0 | 0 | Pair | 2 | 0 | 0 |  | Use Third Drove as L/E RRAP
Site 4 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2mph travelling time to site) | Miles | 1.8 | 16.2 | 21.6 | 32.4 | 0 | Mile |  |  |  |  | Drop to 3 miles per hour walking pace
Site 3 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 5 | 45 | 90 | 187.5 | 0 | Pair | 2 | 0 | 0
Site 3 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2 miles travelling from nearest access) | Miles | 2.3 | 20.7 | 27.6 | 41.4 | 2.3 | Mile
Site 2 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 1.5 | 13.5 | 27 | 56.25 | 6 | Pair | 2 | 3 | 1.5
Site 2 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Site 1 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 1.1 | 9.9 | 19.8 | 41.25 | 2 | Pair | 2 | 1 | 0.5
Site 1 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Volumes Calc
[6 empty] | No. WT | L | Extra | Total
Work Site 1 Down Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 18 | 8 | 8 | 8 | 2 | 9 | 0 | 18 |  |  | Assumed 25m either side for Blue Netlon | Includes a contribution for travelling time of RRV
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 60 | 26.6667 | 26.6667 | 26.6667 | 4 | 9 | 0.6 | 60 |  | 2 X Rails | Assumes WT L + 20m of Guard Rail
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 18 | 38 | 45 | 70 | 2 | 9 | 1 | 18
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 36 | 6 | 12 | 24 | 4 | 9 | 1 | 36 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 36 | 40 | 60 | 72.4 | 4 | 9 | 1 | 36 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 18 | 24 | 30 | 50 | 2 | 9 | 1 | 18 |  |  | Increase time to reflect 9m timber
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 36 | 60 | 120 | 140 | 4 | 9 | 1 | 36 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 18 | 17 | 25 | 44 | 2 | 9 | 1 | 18
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  | 2 x Rails | Total of baseplate activity
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 36 | 172 | 216 | 256 | 4 | 9 | 1 | 36 |  | 2 x Rails | 20m each side to be unkeyed
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 36 | 172 | 216 | 256 | 4 | 9 | 1 | 36 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 18 | 8 | 8 | 8 | 2 | 9 | 0 | 18
Number of Hours required |  |  | 23.3056 | 28.7778 | 35.9178 | [5 empty] | Total mins / 60
Number of days access required |  |  | 0.97106 | 1.1991 | 1.4966 | [5 empty] | Total hrs / 24
Work Site 1 Up Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 18 | 8 | 8 | 8 | 2 | 9 | 0 | 18
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 60 | 26.6667 | 26.6667 | 26.6667 | 4 | 9 | 0.6 | 60 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 18 | 38 | 45 | 70 | 2 | 9 | 1 | 18
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 36 | 6 | 12 | 24 | 4 | 9 | 1 | 36 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 36 | 40 | 60 | 72.4 | 4 | 9 | 1 | 36 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 18 | 24 | 30 | 50 | 2 | 9 | 1 | 18
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 36 | 60 | 120 | 140 | 4 | 9 | 1 | 36 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 18 | 17 | 25 | 44 | 2 | 9 | 1 | 18
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 36 | 172 | 216 | 256 | 4 | 9 | 1 | 36 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 36 | 172 | 216 | 256 | 4 | 9 | 1 | 36 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 18 | 8 | 8 | 8 | 2 | 9 | 0 | 18
Number of Hours required |  |  | 23.3056 | 28.7778 | 35.9178
Number of days access required |  |  | 0.97106 | 1.1991 | 1.4966
Work Site 2 Down Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0.6 | 0 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 0 | 0 | 0 | 0 | 0 | 9 | 0.6 | 0 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 0 | 0 | 0 | 0 | 0 | 9 | 0.6 | 0 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
Number of Hours required |  |  | 0 | 0 | 0
Number of days access required |  |  | 0 | 0 | 0
Work Site 2 Up Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 9 | 4 | 4 | 4 | 1 | 9 | 0 | 9
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 30 | 13.3333 | 13.3333 | 13.3333 | 2 | 9 | 0.6 | 30 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 9 | 19 | 22.5 | 35 | 1 | 9 | 1 | 9
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 18 | 3 | 6 | 12 | 2 | 9 | 1 | 18 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 18 | 20 | 30 | 36.2 | 2 | 9 | 1 | 18 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 9 | 12 | 15 | 25 | 1 | 9 | 1 | 9
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 18 | 30 | 60 | 70 | 2 | 9 | 1 | 18 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 9 | 8.5 | 12.5 | 22 | 1 | 9 | 1 | 9
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 30 | 206.6667 | 240 | 300 | 2 | 9 | 0.6 | 30 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 30 | 206.6667 | 240 | 300 | 2 | 9 | 0.6 | 30 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 18 | 86 | 108 | 128 | 2 | 9 | 1 | 18 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 18 | 86 | 108 | 128 | 2 | 9 | 1 | 18 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 9 | 4 | 4 | 4 | 1 | 9 | 0 | 9
Number of Hours required |  |  | 11.6528 | 14.3889 | 17.9589
Number of days access required |  |  | 0.48553 | 0.59954 | 0.74829
Work Site 3 Down Road 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 27 | 12 | 12 | 12 | 3 | 9 | 0 | 27
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 90 | 40 | 40 | 40 | 6 | 9 | 0.6 | 90 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 27 | 57 | 67.5 | 105 | 3 | 9 | 1 | 27
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 0 | 0 | 0 | 0 | 6 | 9 | 1 | 54 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 54 | 60 | 90 | 108.6 | 6 | 9 | 1 | 54 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 0 | 0 | 0 | 0 | 3 | 9 | 1 | 27
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 0 | 0 | 0 | 0 | 6 | 9 | 1 | 54 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 0 | 0 | 0 | 0 | 3 | 9 | 1 | 27
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 90 | 620 | 720 | 900 | 6 | 9 | 0.6 | 90 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 90 | 620 | 720 | 900 | 6 | 9 | 0.6 | 90 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 54 | 258 | 324 | 384 | 6 | 9 | 1 | 54 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 54 | 258 | 324 | 384 | 6 | 9 | 1 | 54 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 9 | 4 | 4 | 4 | 1 | 9 | 0 | 9
Number of Hours required |  |  | 32.15 | 38.3583 | 47.2933
Number of days access required |  |  | 1.3396 | 1.5983 | 1.9706
Work Site 3 Up Road Br 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 65 | 28.8889 | 28.8889 | 28.8889 | 5 | 9 | 20 | 65
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 4.5 | 2 | 2 | 2 | 10 | 9 | 20 | 4.5 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 45 | 95 | 112.5 | 175 | 5 | 9 | 1 | 45
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 6 | 1 | 2 | 4 | 10 | 9 | 1 | 90 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 45mins/m) | M | 9 | 10 | 15 | 18.1 | 10 | 9 | 0.1 | 9 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 6 | 8 | 10 | 16.6667 | 5 | 9 | 1 | 45
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 6 | 10 | 20 | 23.3333 | 10 | 9 | 1 | 90 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 6 | 5.6667 | 8.3333 | 14.6667 | 5 | 9 | 1 | 45
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 150 | 1033.3333 | 1200 | 1500 | 10 | 9 | 0.6 | 150 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 150 | 1033.3333 | 1200 | 1500 | 10 | 9 | 0.6 | 150 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 180 | 860 | 1080 | 1280 | 10 | 9 | 2 | 180 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 180 | 860 | 1080 | 1280 | 10 | 9 | 2 | 180 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 65 | 28.8889 | 28.8889 | 28.8889 | 5 | 9 | 20 | 65
Number of Hours required |  |  | 66.2685 | 79.7935 | 97.8591
Number of days access required |  |  | 2.7612 | 3.3247 | 4.0775
Work Site 4 Down Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 47 | 20.8889 | 20.8889 | 20.8889 | 3 | 9 | 20 | 47
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 90 | 40 | 40 | 40 | 6 | 9 | 0.6 | 90 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 54 | 114 | 135 | 210 | 3 | 9 | 2 | 54
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 108 | 18 | 36 | 72 | 6 | 9 | 2 | 108 |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 108 | 120 | 180 | 217.2 | 6 | 9 | 2 | 108 |  | 2 x Rails | Assumes 80% of top flange requires repairs
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 45 minutes / Pair) | M | 54 | 72 | 90 | 150 | 3 | 9 | 2 | 54
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 108 | 180 | 360 | 420 | 6 | 9 | 2 | 108 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 54 | 51 | 75 | 132 | 3 | 9 | 2 | 54
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 90 | 620 | 720 | 900 | 6 | 9 | 0.6 | 90 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 90 | 620 | 720 | 900 | 6 | 9 | 0.6 | 90 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 108 | 516 | 648 | 768 | 6 | 9 | 2 | 108 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 108 | 516 | 648 | 768 | 6 | 9 | 2 | 108 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 47 | 20.8889 | 20.8889 | 20.8889 | 3 | 9 | 20 | 47
Number of Hours required |  |  | 48.4796 | 61.563 | 76.983
Number of days access required |  |  | 2.02 | 2.5651 | 3.2076
Work Site 4 Up Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 56 | 24.8889 | 24.8889 | 24.8889 | 4 | 9 | 20 | 56
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 120 | 53.3333 | 53.3333 | 53.3333 | 8 | 9 | 0.6 | 120 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 72 | 152 | 180 | 280 | 4 | 9 | 2 | 72
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 144 | 24 | 48 | 96 | 8 | 9 | 2 | 144 |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 144 | 160 | 240 | 289.6 | 8 | 9 | 2 | 144 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 72 | 96 | 120 | 200 | 4 | 9 | 2 | 72
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 144 | 240 | 480 | 560 | 8 | 9 | 2 | 144 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 72 | 68 | 100 | 176 | 4 | 9 | 2 | 72
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 120 | 826.6667 | 960 | 1200 | 8 | 9 | 0.6 | 120 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 120 | 826.6667 | 960 | 1200 | 8 | 9 | 0.6 | 120 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 144 | 688 | 864 | 1024 | 8 | 9 | 2 | 144 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 144 | 688 | 864 | 1024 | 8 | 9 | 2 | 144 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 56 | 24.8889 | 24.8889 | 24.8889 | 4 | 9 | 20 | 56
Number of Hours required |  |  | 64.5407 | 81.9852 | 102.5452
Number of days access required |  |  | 2.6892 | 3.416 | 4.2727
Clear Site 3 & 4 of RRV's |  | 8 | 120 | 240 | 360
Hand back Worksite to PICOP |  |  | 10 | 15 | 15
Possession Handed Back |  |  | 3 | 5 | 5

## Orange Forecast
|  | Critical Path |  |  |  | Road Rail Vehicle Volume Calc
Activity | NUOM | Volume | Minimum | Most Likely | Maximum | No. of WT | NUOM | Trailer Load | No. of Trailer | No. of RRV | Timing Assumptions
Possession Mobilisation Activities |  | (Rounded)
Take Possession (ML = 25 minutes) |  |  | 15 | 25 | 35
Site 4 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 4.75 | 42.75 | 85.5 | 178.125 | 19 | Pair | 2 | 9.5 | 4.75 |  | Use Third Drove as L/E RRAP
Site 4 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2mph travelling time to site) | Miles | 1.8 | 16.2 | 21.6 | 32.4 | 1.8 | Mile |  |  |  |  | Drop to 3 miles per hour walking pace
Site 3 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 5 | 45 | 90 | 187.5 | 21 | Pair | 2 | 10.5 | 5.25
Site 3 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2 miles travelling from nearest access) | Miles | 2.3 | 20.7 | 27.6 | 41.4 | 2.3 | Mile
Site 2 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 1.5 | 13.5 | 27 | 56.25 | 7 | Pair | 2 | 3.5 | 1.75
Site 2 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Site 1 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 1.1 | 9.9 | 19.8 | 41.25 | 4 | Pair | 2 | 2 | 1
Site 1 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Volumes Calc
[6 empty] | No. WT | L | Extra | Total
Work Site 1 Down Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 50 | 22.2222 | 22.2222 | 22.2222 |  | 9 | 50 | 50 |  |  | Assumed 25m either side for Blue Netlon | Includes a contribution for travelling time of RRV
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 0 | 0 | 0 | 0 |  | 9 | 0.6 | 0 |  | 2 X Rails | Assumes WT L + 20m of Guard Rail
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | Pair | 0 | 0 | 0 | 0 |  | 9 | 1 | 0 |  |  | Increase time to reflect 9m timber
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 0 | 0 | 0 | 0 |  | 9 | 0.6 | 0 |  | 2 x Rails | Total of baseplate activity
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 0 | 0 | 0 | 0 |  | 9 | 0.6 | 0 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails | 20m each side to be unkeyed
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 50 | 22.2222 | 22.2222 | 22.2222 |  | 9 | 50 | 50
Number of Hours required |  |  | 0.74074 | 0.74074 | 0.74074 | [5 empty] | Total mins / 60
Number of days access required |  |  | 0.030864 | 0.030864 | 0.030864 | [5 empty] | Total hrs / 24
Work Site 1 Up Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 50 | 22.2222 | 22.2222 | 22.2222 |  | 9 | 50 | 50
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 0 | 0 | 0 | 0 |  | 9 | 0.6 | 0 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | Pair | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 0 | 0 | 0 | 0 |  | 9 | 0.6 | 0 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 0 | 0 | 0 | 0 |  | 9 | 0.6 | 0 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 50 | 22.2222 | 22.2222 | 22.2222 |  | 9 | 50 | 50
Number of Hours required |  |  | 0.74074 | 0.74074 | 0.74074
Number of days access required |  |  | 0.030864 | 0.030864 | 0.030864
Work Site 2 Down Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 59 | 26.2222 | 26.2222 | 26.2222 | 1 | 9 | 50 | 59
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 30 | 13.3333 | 13.3333 | 13.3333 | 2 | 9 | 0.6 | 30 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 9 | 19 | 22.5 | 35 | 1 | 9 | 1 | 9
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 36 | 6 | 12 | 24 | 2 | 9 | 2 | 36 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 36 | 40 | 60 | 72.4 | 2 | 9 | 2 | 36 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | Pair | 9 | 12 | 15 | 25 | 1 | 9 | 1 | 9
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 36 | 60 | 120 | 140 | 2 | 9 | 2 | 36 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 9 | 8.5 | 12.5 | 22 | 1 | 9 | 1 | 9
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 30 | 206.6667 | 240 | 300 | 2 | 9 | 0.6 | 30 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 30 | 206.6667 | 240 | 300 | 2 | 9 | 0.6 | 30 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 36 | 172 | 216 | 256 | 2 | 9 | 2 | 36 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 36 | 172 | 216 | 256 | 2 | 9 | 2 | 36 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 59 | 26.2222 | 26.2222 | 26.2222 | 1 | 9 | 50 | 59
Number of Hours required |  |  | 16.1435 | 20.3296 | 24.9363
Number of days access required |  |  | 0.67265 | 0.84707 | 1.039
Work Site 2 Up Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 180 | 80 | 80 | 80 | 12 | 9 | 0.6 | 180 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 54 | 114 | 135 | 210 | 6 | 9 | 1 | 54
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 6 | 1 | 2 | 4 | 12 | 9 | 2 | 216 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 216 | 240 | 360 | 434.4 | 12 | 9 | 2 | 216 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | Pair | 6 | 8 | 10 | 16.6667 | 6 | 9 | 1 | 54
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 6 | 10 | 20 | 23.3333 | 6 | 9 | 2 | 108 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 6 | 5.6667 | 8.3333 | 14.6667 | 6 | 9 | 1 | 54
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Number of Hours required |  |  | 84.9185 | 102.9963 | 125.7919
Number of days access required |  |  | 3.5383 | 4.2915 | 5.2413
Work Site 3 Down Road 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 95 | 42.2222 | 42.2222 | 42.2222 | 5 | 9 | 50 | 95
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 150 | 66.6667 | 66.6667 | 66.6667 | 10 | 9 | 0.6 | 150 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 45 | 95 | 112.5 | 175 | 5 | 9 | 1 | 45
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 4 | 0.66667 | 1.3333 | 2.6667 | 10 | 9 | 2 | 180 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 180 | 200 | 300 | 362 | 10 | 9 | 2 | 180 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | Pair | 4 | 5.3333 | 6.6667 | 11.1111 | 5 | 9 | 1 | 45
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 4 | 6.6667 | 13.3333 | 15.5556 | 10 | 9 | 2 | 180 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 4 | 3.7778 | 5.5556 | 9.7778 | 5 | 9 | 1 | 45
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 150 | 1033.3333 | 1200 | 1500 | 10 | 9 | 0.6 | 150 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 150 | 1033.3333 | 1200 | 1500 | 10 | 9 | 0.6 | 150 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 180 | 860 | 1080 | 1280 | 10 | 9 | 2 | 180 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 180 | 860 | 1080 | 1280 | 10 | 9 | 2 | 180 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 95 | 42.2222 | 42.2222 | 42.2222 | 5 | 9 | 50 | 95
Number of Hours required |  |  | 70.8204 | 85.8417 | 104.787
Number of days access required |  |  | 2.9508 | 3.5767 | 4.3661
Work Site 3 Up Road Br 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 203 | 90.2222 | 90.2222 | 90.2222 | 17 | 9 | 50 | 203
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 510 | 226.6667 | 226.6667 | 226.6667 | 34 | 9 | 0.6 | 510 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 153 | 323 | 382.5 | 595 | 17 | 9 | 1 | 153
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 17 | 2.8333 | 5.6667 | 11.3333 | 34 | 9 | 2 | 612 |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 45mins/m) | M | 612 | 680 | 1020 | 1230.8 | 34 | 9 | 2 | 612 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | Pair | 17 | 22.6667 | 28.3333 | 47.2222 | 17 | 9 | 1 | 153
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 17 | 28.3333 | 56.6667 | 66.1111 | 34 | 9 | 2 | 612 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 17 | 16.0556 | 23.6111 | 41.5556 | 17 | 9 | 1 | 153
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 510 | 3513.3333 | 4080 | 5100 | 34 | 9 | 0.6 | 510 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 510 | 3513.3333 | 4080 | 5100 | 34 | 9 | 0.6 | 510 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 612 | 2924 | 3672 | 4352 | 34 | 9 | 2 | 612 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 612 | 2924 | 3672 | 4352 | 34 | 9 | 2 | 612 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 203 | 90.2222 | 90.2222 | 90.2222 | 17 | 9 | 50 | 203
Number of Hours required |  |  | 239.2444 | 290.4648 | 355.0522
Number of days access required |  |  | 9.9685 | 12.1027 | 14.7938
Work Site 4 Down Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 167 | 74.2222 | 74.2222 | 74.2222 | 13 | 9 | 50 | 167
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 390 | 173.3333 | 173.3333 | 173.3333 | 26 | 9 | 0.6 | 390 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 117 | 247 | 292.5 | 455 | 13 | 9 | 1 | 117
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 13 | 2.1667 | 4.3333 | 8.6667 | 26 | 9 | 2 | 468 |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 468 | 520 | 780 | 941.2 | 26 | 9 | 2 | 468 |  | 2 x Rails | Assumes 80% of top flange requires repairs
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 45 minutes / Pair) | Pair | 13 | 17.3333 | 21.6667 | 36.1111 | 13 | 9 | 1 | 117
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 13 | 21.6667 | 43.3333 | 50.5556 | 26 | 9 | 2 | 468 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 13 | 12.2778 | 18.0556 | 31.7778 |  | 9 | 1 | 0
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 195 | 1343.3333 | 1560 | 1950 | 13 | 9 | 0.6 | 195 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 195 | 1343.3333 | 1560 | 1950 | 13 | 9 | 0.6 | 195 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 234 | 1118 | 1404 | 1664 | 13 | 9 | 2 | 234 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 234 | 1118 | 1404 | 1664 | 13 | 9 | 2 | 234 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 167 | 74.2222 | 74.2222 | 74.2222 | 13 | 9 | 50 | 167
Number of Hours required |  |  | 101.0815 | 123.4944 | 151.2181
Number of days access required |  |  | 4.2117 | 5.1456 | 6.3008
Work Site 4 Up Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 180 | 80 | 80 | 80 | 12 | 9 | 0.6 | 180 |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 54 | 114 | 135 | 210 | 6 | 9 | 1 | 54
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | Pair | 6 | 1 | 2 | 4 | 12 | 9 | 2 | 216 |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 216 | 240 | 360 | 434.4 | 12 | 9 | 2 | 216 |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | Pair | 6 | 8 | 10 | 16.6667 | 6 | 9 | 1 | 54
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | Pair | 6 | 10 | 20 | 23.3333 | 12 | 9 | 2 | 216 |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | Pair | 6 | 5.6667 | 8.3333 | 14.6667 | 6 | 9 | 1 | 54
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Number of Hours required |  |  | 84.9185 | 102.9963 | 125.7919
Number of days access required |  |  | 3.5383 | 4.2915 | 5.2413
Clear Site 3 & 4 of RRV's |  | 8 | 120 | 240 | 360
Hand back Worksite to PICOP |  |  | 10 | 15 | 15
Possession Handed Back |  |  | 3 | 5 | 5

## Yellow Forecast
|  | Critical Path |  |  |  | Road Rail Vehicle Volume Calc
Activity | NUOM | Volume | Minimum | Most Likely | Maximum | No. of WT | NUOM | Trailer Load | No. of Trailer | No. of RRV |  | Timing Assumptions
Possession Mobilisation Activities |  | (Rounded)
Take Possession (ML = 25 minutes) |  |  | 15 | 25 | 35
Site 4 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 0 | 0 | 0 | 0 | 0 | Pair | 2 | 0 | 0 |  |  | Use Third Drove as L/E RRAP
Site 4 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2mph travelling time to site) | Miles | 1.8 | 16.2 | 21.6 | 32.4 | 0 | Mile | [5 empty] | Drop to 3 miles per hour walking pace
Site 3 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 5 | 45 | 90 | 187.5 | 0 | Pair | 2 | 0 | 0
Site 3 RRV's and Trailers Transit to site (assumes 2 machines travelling in convoy first and three second) (assumes 2 miles travelling from nearest access) | Miles | 2.3 | 20.7 | 27.6 | 41.4 | 2.3 | Mile
Site 2 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Welney Rd | RRV | 1.5 | 13.5 | 27 | 56.25 | 6 | Pair | 2 | 3 | 1.5
Site 2 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Site 1 RRV's and Trailers On track with temporary RRAP (Assumes 2 pairs per trailer and 2 x trailers per machine) @ Manea | RRV | 1.1 | 9.9 | 19.8 | 41.25 | 2 | Pair | 2 | 1 | 0.5
Site 1 RRV's and Trailers Transit to site | Miles | 1 | 9 | 12 | 18
Volumes Calc
[6 empty] | No. WT | L | Extra | Total
Work Site 1 Down Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 68 | 30.2222 | 30.2222 | 30.2222 | 2 | 9 | 50 | 68 |  |  |  | Assumed 25m either side for Blue Netlon | Includes a contribution for travelling time of RRV
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 60 | 26.6667 | 26.6667 | 26.6667 | 4 | 9 | 0.6 | 60 |  |  | 2 X Rails | Assumes WT L + 20m of Guard Rail
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 18 | 38 | 45 | 70 | 2 | 9 | 1 | 18
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 72 | 12 | 24 | 48 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 72 | 80 | 120 | 144.8 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 18 | 24 | 30 | 50 | 2 | 9 | 1 | 18 |  |  |  | Increase time to reflect 9m timber
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 72 | 120 | 240 | 280 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 18 | 17 | 25 | 44 | 2 | 9 | 1 | 18
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  |  | 2 x Rails | Total of baseplate activity
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 60 | 413.3333 | 480 | 600 | 4 | 9 | 0.6 | 60 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 72 | 344 | 432 | 512 | 4 | 9 | 2 | 72 |  |  | 2 x Rails | 20m each side to be unkeyed
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 72 | 344 | 432 | 512 | 4 | 9 | 2 | 72 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 68 | 30.2222 | 30.2222 | 30.2222 | 2 | 9 | 50 | 68
Number of Hours required |  |  | 31.5463 | 39.9185 | 49.1319 | [6 empty] | Total mins / 60
Number of days access required |  |  | 1.3144 | 1.6633 | 2.0472 | [6 empty] | Total hrs / 24
Work Site 1 Up Road Br1815
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 180 | 80 | 80 | 80 | 12 | 9 | 0.6 | 180 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 54 | 114 | 135 | 210 | 6 | 9 | 1 | 54
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 216 | 36 | 72 | 144 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 216 | 240 | 360 | 434.4 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 54 | 72 | 90 | 150 | 6 | 9 | 1 | 54
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 216 | 360 | 720 | 840 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 54 | 51 | 75 | 132 | 6 | 9 | 1 | 54
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Number of Hours required |  |  | 93.1574 | 118.2741 | 145.9141
Number of days access required |  |  | 3.8816 | 4.9281 | 6.0798
Work Site 2 Down Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 86 | 38.2222 | 38.2222 | 38.2222 | 4 | 9 | 50 | 86
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 120 | 53.3333 | 53.3333 | 53.3333 | 8 | 9 | 0.6 | 120 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 36 | 76 | 90 | 140 | 4 | 9 | 1 | 36
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 144 | 24 | 48 | 96 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 144 | 160 | 240 | 289.6 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 36 | 48 | 60 | 100 | 4 | 9 | 1 | 36
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 144 | 240 | 480 | 560 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 36 | 34 | 50 | 88 | 4 | 9 | 1 | 36
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 120 | 826.6667 | 960 | 1200 | 8 | 9 | 0.6 | 120 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 120 | 826.6667 | 960 | 1200 | 8 | 9 | 0.6 | 120 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 144 | 688 | 864 | 1024 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 144 | 688 | 864 | 1024 | 8 | 9 | 2 | 144 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 86 | 38.2222 | 38.2222 | 38.2222 | 4 | 9 | 50 | 86
Number of Hours required |  |  | 62.3519 | 79.0963 | 97.523
Number of days access required |  |  | 2.598 | 3.2957 | 4.0635
Work Site 2 Up Road Br1814a
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 180 | 80 | 80 | 80 | 12 | 9 | 0.6 | 180 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 54 | 114 | 135 | 210 | 6 | 9 | 1 | 54
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 216 | 36 | 72 | 144 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 216 | 240 | 360 | 434.4 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 54 | 72 | 90 | 150 | 6 | 9 | 1 | 54
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 216 | 360 | 720 | 840 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 54 | 51 | 75 | 132 | 6 | 9 | 1 | 54
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 180 | 1240 | 1440 | 1800 | 12 | 9 | 0.6 | 180 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 216 | 1032 | 1296 | 1536 | 12 | 9 | 2 | 216 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 104 | 46.2222 | 46.2222 | 46.2222 | 6 | 9 | 50 | 104
Number of Hours required |  |  | 93.1574 | 118.2741 | 145.9141
Number of days access required |  |  | 3.8816 | 4.9281 | 6.0798
Work Site 3 Down Road 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 257 | 114.2222 | 114.2222 | 114.2222 | 23 | 9 | 50 | 257
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 690 | 306.6667 | 306.6667 | 306.6667 | 46 | 9 | 0.6 | 690 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 207 | 437 | 517.5 | 805 | 23 | 9 | 1 | 207
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 828 | 138 | 276 | 552 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 30mins/m) | M | 828 | 920 | 1380 | 1665.2 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 207 | 276 | 345 | 575 | 23 | 9 | 1 | 207
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 828 | 1380 | 2760 | 3220 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 207 | 195.5 | 287.5 | 506 | 23 | 9 | 1 | 207
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 690 | 4753.3333 | 5520 | 6900 | 46 | 9 | 0.6 | 690 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 690 | 4753.3333 | 5520 | 6900 | 46 | 9 | 0.6 | 690 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 828 | 3956 | 4968 | 5888 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 828 | 3956 | 4968 | 5888 | 46 | 9 | 2 | 828 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 257 | 114.2222 | 114.2222 | 114.2222 | 23 | 9 | 50 | 257
Number of Hours required |  |  | 355.0046 | 451.2852 | 557.2385
Number of days access required |  |  | 14.7919 | 18.8035 | 23.2183
Work Site 3 Up Road Br 1814
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 248 | 110.2222 | 110.2222 | 110.2222 | 22 | 9 | 50 | 248
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 330 | 146.6667 | 146.6667 | 146.6667 | 22 | 9 | 0.6 | 330 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 198 | 418 | 495 | 770 | 22 | 9 | 1 | 198
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 396 | 66 | 132 | 264 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Steel work repairs over 10% of exposed girder (ML = 45mins/m) | M | 396 | 440 | 660 | 796.4 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 198 | 264 | 330 | 550 | 22 | 9 | 1 | 198
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 396 | 660 | 1320 | 1540 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 198 | 187 | 275 | 484 | 22 | 9 | 1 | 198
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 330 | 2273.3333 | 2640 | 3300 | 22 | 9 | 0.6 | 330 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 330 | 2273.3333 | 2640 | 3300 | 22 | 9 | 0.6 | 330 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 396 | 1892 | 2376 | 2816 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 396 | 1892 | 2376 | 2816 | 22 | 9 | 2 | 396 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 248 | 110.2222 | 110.2222 | 110.2222 | 22 | 9 | 50 | 248
Number of Hours required |  |  | 178.8796 | 226.8519 | 283.3919
Number of days access required |  |  | 7.4533 | 9.4522 | 11.808
Work Site 4 Down Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 375 | 166.6667 | 166.6667 | 166.6667 | 25 | 9 | 0.6 | 375 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 225 | 475 | 562.5 | 875 | 25 | 9 | 1 | 225
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 450 | 75 | 150 | 300 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 450 | 500 | 750 | 905 | 25 | 9 | 2 | 450 |  |  | 2 x Rails | Assumes 80% of top flange requires repairs
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 45 minutes / Pair) | M | 225 | 300 | 375 | 625 | 25 | 9 | 1 | 225
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 450 | 750 | 1500 | 1750 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 225 | 212.5 | 312.5 | 550 | 25 | 9 | 1 | 225
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  | 108 | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Number of Hours required |  |  | 203.1713 | 257.6852 | 321.9352
Number of days access required |  |  | 8.4655 | 10.7369 | 13.414
Work Site 4 Up Road Br 1813
Install Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Remove Guard Rail and holding arrangements at 600mm spacing (ML = 4 Minutes) | M | 375 | 166.6667 | 166.6667 | 166.6667 | 25 | 9 | 0.6 | 375 |  |  | 2 X Rails
Remove existing wheel timber in pairs and remove to cess (ML = 45 minutes) | M | 225 | 475 | 562.5 | 875 | 25 | 9 | 1 | 225
Inspect top flange steel work throughout the exposed support area, remove rust and apply paint (ML = 6 Minutes/WT) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  |  | 2 x Rails
Steel work repairs over 80% of exposed girder (ML = 30mins/m) | M | 450 | 500 | 750 | 905 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Show Wheel Timber Pair to Rivet Head to create routing plan (ML = 30 minutes / Pair) | M | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Route Rivet Pattern and test timbers (assumes RFT) (ML = 60 minutes / pair) | M | 0 | 0 | 0 | 0 |  | 9 | 2 | 0 |  |  | 2 x Rails
Set timber to steel support system assumes Transom preinstalled (ML = 25 minutes / pair) | M | 0 | 0 | 0 | 0 |  | 9 | 1 | 0
Set cess baseplates from bridge offsets (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  |  | 2 x Rails
Set six foot baseplates at 1435mm (assumes 600 spacing) (ML = 8 minutes / baseplate) | No. | 375 | 2583.3333 | 3000 | 3750 | 25 | 9 | 0.6 | 375 |  |  | 2 x Rails
Reinstate Running Rail and prep for Stressing (assumes single site stress) (ML = 6 minutes per M) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Reinstate Guard Rail & Walkways (ML = 6 minutes) | M | 450 | 2150 | 2700 | 3200 | 25 | 9 | 2 | 450 |  |  | 2 x Rails
Remove Acoustic Barriers & Blue Netlon through worksite + 25m either side | M | 275 | 122.2222 | 122.2222 | 122.2222 | 25 | 9 | 50 | 275
Number of Hours required |  |  | 180.8796 | 218.7269 | 268.1852
Number of days access required |  |  | 7.5367 | 9.1136 | 11.1744
Clear Site 3 & 4 of RRV's |  | 8 | 120 | 240 | 360
Hand back Worksite to PICOP |  |  | 10 | 15 | 15
Possession Handed Back |  |  | 3 | 5 | 5

## Line Drawing
B1411 One Hundred Foot Bank goes under the railway L/S of New Bedford and has a rough road access upto the embankment and to the NR Fence Line.
Temporary Road surface can be installed to make this fit for HGV purpose.
Requires Natural England consent
WDA prefer to use Third Drove as the RRV point as it only requires a Road Closure and no prep works.
Adds 25% travelling time to site from existing acces at Welney Rd.
Same travelling time as Manea Station access.
Easier access than Manea Station due to signalling furniture
Site access is available with Natural England approval from Br 1814a fence line.
There is also a haul road from the main road A1011 WASH ROAD.
Previously used as SAC and Steel Prep area.
Site 4
Br 1813 New Bedford Bridge
Up 25 x WT in total
Dn 25 x WT in total
Worst bridge for steelwork
Site 2
Br 1814a Old Bedford Bridge
Up 6 x WT in total
Dn 4 x WT in total
Site 3
1814 Delph River & Floodspan
Up 22 x WT in total
Dn 23 x WT in total
Site 1
Br 1815 over what looks to be a Dyke or drainage channel.
Up 2 x WT in total
Dn 2 x WT in total
Br 1814 exact location is not confirmed.
Construction Strategy:
Contractor 1
Site 4 and 1
Works Site 4 first
RRV Access from B1411
SAC at B1411
Vehicle parking at Manea
Contractor 2
Site 3 and 2
Works Site 3 first
RRV Access from Welney Rd or Manea
SAC at Old Bedford Rd
Vehicle Parking on Haul Road

## Assumptions
Dn Rd | Scaffolding needs to be over 2 weekends at 52Hr
Up Rd | Scaffolding needs to be over 2 weekends at 52Hr
Resources | 2 x Contractors supplying 2 x WT & Steelworkers on 2 sites at same time
RRAP | Access at north and south of site
Resources | Shift changeover timed with passing Engineering Trains
SAC | Access at north and south of site
Time | Br1813 is worst condition and requires 80% steelwork repairs
Freight 1 | Friday Last train 23:11 | As of week 5 | 30 minute service
Freight 2 | Saturday First Train 01:43 | As of week 5 | 30 minute service
Freight 3 | Saturday Last Train 22:44 | As of week 5 | 30 minute service
Freight 4 | Sunday First Train 00:12 | As of week 5 | 30 minute service
Freight 5 | Sunday Last Train 21:30 | As of week 5 | 12hr Gap 08:58 to 21:30
Freight 6 | Monday First Train 03:56 | As of week 5 | 30 minute service
There is a possession that covers the Manea area
There is a possession that could be extended or utilised in Manea area
There is probably an Engineering Train clash impacting the Manea Access
Renewals | Not losing any of my Renewal Plan to facilitate Manea so needs to deconflict
WT Core Works
No WT Core works
WT Prep or FU works
Recommended | DEFCON4&5

## Volumes of Work
|  |  | Br1815 |  | Br1814a |  | Br1814 |  | Br1813
Scope | Yr | NUOM | Up | Dn | Up | Dn | Up | Dn | Up | Dn | Total No. | Length | Linear
Red WT | 2020 | Pair | 2 | 2 | 1 | 0 | 5 | 3 | 4 | 3 | 20 | 9 | 180
Orange WT | 2020 | Pair | 0 | 0 | 5 | 1 | 12 | 2 | 2 | 10 | 32 | 9 | 288
Yellow WT | 2021 | Pair | 0 | 0 | 0 | 2 | 4 | 13 | 8 | 5 | 32 | 9 | 288
White WT | 2022 | Pair | 0 | 0 | 0 | 1 | 1 | 5 | 10 | 5 | 22 | 9 | 198
Total No. by Road |  |  | 2 | 2 | 6 | 4 | 22 | 23 | 24 | 23
Total L by Road |  |  | 18 | 18 | 54 | 36 | 198 | 207 | 216 | 207 | 954 | 324 | 8586
TSR No. by Road |  | Pair | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 1
Top Flange % |  |  | 10% | 10% | 10% | 10% | 10% | 10% | 80% | 80% |  | 28%
Top Flange repair by m |  |  | 1.8 | 1.8 | 5.4 | 3.6 | 19.8 | 20.7 | 172.8 | 165.6 |  | 90.72

## Insert for Dispute Paper
Site 4
Br 1813 New Bedford Bridge
Site 2
Br 1814a Old Bedford Bridge
Site 3
1814 Delph River & Floodspan
Site 1
Br 1815 over what looks to be a Dyke or drainage channel.

## Access Forecast
Week | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | Decision criteria
HO | March 27hr Core | March 12hr Core | Westley 52hr Core | Base Green 52hrs Core | Base Green 52hrs Core | Thorpe 28hrs Core | CCH 28hrs FUW | Ely 52hr Core | Needham 28hr Core | Baylham 52hr Core | Littleport 52hr Core | [8 empty] | Brentwood 8hrs RDT
SRSA | Haringay 14hr RDT | Ely 8hrs PREP | [5 empty] | Haringay 47hr Core | Haringay 52hr Core | Haringay 52hr Core |  | Moulton LC 52hr Core | Claydon Barham 52hr Core | Pitsea 52hr Core | Ely 52hrs Core |  | Brampton 6 Days Core | Brampton 52hrs Core |  | Somerleyton 52hr Core
SRSA | Clapton 8hr PREP | Clapton 52hr CORE | Clapton 52hr CORE | Clapton 52hr CORE | Clapton 52hr CORE | Cantley 28hrs Prep | Cantley 9 days Core | Cantley 9 days Core | Clapton 28hr FUW | Bamford 52hr Core | Clacton 52hr Prep |  | Clacton 52hr Prep | Clacton 52hr Prep | Clacton 52hr Prep | Colchester 52hr Core |  | Ely 52hrs Core | Ely 27hrs Core | Colchester 52hr Prep
SRSA | Stowmarket 8hr RDT | Ipswich London Rd 8hr RDT | [7 empty] | Rectory Rd 52hr Core | Ipswich London Rd 52hr Core | Ipswich London Rd 52hr Core | Audley End 52hr Core |  | 2nd Drove LC 28hr Core | Foxton LC 52hr Core |  |  |  | Manningtree 52hr Core
SRSA | [19 empty] | Halifax Jn 47hr Core
HO |  |  | Brentwood 14hrs Prep
BRE |  |  |  | Barking 52hr Core |  |  |  |  | Barking 52hr Core |  |  |  |  | Barking 52hr Core | [5 empty] | Barking 52hr Core
Maintenance |  |  |  |  | Manea 10hrs Maintenance | [5 empty] | Manea 10hrs Maintenance |  |  | Manea 28hrs Maintenance | Broxbourne Jn 27hr Core |  | Manea 10hrs Maintenance |  | Manea 27hrs Maintenance
WDA WT | [7 empty] | Jarrow Rd 28hr WT |  | Jarrow Rd 52hr Core | Jarrow Rd 52hr Core | Coffin 52hr Core | Coffin 52hr Core |  | Ely Dock 52hr Core |  | Strode 47hr Core | Ely Dock 52hr Core |  | Pitmire 52hr Core
CDA Civil | [9 empty] | BGK 52hr Core | BGK 52hr Core |  |  |  | Eccles 52hr Core |  |  | Eccles 52hr Core | Eccles 52hr FUW
GA | [11 empty] | Cow Creek 52hr Core |  | Spikes Lane 27hr Core | [5 empty] | Pannington Hall LC 52hr Core
CDA Signals | [14 empty] | Hiam Fen Hse 52hr Core |  |  | EMP Sig 52hrs Prep | Roundham Hall LC 52hr Core
CDA Signals | [17 empty] | Park Lane LC 52hr Core
CDA M&E | [12 empty] | BGK 47hr Core | BGK 47hr Core
WDA Structures | [13 empty] | Stowmarket 27hrs Core
Manea Wheel Timbers | No Core Wheeltimber works in these weeks | [7 empty] | Best weeks in this timeframe without risking the wider Anglia Plan | [6 empty] | No Core WT |  | No Core WT |  | No Core WT
DEFCON0 | [20 empty] | This approach is repeated: 2020 2021 2022
DEFCON1 | 27hr Scaffold Prep | 12hr Cable Diversion Prep |  |  | 10hr RRAP/Scaffold Prep |  |  | 52hr Scaffold Prep |  | Core 14 Day Blockade All Reds 100% complete |  |  | 27hr Scaffold strike | 12hr Cable Reinstate | [6 empty] | Would need access again in Yr2 for Oranges (Xmas). YR5 for Yellows.
DEFCON2 | 27hr Scaffold Prep | 12hr Cable Diversion Prep |  |  | 10hr RRAP/Scaffold Prep |  |  | 52hr Scaffold Prep |  | 52hr Br1813 |  | Core 14 Day Blockade Br1814a/1814/1815 Reds & Oranges 100% complete |  |  |  |  | 27hr Scaffold strike |  | 12hr Cable Reinstate |  | Gives a 2yr stay of grace. Needs access agreed in Yr5 for Yellows
DEFCON3 | 27hr Scaffold Prep | 12hr Cable Diversion Prep |  |  | 10hr RRAP/Scaffold Prep |  |  | 52hr Scaffold Prep |  | Core 14 Day Blockade Br1813 Red & Orange Br1814a Red & Orange, some yellow |  |  | Core 14 Day Blockade Br1814 Red & Orange Br1815 Red, some yellow |  |  |  | 52hr Br1814 / 1814a / 1813 Yellow |  | 27hr Scaffold strike | 12hr Cable Reinstate | Gives a 5yr stay of grace.
DEFCON4 | 27hr Scaffold Prep | 12hr Cable Diversion Prep |  |  | 10hr RRAP/Scaffold Prep |  |  | 52hr Scaffold Prep |  | 28 Day Blockade Br1813 / 1814a / 1814 / 1813 Red & Orange |  |  |  |  | 52hr Br1814a / 1813 Yellow |  | 52hr Br1814 Yellow |  | 52hr Scaffold Strike Stressing | 27hr Cable Diversions Stressing | Gives a 5yr stay of grace.
DEFCON5 | 27hr Scaffold Prep | 12hr Cable Diversion Prep |  |  | 10hr RRAP/Scaffold Prep |  |  | 52hr Scaffold Prep |  | 42 Day Blockade All works completed Scaffold Struck / Cable Diversions Stressing | [10 empty] | Gives a 5yr stay of grace.

## Optioneering
Option | Description | Methodology | No. | Consequences | Decision | Actions
DEFCON0 | Complete RED/ORANGE/YELLOW Disruptive WE only Undertake works in 52hr windows delivering 2 pairs per window. | Mark up Continuous check rail to as near as possible 18m lengths aligned with wheel timber ends Cut Continuous Guard & Running rail into 60' [18m] lengths and joint to facilitate removal Install Expansion Switch at each end of bridge structures to manage thermal expansion Assume an average length of 9m per pair this allows for 2 pairs per 52hrs to be replaced Assume completing 84 pairs, therefore 24 weekends @ 52hrs from week 21 to 45 | 1 | We would have timbers that passed the forecast deadline (6 months) in situ | Disregarded as far to onerous an option and is non compliant with external stakeholder (AE and NE) guidelines driving out the completion to Year 5, importing clear risk of asset failure and total RoU over extended period if asset were to fail. Whist the works could be approached in this manner it would be highly disruptive in the first instance over a prolonged period of time but moreover Network Rail would be managing the real risk of passing the Engineering timeline of 0-6 months specifically in the wet period. Additional or increased water absorption makes rotten wood more malleable and likely to rotate. Holding down arrangements rely on the timber and steel work being in a condition that manages an element of flex as traffic passes over, this ability is eroded and the 0-6 month timeframe is an indicator that that flexure becomes excessive removing the ability of the wheel rail interface to provide an adequate guideway. As seen in numerous ORR reports (Soton, Gospel Oak etc) for derailment at Wheel Timber locations rotation of the rail is a contributing factor to the cause of derailment.
|  |  | 2 | We would disrupt freight services from Friday night through Saturday and Monday morning throughout
|  |  | 3 | We would need further access between weeks 45 and 08 (2021) to rerail and restress to avoid Heat related speeds for joint and thermal expansion.
|  |  | 4 | We would be non compliant with the EA and NE restrictions of working in sensitive seasons between weeks 31 and 08.
|  |  | 5 | We run the risk of overrun every Monday we work on bridge 1813 due to the unknown top flange works required.
DEFCON1 | Complete RED 1 x 14 day 2 line block 2 x disruptive follow up. | Splay guard and running rails to enable access to Wheel Timber area Assume completing 20 pairs, therefore 18 x 52 hrs = 39 days / 3 teams = 14 days Stress through all bridge structures on completion | 1 | Does not address the orange class 6 - 12 months and on completion these would be 8 weeks away from requiring intervention at worst case. | Disregarded in informal consultation as prohibitive to externals and requires access in Y3 and 4 when others degrade, based on degradation rates. Does not treat the root cause completely. Aids to further spoil the ongoing external stakeholder relationships
|  |  | 2 | We run the risk of introducing a new request for Orange Wheel Timbers which have deteriorated in early 2021 thereby disillusioning our external stakeholders by disrupting service again.
|  |  | 3 | We run the risk of further non compliant disruptive requests due to deterioration of the Yellow Wheel Timbers 12 - 24 months.
DEFCON2 | Complete RED & ORANGE 2 x 52hr prep 14 day 2 line block 1 x 27hr and 1 x 12hr disruptive follow up. | Splay guard and running rails to enable access to Wheel Timber area Assume completing 36 pairs, therefore 20 x 52 hrs = 43 days / 3 teams = 20 days (prep / core / follow up) Stress through all bridge structures on completion | 1 | Only achieves a 18 month breathing window at worst case as the yellow timbers will be four months into their live span at completion of works (12 to 24 months) | Disregarded in informal consultation thought prohibitive to externals as does not guarantee more access will not be required. Gives a short term fix without removing the root cause. Aids to further spoil the ongoing external stakeholder relationships.
|  |  | 2 | Totally disrupts service for 14 days throughout the blockade period as no passenger or freight can run for the blockade to enable the works be completed.
|  |  | 3 | Disrupts Network Trips for 14 days impacting national programmes as the trips used to place equipment around the country and Whitemoor has a strategic North / South role between Toton / Doncaster and Hoo / Eastleigh
|  |  | 4 | Run the risk of further interventions required in Yr3 2020/21 and a repeat of DEFCON2 to complete the forecasted works.
DEFCON3 | Completes RED / ORANGE / YELLOW 1 x 27hr Prep / 1 x 12hr Prep / 1 x 10hr Maintenance Prep 2 x 14 day 2 line blockades (split by one week for restocking) 1 x 52hr Core (one week after the 2nd 2 Line Blockade 1 x 27hr and 1 x 12hr Follow Up | Splay guard and running rails to enable access to Wheel Timber area Assume completing 84 pairs, therefore 20 x 52 hrs = 182 days / 6 teams = 33 days (prep / core / follow up) Stress through all bridge structures on completion | 1 | 6 teams working with RRV support do not have enough space to work as unable to feed worksites with materials. Materials have to be fed from both north and south of the works as the worksite is a combination of bridges and embankments surrounded by the SSSI sites on both sides of the boundaries. | Disregarded due to the volume of skilled resources required to deliver works being prohibitive. The disruption to commercial freight is more than likely to have a wider knock on to the national supply chain as it creates the potential for a black swan event as the forecasted freight timetables are aligned to shipping timings. The disruption to National Trips could be unrecoverable as it creates a rippled risk to haulage putting critical logistics in the wrong depot geographically at the wrong time and projects requirements could not be met. In order to properly define this the capacity planning would need to look some 12 weeks in advance for trip moves.
|  |  | 2 | Totally disrupts service for 2 x 14 days throughout the blockade period as no passenger or freight can run for the blockade to enable the works be completed. Even though a 7 day restocking window is assumed this would have a significant national impact given the COVID situation.
|  |  | 3 | Disrupts Network Trips for 2 x 14 days impacting national programmes as the trips used to place equipment around the country and Whitemoor has a strategic North / South role between Toton / Doncaster and Hoo / Eastleigh. This would have a national delivery impact.
DEFCON4 | Completes RED / ORANGE / YELLOW 1 x 12hr Prep, 1 x 10hr Maintenance Prep, 1 x 52hr Prep (2 Line Blocks) 1 x 28 day block with SLW on Weekdays and 4 x 31hr 2 line Weekend blocks, 2 x 52hr 2 Line blocks 1 x 27hr Follow Up | Splay guard and running rails to enable access to Wheel Timber area Assume completing 84 pairs, therefore 20 x 52 hrs = 182 days / 6 teams = 33 days (prep / core / follow up) Stress through all bridge structures on completion | 1 | Timings for train paths will be critical to confirming success of plan, any delay to the 6hr 2 line block on any day will result in shortfall of work | We currently have deconflicted using SLW to ensure as best as practicable that we serve the freight timetables. Weeks 23 & 24 SX: 58 trains asked to go through the SLW, but no path could be found for 17. 41 paths found.(30% deficit) Weeks 25 & 26 SX: 58 trains asked to go through the SLW, but no path could be found for 21. 37 paths found (36% deficit) We are exploring options around cancelling planned works to improve the numbers above however are weighing the sunk cost against risk and commercial timetable loss to make an informed decision.
|  |  | 2 | Little contingency in output rates as MW timings are reliant on an unknown freight timetable capacity.
|  |  | 3 | SLW disrupts the work flow as machines are required to "ground" the jib arm with the load before passage of train utilising ATWS (Automatic Train Warning Systems).
DEFCON5 | Utilise existing, 1 x disruptive prep, 56 day blockade with SLW, no follow up
| No Hrs required | 4368 |  |  | Gives 5yr grace based on current degradation.
| Number of days required | 182 |  |  | Disregarded in informal consultation as too disruptive.
| Number of teams required to complete works in forecast time | 5.871 | 31 |  | Gives 5yr grace based on current degradation.
Enables a degraded service pattern and services the planned renewals so preferred option
Gives 5yr grace based on current degradation. As D4 but service is recovered sooner. Discounted due to 56 days.

## Train Pathing Hr by Hr
Train pathing hour by hour (Orange Train = Problem and Green Train = No Problem) WS Estimated passing time shown in Orange against hrs Lee Edwards estimated a 10 minute difference between SLW trains past blocked road and 10mph TSR covering Manea WS in open railways 45 minute allowance for reverse shunt moves through Manea Crossovers to facilitate wrong road (bidi) travel WE Possession times are 2030 Sat to 0250 Mon | [9 empty] | Days | Friday |  |  |  | Saturday | [23 empty] | Sunday | [23 empty] | Monday | [23 empty] | Tuesday | [23 empty] | Wednesday | [23 empty] | Thursday | [23 empty] | Friday | [23 empty] | Notes
[10 empty] | Hrs | 21 | 22 | 23 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Week | H/C | PT No. | PAP | Location | PDP | Location | Who? | Estimated departure | Estimated Arrival | [5 empty] | Possession bar is broken into Yellow = SLW times and Green 2 Track blocked times | [23 empty] | Possession bar is broken into Yellow = SLW times and Green 2 Track blocked times | [23 empty] | Possession bar is broken into Yellow = SLW times and Green 2 Track blocked times | [23 empty] | Possession bar is broken into Yellow = SLW times and Green 2 Track blocked times | [23 empty] | Possession bar is broken into Yellow = SLW times and Green 2 Track blocked times | [23 empty] | Possession bar is broken into Yellow = SLW times and Green 2 Track blocked times | [23 empty] | Possession bar is broken into Yellow = SLW times and Green 2 Track blocked times
[11 empty] | 2 Track open for service? | [22 empty] | Weekend Block times are 2030 Saturday to 0250 Monday
Week 23 | H/C | PT No. | PAP | Location | PDP | Location | Who? | Estimated departure | Estimated Arrival |  | Time not in possession | [24 empty] | 2 Track block time | [10 empty] | Passing traffic on Down? | [7 empty] | 2 Track Block Time | [9 empty] | SLW Passing traffic on Down? | [117 empty] | Traffic Notes Up Road is blocked for 2 weeks.
| 6T61 | 450956 | 0135 Sat (05/09) | Stowmarket | 1800 Sat | Bury St Edmunds | CRSA | 2230 Fri | 1930 Sat |  |  | WS | [20 empty] | WS | Freight stops | Blockade Start | [147 empty] | To site & from site in traffic
| 6T62 | 450957 | 0135 Sat | Stowmarket | 1700 Sat | Bury St Edmunds | CRSA | 2300 Fri | 1830 Sat |  |  |  | WS | [18 empty] | WS | [150 empty] | To site & from site in traffic
| 6T63 | 450958 | 0135 Sat | Stowmarket | 0245 Mon | Haughley Jn | CRSA | 2330 Fri | 0315 Mon |  |  |  | WS | [51 empty] | WS | [117 empty] | To site in traffic, from site PDP 04:45 Mon. Changed to 02:45 Mon (note this will now mean 12 mile traveling in possession) to hit window between 05:10 and 05:50. Windows to be comfrined and passed to Anglia timer ASAP please. Note RAP team to check path WA Type R P2552448 is one possession which will need to be removed. Back CANNOT TIME UNTIL THE FOC / TOC RE BID FOR THE SLW. Note SCO are now 2 weeks late processing timings to the supplier.
| 6T64 | 450959 | 0800 Sat | Bury St Edmunds | 0910 Sun | Bury St Edmunds | CRSA | 0630 Sat | 1040 Sun | [10 empty] | WS | [27 empty] | WS | [134 empty] | To site in traffic from site via possession Back CANNOT TIME UNTIL THE FOC / TOC RE BID FOR THE SLW. Note SCO are now 2 weeks late processing timings to the supplier.
| 6T65 | 450960 | 0900 Sat | Bury St Edmunds | 0750 Sun | Bury St Edmunds | CRSA | 0730 Sat | 0920 Sun | [11 empty] | WS | [25 empty] | WS | [135 empty] | To site in traffic from site via possession. Back CANNOT TIME UNTIL THE FOC / TOC RE BID FOR THE SLW. Note SCO are now 2 weeks late processing timings to the supplier.
| 6Y70 | 466221 | 2300 Fri | Off Patch | N/A | N/A | LNE | N/A | N/A
| 6G01 | 485829 | 0045 Sat | Off Patch | 1230 Sat | Off Patch | LNE | N/A | N/A
| 6G02 | 485830 | 0630 Sat | Off Patch | 1700 Sat | Off Patch | LNE | N/A | N/A
| 6Y71 | 485834 | 1100 Sat | Off Patch | 0900 Sun | Off Patch | LNE | N/A | N/A
| 6C80 | 485838 | 2045 Sat | Off Patch | 1245 Sun | Off Patch | LNE | N/A | N/A
| 6C81 | 485842 | 2245 Sat | Off Patch | 1645 Sun | Off Patch | LNE | N/A | N/A
| 6P01 | 499633 | 0400 Sat | Rectory Road | 0745 Sun | Rectory Road | SRSA | 0200 Sat | 0945 Sun | [6 empty] | WS | [30 empty] | WS | [135 empty] | To site in traffic from site via possession
| 6P02 | 499634 | 1300 Sat | Rectory Road | 1330 Sun | Rectory Road | SRSA | 1100 Sat | 1530 Sun | [15 empty] | WS | [27 empty] | WS | [129 empty] | To site in traffic from site via possession
| 6Y90 | 509963 | 0005 Tue | Shenfield | 0500 Tue | Shenfield | Romford DU | 2100 Mon | 0800 Tue | [72 empty] | WS | [11 empty] | WS | [88 empty] | To PAP route to confirm if 4E59 path is to be used? From PDP route to confirm if 6L88 path is to be used? FOLLOWING CON CALL WITH ANGLIA TIMER HARD TO SEE HOW PATH OF 6E59 HELP WITH PAP. PATH 6L88 ELY NORTH 05:52 PDP 05:00 THIS DOES NOT WORK. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 2 weeks late processing timings to the supplier.
| 6Y91 | 509964 | 2355 Wed | Shenfield | 0450 Thu | Shenfield | Romford DU | 2000 Wed | 0800 Thu | [120 empty] | WS | [11 empty] | WS | [40 empty] | To PAP route to confirm if 4E59 path is to be used? From PDP route to confirm if 6L88 path is to be used? Note SCO are now 2 weeks late processing timings to the supplier. FOLLOWING CON CALL WITH ANGLIA TIMER HARD TO SEE HOW PATH OF 6E59 HELP WITH PAP. PATH 6L88 ELY NORTH 05:52 PDP 05:00 THIS DOES NOT WORK. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 2 weeks late processing timings to the supplier.
| 6O36 |  | 22:02 SX | Whitemoor | 02:18 SX | Hoo | NR Trip Service | [77 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS |  | Travels via Cambridge therefore and impacts later HO campaign
| 6L37 |  | 09:54 SX | Hoo | 15:33 SX | Whitemoor | NR Trip Service | [64 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [14 empty] | This one will impact any HO or DU stabling in sidings as it also will need to be pathed through
| 6O35 |  | 01:38 SO | Whitemoor | 07:08 SO | Hoo | NR Trip Service | [7 empty] | WS
| 6O35 |  | 01:38 SX | Whitemoor | 07:08 SX | Hoo | NR Trip Service | [55 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | Team need to confirm with SCO National Team what this is to understand criticality
| 6L34 |  | 19:54 SX | Hoo | 00:14 SX | Whitemoor | NR Trip Service | [76 empty] | WS | [25 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | Team need to confirm with SCO National Team what this is to understand criticality
| 6L84 |  | 21:43 MX | Doncaster | 23:54 MX | Whitemoor | NR Trip Service | [29 empty] | WS | [47 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS
| 6E04 |  | 02:13 MX | Whitemoor | 5:24 | Doncaster | NR Trip Service | [8 empty] | WS | [47 empty] | WS
| 6L15 |  | 18:04 SX | Toton | 20:21 SX | Whitemoor | NR Trip Service | [74 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS
| 6M15 |  | 21:35 SX | Whitemoor | 00:56 SX | Toton | NR Trip Service | [78 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | [23 empty] | WS | If possession limits include Whitemoor cannot come on until this train leaves
[11 empty] | SLW over Down Road? | [22 empty] | Weekend Block times are 2030 Saturday to 0250 Monday
Week 24 | H/C | PT No. | PAP | Location | PDP | Location | Who? | Estimated departure | Estimated Arrival | [6 empty] | Limited as FOC running post double line block | [21 empty] | Unlimited due to no FOC. DLB running | [20 empty] | Unlimited due to no FOC. DLB running | [123 empty] | Traffic Notes Up Road is blocked for 1 week
| 6Y90 | 450666 | 0050 Sun | Seven Sisters | 1600 Sun | South Tottenham | SRSA | 2200 Sat | 1900 Sun | [26 empty] | WS Est | [20 empty] | WS Est | [125 empty] | Both ways via possession
| 6T61 | 450992 | 0200 Sat | Ipswich | 1130 Sun | Haughley Jn | SRSA | 2230 Fri | 1330 Sun |  |  | WS Est | [38 empty] | WS Est | [131 empty] | GE possession to start at 22:00, comment from con call 31/07 Update please AW & DT? Or run like week 25? Back via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 6T62 | 451012 | 0200 Sat | East Suffolk Jn | 1100 Sun | Haughley Jn | SRSA | 2300 Fri | 1300 Sun |  |  |  | WS Est | [37 empty] | WS Est | [131 empty] | GE possession to start at 22:00, comment from con call 31/07 Update please AW & DT? Or run like week 25? Back via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 6T63 | 451013 | 0200 Sat | East Suffolk Jn | 1200 Sun | Haughley Jn | SRSA | 2330 Fri | 1400 Sun |  |  |  | WS Est | [38 empty] | WS Est | [130 empty] | GE possession to start at 22:00, comment from con call 31/07 Update please AW & DT? Or run like week 25? Back via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 6T64 | 451014 | 1600 Sat | Ipswich | 1230 Sun | Bury St Edmunds | SRSA | 1400 Sat | 1430 Sun | [18 empty] | WS Est | [23 empty] | WS Est | [130 empty] | To site via SLW Window 12:40 to 13:00 Sat. window to Anglia timer ASAP please. Back via possession NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 6T65 | 451015 | 1700 Sat | Ipswich | 1300 Sun | Bury St Edmunds | SRSA | 1840 Sat | 1500 Sun | [22 empty] | WS Est | [20 empty] | WS Est | [129 empty] | To site via SLW Window 14:00 to 18:00 Sat. window to Anglia timer ASAP please. Back via possession NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 6T66 | 451017 | 2230 Sat | Haughley Jn | 2315 Sun | Bury St Edmunds | SRSA | 2125 Sat | 0356 Mon | [25 empty] | WS Est | [30 empty] | WS Est | [116 empty] | PAP was 00:25 Sun changed to 22:30 Sat via possession. PDP, 23:15 Sun via SLW try and hold service for window 03:56 could have to hold only place would by Ely which the FOC could be using. Mon window to Anglia timer ASAP please. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 4Y09 | 466180 | 0100 Sat | Littleport | 0350 Mon | Littleport | HOBC | 0030 Sat | N/A |  |  |  |  | WS Est | [168 empty] | To site start P255222 post 4Y09 at Ely???? To look at this with Shaun to see how it gets back to Whitemoor???????? My notes PDP 03:50 Mon via SLW in 6L30 path. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 0Y08 | 466184 | 1800 Sun | Littleport | 0330 Mon | Ely North Jn | HOBC | 1730 Sun | 0430 Mon | [45 empty] | WS Est | [10 empty] | WS Est | [116 empty] | Can move through Manea. PAP via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 6Y95 | 433830 | 2200 Mon Recess | Audley End | 0440 Tue | Audley End | HOBC | 2320 Mon | 0615 Tue |  |  |  | WS Est | [71 empty] | WS |  |  |  |  | WS | [92 empty] | PAP 00:50 Tue route to confirm path from 4E59 can be used DT? Will still have to hold to site) PDP 04:45 Tue via SLE window 06:15 ish window to be confirmed to Anglia times before timing.can be processed. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier.
| 0Y09 | 471669 | N/A | Site | 0700 Sat | Littleport | HOBC | 830 Sat | 0700 Sat | [12 empty] | WS | [22 empty] | WS | [137 empty] | PDP 07:00 Sat via SLW window to Anglia timer ASAP please NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO are now 1 weeks late processing timings to the supplier. Confirm Dep and Arr days (I&J)
| 0Y07 | 509743 | 0030 Thu | Broxbourne | 0608 Thu | Broxbourne | HOBC | 2330 | Aft. 0615 Thu | [123 empty] | WS | [6 empty] | WS | [42 empty] | Works Exit Whitemoor 22:31 Back Whitmoor 09:21 can it have this path, DT? Comments from SB email Confirm Dep day (I)
| PLPR |  | 1802 | Peterborough | 1844 | Ely North Jn | PLPR
[35 empty] | Weekend Block times are 2030 Saturday to 0250 Monday | [147 empty] | Tuesday Wk24 needs a trip past Manea to Scotland
Week 25 | H/C | PT No. | PAP | Location | PDP | Location | Who? | Estimated departure | Estimated Arrival | [6 empty] | Limited as FOC running post double line block | [17 empty] | Freight stops |  |  |  |  | Unlimited due to no FOC. DLB running | [15 empty] | Unlimited due to no FOC. DLB running | [127 empty] | The Possession swaps from one to the other between Dn & Up roads. Dn Road (Page 82) is blocked
| 6T62 | 451016 | 0240 Sat | Ipswich | 1130 Sun | Haughley Jn | SRSA | 0001 Sat | 1330 Sun |  |  |  |  | WS Est | [36 empty] | WS Est | [131 empty] | Double line block starts later to allow trip past in SLW; Possession to be taken post 6Y90. This night 4 trains in total to pass before possession is taken P2825755. Head code could change from last train being 6Y90 Commetns to be added to PPS item LE? PDP via possession NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 7th August. Processing timings to the supplier, Friday 14th August.
| 6T63 | 451036 | 0240 Sat | Ipswich | 1100 Sun | Haughley Jn | SRSA | 0030 Sat | 1300 Sun |  |  |  |  | WS Est | [36 empty] | WS Est | [131 empty] | Double line block starts later to allow trip past in SLW; Possession to be taken post 6Y90. As above Blue & red comment
| 6Y90 | 451040 | 0240 Sat | Ipswich | 1200 Sun | Haughley Jn | SRSA | 2330 Fri | 1400 Sun |  |  |  | WS Est | [38 empty] | WS Est | [130 empty] | Double line block starts later to allow trip past in SLW; Possession to be taken post 6Y90. As above Blue & red comment
| 6T64 | 451075 | 1600 Sat | Ipswich | 1230 Sun | Haughley Jn | SRSA | 1400 Sat | 1430 Sun | [17 empty] | WS Est | [24 empty] | WS Est | [130 empty] | Clear of two line block to allow trip past in SLW; gap at 14.00 to trip past Manea SLW. Window to be confrimed to Anglia timer ASAP please. Note this window will not meet planned PAP 16:00 Sat. More like 19:00 PAP. Steer please? PDP via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 7th August. Processing timings to the supplier, Friday 14th August.
| 6Y91 | 451098 | 1700 Sat | Ipswich | 1300 Sun | Haughley Jn | SRSA | 1500 Sat | 1500 Sun | [18 empty] | WS Est | [24 empty] | WS Est | [129 empty] | Clear of two line block to allow trip past in SLW; gap at 15.00 to trip past Manea SLW. CP window 14:00 to 18:00. Note roads change at 16:00 Sat will have wait until 16:00 before moving via possession. Steer Please? Window to be confrimed to Anglia timer ASAP please. PAP 17:00 Sat. More like 21:00 PAP. Steer please? PDP via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 7th August. Processing timings to the supplier, Friday 14th August.
| 6T65 | 451102 | 0025 Sun | Haughley Jn | 2315 Sun | Haughley Jn | SRSA | 2230 Sat | 0115 Mon | [26 empty] | WS Est | [26 empty] | WS Est | [119 empty] | Pass via 2 Line possession to and from PAP / PDP. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 7th August. Processing timings to the supplier, Friday 14th August.
| 6G01 | 466311 | 0150 Sun | Off Patch | 0710 Sun | Off Patch | LNE | 2130 Sat | 1030 Sun | [25 empty] | WS Est | [12 empty] | WS Est | [134 empty] | Can pass through the SLW as the 2 line block has been moved
| 6G02 | 473282 | 0150 Sun | Off Patch | 0710 Sun | Off Patch | LNE | 1947 Sat | 1000 Sun | [23 empty] | WS Est | [14 empty] | WS Est | [134 empty] | Can pass through the SLW as the 2 line block has been moved
| 6B01 | 472423 | 2210 Sat | Off Patch | N/A | N/A | LNE | N/A | N/A | [24 empty] | Freight stops | [148 empty] | Can pass through the SLW as the 2 line block has been moved
| 6B02 | 472424 | 2230 Sat | Off Patch | N/A | N/A | LNE | N/A | N/A | [173 empty] | Can pass through the SLW as the 2 line block has been moved
| 6T66 | 454943 | N/A | N/A | 0445 Mon | Moulton | CRSA | N/A | 0645 Mon | [173 empty] | Needs a path to Parkston, outstabling move on MWN24 Thursday 7/9, 4E59 blocks this path,. Above comment midweek 24 please? PDP coming back is at risk as there is only a trip post 09.00 (6L86 Right Road at Manea) therefore needs to parked in a siding, therefore back at Whitemoor at circa 1000hrs.. When a window has been passed to Anglia timer (ASAP PLEASE) he will try and get a path from PDP to Whitemoor. Look at holding Stow Down goods Loop or Ely Up goods Loop. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 7th August. Processing timings to the supplier, Friday 14th August.
| 6T67 | 508087 | 0240 Sat | Moulton | 0445 Mon | Moulton | CRSA | 0100 Sat | 0715 Mon |  |  |  | WS Est | [169 empty] | Needs a path to Parkston, outstabling move on MWN24 Thursday 7/9, 4E59 blocks this path, Above incorrect remove comment PDP coming back is at risk as there is only a trip post 09.00 (6L86 Right Road at Manea) therefore needs to parked in a siding, therefore back at Whitemoor at circa 1000hrs.Possible window 09:00 or 14:30 with 6T66 possibly taking 09:00window, 6T67 will be using 14:30 if available meaning back into Whitemoor around 15:45. Windows to Anglia timer ASAP please. Look at holding at Parkston and try and find path for window. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 7th August. Processing timings to the supplier, Friday 14th August.
|  | 509225 | 0115 Tue | Upminster | 0435 Tue | Upminster | Romford DU | [175 empty] | Late requests and rejected
|  | 509226 | 0115 Wed | Upminster | 0435 Wed | Upminster | Romford DU | [175 empty] | Late requests and rejected
|  | 509449 | 0115 Thu | Upminster | 0435 Thu | Upminster | Romford DU | [175 empty] | Late requests and rejected
|  | 509450 | 0115 Fri | Upminster | 0435 Fri | Upminster | Romford DU | [175 empty] | Late requests and rejected
| 6Y92 | 510176 | 0150 Sun | Meldreth | 0630 Sun | Meldreth | Tott DU | 2350 Sat | 0830 Sun | [27 empty] | WS Est | [8 empty] | WS Est | [136 empty] | Double line taken post trip (02.00 Sun to 08.00 Sun) so travelling through possession in both directions. Agree
[35 empty] | 21 | 22 | 23 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 0 | 1 | 2 | 3
Week 26 | H/C | PT No. | PAP | Location | PDP | Location | Who? | Estimated departure | Estimated Arrival | [5 empty] | Limited as FOC running post double line block | [18 empty] | Freight stops | WS Est 23: Unlimited due to no FOC. DLB running; WS Est 17: Unlimited due to no FOC. DLB running; WS Est 0: Unlimited due to no FOC. DLB running | [117 empty] | Possession not to be taken until passage of 6T63, 2 line block is split to a 5hr and 3hr window
| 6Y91 | 450620 | 0135 Sat | Ipswich | 0445 Mon | Haughley Jn | CRSA | 2230 Fri | 0745 Mon |  |  | WS Est | [170 empty] | Trip through in SLW prior to block being taken, This night 5 trains in total to pass before possession is taken. Commetns to be added to PPS item LE? Trip back is post 09.00 as per Wk25. PDP 04:45 Mon will have to hold poss Stow Down Goods Loop. When a window has been passed to Anglia timer (ASAP PLEASE) he will try and get a apth from PDP to Whitemoor. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 14th August. Processing timings to the supplier, Friday 21st August.
| 6T61 | 454911 | 0105 Sat | Newport | 0440 Mon | Shepreth Jn | CRSA | 2300 Fri | 0640 Mon |  |  | WS Est | [170 empty] | Trip through in SLW prior to block being taken,This night 4 trains in total to pass before possession is taken. Commetns to be added to PPS item LE? Trip back is post 09.00 as per Wk25. Possible window 09:00 or 14:30 with 6Y91 possibly taking 09:00 window, 6T61 will be using 14:30 if available meaning back into Whitemoor around 15:45. Windows to Anglia timer ASAP please. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 14th August. Processing timings to the supplier, Friday 21st August.
| 6G36 | 472361 | 2215 Sat | Off Patch | 0845 Sun | Off Patch | LNE | 2100 Sat | 0930 Sun | [25 empty] | 21: WS Est; WS Est 9: WS Est | [117 empty] | Trip through in SLW prior to block being taken. This night 5 trains in total to pass before possession is taken. Commetns to be added to PPS item LE?
| 6Y92 | 506810 | 0135 Sat | Bury St Edmunds | 1400 Sun | Bury St Edmunds | WDA | 2330 Fri | 1530 Sun |  |  |  | WS Est | [21 empty] | WS Est 15: WS Est | [117 empty] | Trip through in SLW prior to block being taken, back in via possession. This night 5 trains in total to pass before possession is taken. Commetns to be added to PPS item LE? Back via possession
| 6T62 | 506811 | 0205 Sat | Bury St Edmunds | 1300 Sun | Bury St Edmunds | WDA | 0001 Sat | 1430 Sun |  |  |  | WS Est | [21 empty] | WS Est 14: WS Est | [117 empty] | Trip through in SLW prior to block being taken, back in via possession. This night 5 trains in total to pass before possession is taken. Commetns to be added to PPS item LE? Back via possession
| 6T63 | 507015 | 2300 Sun | Second Drove | 0255 Mon | Second Drove | CRSA | 2230 Sun | 0325 Mon | [25 empty] | WS Est 22: WS Est; WS Est 3: WS Est | [117 empty] | This train RDT works within the Manea blockade. Lee as said PT has been updated with the project to what was agreed please confirm you and the project are happy with the updated PT to deliver the rails?
| 6T70 | 472406 | 0045 Tue | Canons Mill Lane | 0450 Tue | Canons Mill Lane | Tott DU | 2300 | 600 | [173 empty] | Last freight 4L76 time at Manea 23.20, RDT needs to be at Manea for 21.45-22.20 or 22.45-22.55. to be confirmed in Wk21. When it is confirmed path from 4L76 can be used, service can be processed for timing. PDP will have to be post 09.00hrs so will need to park in siding. Hold Coldham Lane otr Ely. Window to Anglia timer ASAP please? NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 14th August. Processing timings to the supplier, Friday 21st August.
| 6T72 | 472417 | 0055 Wed | Bishop Stortford | 0435 Wed | Bishop Stortford | Tott DU | 2300 | 600 | [173 empty] | Last freight 4L76 time at Manea 23.20, RDT needs to be at Manea for 21.45-22.20 or 22.45-22.55. to be confirmed in Wk21. When it is confirmed path from 4L76 can be used, service can be processed for timing. PDP will have to be post 09.00hrs so will need to park in siding Hold Coldham Lane otr Ely. Window to Anglia timer ASAP please? NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 14th August. Processing timings to the supplier, Friday 21st August.
| 6T74 | 472420 | 0055 Thu | Bishop Stortford | 0435 Thu | Bishop Stortford | Tott DU | 2300 | 600 | [173 empty] | Last freight 4L76 time at Manea 23.20, RDT needs to be at Manea for 21.45-22.20 or 22.45-22.55. to be confirmed in Wk21. When it is confirmed path from 4L76 can be used, service can be processed for timing. DT? PDP will have to be post 09.00hrs so will need to park in siding. Hold Coldham Lane otr Ely. Window to Anglia timer ASAP please? NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 14th August. Processing timings to the supplier, Friday 21st August.
| 6T76 | 472422 | 0045 Fri | Harlow Town | 0400 Fri | Harlow Town | Tott DU | 2300 | 600 | [173 empty] | 4L78 departs Manea 23.00 so no outward problem, When it is confirmed path from 4L78 can be used, service can be processed for timing. PDP will have to be post 09.00hrs so will need to park in siding.Hold Coldham Lane otr Ely. Window to Anglia timer ASAP please? NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 14th August. Processing timings to the supplier, Friday 21st August.
[35 empty] | 21 | 22 | 23 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 0 | 1 | 2 | 3
Week 27 | H/C | PT No. | PAP | Location | PDP | Location | Who? | Estimated departure | Estimated Arrival | [5 empty] | Limited as FOC running post double line block | [18 empty] | Freight stops | 23: Unlimited due to no FOC. DLB running; 12: Last Double Line Block during blockade | [117 empty] | Possession not to be taken until passage of 6T6, 2 line block is to be planned around 00.01
| 6Y93 | 454056 | 0100 Sun | Sawbridgeworth | N/A | N/A | HOBC | 2300 Sun | N/A | [25 empty] | 3: Blockade Finish | [117 empty] | Cancelled
| 6T61 | 454176 | 0235 Sat | Arlesford | 1410 Sun | Colchester | CRSA | 2130 Fri | 1800 Sun |  | WS Est | [23 empty] | 17: WS Est | [117 empty] | Out before 2 line block. My note says the same as other weeks 2 line block to be taken post train passing Manea? 4 Friday night starters. Back via possession NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 21st August. Processing timings to the supplier, Friday 28th August.
| 6T62 | 454177 | 0235 Sat | Arlesford | 1510 Sun | Colchester | CRSA | 2300 Fri | 1900 Sun |  |  | WS Est | [22 empty] | 18: WS Est | [117 empty] | Out before 2 line block. My note says the same as other weeks 2 line block to be taken post train passing Manea? 4 Friday night starters. Back via possession NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 21st August. Processing timings to the supplier, Friday 28th August.
| 6T63 | 454178 | 1150 Sat | Colchester | 1710 Sun | Colchester | CRSA | 0830 Sat | 2000 Sun | [12 empty] | WS Est | [12 empty] | 19: WS Est | [117 empty] | Out through SLW.Windows to Anglia timer ASAP please. Back via possession
| 6T64 | 454179 | 1920 Sat | Colchester | 1810 Sun | Colchester | CRSA | 1600 Sat | 2030 Sun | [20 empty] | WS Est |  |  |  |  | 20: WS Est | [117 empty] | Out through SLW. Windows to Anglia timer ASAP please. Back via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 21st August. Processing timings to the supplier, Friday 28th August.
| 6G30 | 465856 | 1700 Sun | Off Patch | N/A | N/A | LNE | 1300 Sun | N/A | [18 empty] | WS Est
| 6C60 | 473200 | 0200 Sat | Barking | 1830 Sun | Barking | Volkers | 2200 Fri | 2230 Sun |  |  | WS Est | [22 empty] | 22: WS Est | [117 empty] | to site should clear Manea before two line block taken. But same comment as 6T61 & T62. Back via possession. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 21st August. Processing timings to the supplier, Friday 28th August.
| 6C61 | 473202 | 0200 Sat | Barking | 0900 Sun | Barking | Volkers | 2230 Fri | 1300 Sun |  |  | WS Est | [22 empty] | 13: WS Est | [117 empty] | to site should clear Manea before two line block taken. But same comment as 6T61 & T62. Back via possession NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 21st August. Processing timings to the supplier, Friday 28th August.
| 6Y90 | 480430 | 0135 Sun | Stowmarket | 0430 Mon | Stowmarket | HOBC | 2230 Sat | 0730 Mon | [25 empty] | 22: WS Est | [117 empty] | Out through possession, back through in traffic. Agree. NOTE UNABLE TO TIME UNTIL FOC / TOC RE BID FOR THE SLW. Note SCO should be sending bids to CP for timing Friday 21st August. Processing timings to the supplier, Friday 28th August.
| 6Y70 | 465855 | N/A | N/A | 1900 Sun | Off Patch | LNE | N/A | 0100 Mon | [56 empty] | WS Est | [116 empty] | Back through SLW
| 6Y94 | 454909 | N/A | N/A | 0430 Mon | Ipswich | SRSA | N/A | 0700 Mon | [25 empty] | 1: WS Est | [117 empty] | Back through SLW
| 6Y71 | 479812 | N/A | N/A | 1000 Sun | Off Patch | LNE | N/A | N/A | [173 empty] | Confirm if impacts the commercial freight timetable
| 6G31 | 482147 | 2300 Sat | Off Patch | 0845 Sun | Off Patch | LNE | 2130 Sat | 0945 Sun | [25 empty] | 21: WS Est | [117 empty] | Confirm if impacts the commercial freight timetable
|  | 509302 | 0100 Sun (04/10) | Homerton | N/A | Off Patch | LNE |  | N/A | [173 empty] | Confirm if impacts the commercial freight timetable
Blockade finish Monday 5th of Oct

## Network Service Maps and Notes
Service | Service Frequency
SX | Monday, Tuesday, Wednesday, Thursday, Friday
MSX | Tuesday, Wednesday, Thursday, Friday
SO | Saturday only
MX | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday
MWFO | Monday, Wednesday, Friday only

## Previous Plans
Year | Plan
2018/19 | Week No. | Potential times |  | Worksite No. | Possession | ACT Req | Times | Notes
|  | From | To
| 18 | 2300 Sat | 0830 Sun |  | No | Yes | 9hrs 30m
| 19 | 2255 Sat | 0915 Sun |  | No | Yes | 10hr 20m
| 20 | 0100 Sun | 0850 Sun |  | P/2443347 | Yes | 7hrs 50m | High Output worksite 73m 60ch - 76m 60ch
| 21 | 2350 Sat | 0840 Sun |  | P/2301769 | Yes | 8hrs 50m
| 22 | Protected paths in place |  |  |  | Yes | 0
| 23 | 0100 Sun | 0850 Sun |  | P/2448289 |  | 0 | High Output worksite 73m 60ch - 76m 60ch - Not compatible with HOBC
| 24 | 0100 Sun | 0815 Sun | 6131333 | P/2447414 |  | 7hr 15m | High Output worksite 73m 60ch - 76m 60ch - requires block to be extended out
| 25 | 0030 Sun | 1030 Sun | 6131339 | No |  | 10hr
| 26 | 2300 Sat | 0745 Sun | 6131358 | No |  | 8hr 45m | Protected Path P/2465431 from 0745 Sun
| 27 | 0030 Sun | 2300 Sun | 6056040 | P/2363433 |  | 22hr 30m | Disruptive block
| 28 | 0030 Sun | 2300 Sun | 6056062 | P/2307455 |  | 22hr 30m | Disruptive block
| 29 | 2255 Sat | 0700 Sun | 6131364 | No |  | 8hr 5m | Protected Path P/2468316 from 0700 Sun
| 30 | Protected Path |  |  |  |  | 0
| 31 | 0120 Sun | 0800 Sun | 6131369 | P/2547472 |  | 6hr 40m | PP P/2492373 from 0815 Sun
| 32 | 0100 Sun | 0830 Sun | 6131372 | P/6131372 |  | 7hr 30m | PP P/2471576 until 0115 Sun
| 33 | 2350 Sat | 1050 Sun | 6131377 | P/2433168 |  | 11hr | Confirmed with Tott DU to link into cyclical
| 34 | 0105 Sun | 1030 Sun | 6131381 | P/2554462 |  | 9hr 25m
| 35 | 0050 Sun | 0830 Sun | 6131384 | P/2557928 |  | 7hr 40m | PP P/2477424 from 0850 Sun
| 36 | 2255 Sat | 1045 Sun | 6131387 | P/2561194 |  | 11hr 50m
| 37 | 2350 Sat | 0900 Sun | 6131391 | P/2424340 |  | 9hr 10m | Confirmed with Tott DU to link into cyclical
|  | 2240 Mon | 0435 Tue | 6236988 | P/2461652 |  |  | Agreed with Ely DU
|  | 2240 Tue | 0435 Wed | 6236997 | P/2461743 |  |  | Agreed with Ely DU
|  | 2240 Wed | 0435 Thur | 6236999 | P/2461744 |  |  | Agreed with Ely DU
|  | 2240 Thur | 0435 Fri | 6237000 | P/2461745 |  |  | Agreed with Ely DU
| 38 | 2255 Sat | 1045 Sun | 6131393 | P/2565101 |  | 11hr 50m
| 39 | 2255 Sat | 0900 Sun | 6131398 | No |  | 10hr 25m | PP P/2486907 from 0920 Sun
| Christmas | 2315 Mon | 0400 Thur | 6131400 | P/2548099 |  | 52hrs | Additional disruptive possession
| 41 | 0200 Sun | 0900 Sun | 6156403 | No |  | 7hr | PP P/2504664 until 0200 Sun, P/2498791 from 0900 Sun
| 42 | 0300 Sun | 0800 Sun |  |  |  | 5hr | PP P/2498803 until 0300 Sun
| 43 | 0050 Sun | 0700 Sun | 6156482 |  |  | 6hr 10m | PP P/2502227 from 0700 Sun
| 44 | 2315 Fri | 0250 Mon | 6252726 | NEW |  | 52hr | Additional disruptive possession
| 44 | 01:00 Sat | 15:00 Sat | 6252726 |  |  | 14hrs | Working time available in week 44 access.
| 44 | 21:00 Sat | 13:00 Sun | 6252726 |  |  | 16hrs | Working time available in week 44 access.
| 44 | 19:00 Sun | 03:00 Mon | 6252726 |  |  | 8hrs | Working time available in week 44 access.
| 45 | 0030 Sun | 0830 Sun | 6156488 | P/2425329 |  | 8hr | Confirmed with Tott DU to link into cyclical
|  | 2250 Sat | 0250 Mon | 6252735 | NEW |  | 27hr | Additional disruptive possession
| 45 | 01:00 Sun | 07:00 Sun | 6252735 |  |  | 6hrs | Working time available in week 45 access.
| 45 | 12:00 Sun | 02:50 Mon | 6252735 |  |  | 14.50hrs | Working time available in week 45 access.
| 46 | 2250 Sat | 0250 Mon | 6252738 | NEW |  | 27hr | Additional disruptive possession
| 46 | 00:00 Sat | 09:00 Sun | 6252738 |  |  | 9hrs | Working time available in week 46 access.
| 46 | 21:00 Sun | 03:00 Mon | 6252738 |  |  | 6hrs | Working time available in week 46 access.
| 47 | 0050 Sun | 0720 Sun | 6156538 |  |  | 6hr 30m | PP P/2507436 until 0050 Sun, P/2507438 from 0830 Sun
|  | 2250 Sat | 0250 Mon | 6256866 | NEW |  | 27hr | Additional disruptive possession
| 47 | 22:50 Sat | 08:00 Sun | 6256866 |  |  | 9hrs | Working time available in week 47 access.
| 47 | 12:00 Sun | 02:50 Mon | 6256866 |  |  | 15hrs | Working time available in week 47 access.
| 48 | 0100 Sun | 0720 Sun | 6156542 |  |  | 6hr 20m | PP P/2507646 until 0100 Sun, P/2507654 from 0830 Sun
|  | 2250 Sat | 0250 Mon | 6256867 | NEW |  | 27hr | Additional disruptive possession
| 48 | 01:00 Sun | 08:00 Sun | 6256867 |  |  | 7hrs | Working time available in week 48 access.
| 48 | 16:00 Sun | 03:00 Mon | 6256867 |  |  | 11hrs | Working time available in week 48 access.
| 49 | 0030 Sun | 0830 Sun | 6156548 |  |  | 8hr | PP P/2515540 until 0030 Sun, P/2521143 from 0830 Sun
|  | 2250 Sat | 0250 Mon | 6252739 | NEW |  | 27hr | Additional disruptive possession
| 49 | 22:50 Sun | 10:00 Sun | 6252739 |  |  | 11hr 10m | Working time available in week 49 access.
| 49 | 17:00 Sun | 02:50 Mon | 6252739 |  |  | 9hr 50m | Working time available in week 49 access.
| 50 | 2255 Sat | 1045 Sun | 6156557 |  |  | 11hr 50m
| 51 | 0030 Sun | 0830 Sun | 6156553 | P/2425330 |  | 8hr | Tott DU PL Tamper 74mp - 81mp
| 52 | 0300 Sun | 1045 Sun | 6156554 |  |  | 7hr 45m | PP P/2515535 0100 - 0300 Sun
Ellipse Plans
Engineer | Work Group Set | MNT Code & Desc | MNT Unit of Measure Code & Desc | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2020/21 |  | 2020/21 |  | 2020/21 |  | 2020/21 |  | Total Units | Total Hours
|  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 8 |  | 10 |  | 11 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4
|  |  |  | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours
Barking TME | Barking SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber |  |  |  |  | 56 | 36 |  |  | 400 | 32 | 202.2 | 36 | 10 | 3 | 146 | 63.75 | 230.1 | 176 | [8 empty] | 29.4 | 33.25 | 26 | 70 | [6 empty] | 106.4 | 71.75 | 50.4 | 41 | 2.6 | 3.83 | 4.4 | 40.25 | 16.7 | 53.24 |  |  | 41 | 21.5 |  |  |  |  | 10 | 24 |  |  |  |  | 20 | 7 |  |  |  |  | 3 | 12 |  |  |  |  | 3.7 | 40 | 2.2 | 10 |  |  | 1.5 | 9 | [8 empty] | 1.1 | 29 | 70.6 | 33.75 |  |  |  |  | 2 | 1.5 | [6 empty] | 1.1 | 7.5 | 3 | 8 |  |  |  |  | 0.1 | 6 | 44 | 16.5 |  |  | 8 | 15 | 6.3 | 30 |  |  | 6 | 12 | 2.2 | 10.5 | 12 | 4 | 15.6 | 37 | 2.2 | 24 | 20 | 15.16 |  |  | 3 | 6 | 27 | 19 | 1 | 0.25 | 16 | 27 | 20 | 8 | 8.8 | 5 | 11 | 5 | 1642.6 | 1103.73
| Leigh On Sea SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [88 empty] | 1 | 30 | [62 empty] | 1 | 30
Ely TME | Ely SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [6 empty] | 11.4 | 21 | 23.4 | 37.5 | 21.2 | 32 |  |  |  |  | 38.4 | 66.5 |  |  |  |  | 54.1 | 138 | 4 | 28 | 123 | 65.33 | [124 empty] | 275.5 | 388.33
| Ely SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [6 empty] | 9 | 54 |  |  |  |  | 3 | 5 |  |  |  |  | 1 | 13 | 4 | 60 | [20 empty] | 2 | 12 | [8 empty] | 5 | 11 |  |  | 16 | 35 | [80 empty] | 1 | 10 | [12 empty] | 41 | 200
| March SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 2 | 73 | 25 | 50 | 9 | 22.5 |  |  | 8 | 16 |  |  | 25 | 58 | 11 | 18 |  |  | 36 | 51.5 |  |  | 100.1 | 184 | 48 | 92 |  |  | 12 | 10 |  |  | 6 | 13 | [8 empty] | 20 | 45 | [12 empty] | 2 | 3 | [6 empty] | 2 | 40 |  |  | 2 | 12 | 68 | 51 | [10 empty] | 2 | 22 | [6 empty] | 35 | 29 |  |  |  |  | 1 | 10 | 178.2 | 49 | 30 | 10 | 18 | 19 |  |  |  |  | 60 | 20 | [14 empty] | 2 | 20 | [6 empty] | 50 | 25.5 | 116 | 43 |  |  |  |  | 2 | 12 | 4 | 11 | 162 | 77 | 206 | 100 | 21 | 9.5 |  |  | 1263.3 | 1196
Ipswich S&TME | Norwich SM(SIGNALS) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [6 empty] | 1 | 6 | [144 empty] | 1 | 6
Ipswich TME | Colchester SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [8 empty] | 4 | 3 |  |  |  |  | 1 | 3 | 4 | 1 | 4 | 3 | [16 empty] | 4 | 4 | [6 empty] | 4 | 22 |  |  | 3 | 11 | 4 | 10 | [26 empty] | 22 | 6 |  |  |  |  | 2 | 4 |  |  |  |  | 33 | 22 | 18 | 11.75 |  |  | 30 | 10 | [6 empty] | 2 | 0.5 | 9 | 21 | 11 | 4 | 6 | 104 | 160 | 30 | [34 empty] | 15 | 9 |  |  | 336 | 279.25
| Ipswich SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [20 empty] | 2 | 70 | [16 empty] | 0.2 | 10 | [52 empty] | 80 | 72 | [8 empty] | 11 | 10 | 51 | 89 | 44 | 22 | 28 | 28.02 | 2 | 198 | 9 | 2 | 140 | 68 |  |  | 44 | 30 | 1 | 20 |  |  |  |  | 83 | 19 | [8 empty] | 3 | 16 |  |  |  |  | 1 | 32 | [8 empty] | 499.2 | 686.02
| Ipswich SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber |  |  | 3.5 | 14 |  |  | 10 | 14 |  |  | 4.5 | 11 |  |  | 4 | 7 | 2 | 3 | [12 empty] | 4 | 4 |  |  | 2 | 6 | [50 empty] | 4.8 | 58 |  |  |  |  | 12 | 15 | 2.2 | 5 | [6 empty] | 4 | 13 |  |  |  |  | 1 | 2 | [6 empty] | 6 | 20 | 1 | 1 | [24 empty] | 4 | 10.83 | [6 empty] | 65 | 183.83
| Ipswich SM(W&G) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [54 empty] | 3 | 4 | [96 empty] | 3 | 4
Norwich TME | Lowestoft SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [8 empty] | 3.2 | 3.5 | 10 | 8 |  |  | 3 | 2.33 | 2.2 | 3.5 |  |  |  |  | 1 | 2 |  |  | 0.6 | 10 | [10 empty] | 5.8 | 10 | [8 empty] | 3.6 | 17 |  |  | 1 | 5 | 6 | 133 |  |  |  |  | 3 | 4 | [22 empty] | 8 | 10 | [10 empty] | 6 | 33 |  |  | 30 | 25 | [16 empty] | 0.6 | 6 | 10 | 18 | 32 | 103 | 4 | 46 |  |  | 1 | 3 |  |  |  |  | 1 | 1 | 10 | 7 | 14 | 28 |  |  | 4 | 0.02 | [6 empty] | 6 | 0.02 | 166 | 478.37
| Norwich SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber |  |  | 6 | 25.5 | [6 empty] | 0.4 | 1 | [28 empty] | 12 | 50 | [16 empty] | 21 | 20 |  |  | 2 | 10 | [10 empty] | 2 | 4 | [8 empty] | 1 | 2 | [32 empty] | 2 | 12 | [14 empty] | 22 | 6 | 6 | 25 |  |  | 40 | 9 | 22 | 20.5 |  |  | 41 | 28 | 5.2 | 11 | 6 | 5 | 188.6 | 229
| Norwich SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 12 | 8 | 51.4 | 25 |  |  |  |  | 49 | 12 | [6 empty] | 30 | 12.5 | 40 | 17 | [16 empty] | 0.8 | 12 |  |  | 17 | 33 | 16 | 12.01 | 1 | 9 | [18 empty] | 7 | 8.25 | [6 empty] | 10 | 6 | [12 empty] | 36.5 | 23 | 1 | 1 |  |  | 400 | 40 | [6 empty] | 20 | 18.02 |  |  |  |  | 2 | 1 | [6 empty] | 72 | 24 |  |  | 1 | 18 |  |  |  |  | 126 | 103.66 | 16 | 53.25 |  |  |  |  | 20 | 53.4 | 20 | 1 | [16 empty] | 948.7 | 491.09
Romford TME | Liverpool Street SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [8 empty] | 4 | 0.01 | [104 empty] | 2 | 1 | 29 | 11.75 | [24 empty] | 15 | 180 | [8 empty] | 50 | 192.76
| Shenfield SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 41.8 | 47 | 12 | 24.5 | [8 empty] | 4.4 | 42 | [32 empty] | 2 | 2 |  |  | 3.3 | 22 | [8 empty] | 6.6 | 1.5 | [90 empty] | 70.1 | 139
| Stratford SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [140 empty] | 0.4 | 4 | [10 empty] | 0.4 | 4
Tottenham TME | Broxbourne SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [26 empty] | 2 | 10 | [34 empty] | 10 | 6 | [16 empty] | 50 | 1 | [60 empty] | 2 | 4 | [8 empty] | 64 | 21
| Camden SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 21 | 265 |  |  |  |  | 2 | 40 | 44 | 24 | [18 empty] | 4 | 56 | [20 empty] | 4 | 10 | [18 empty] | 2 | 1 | [8 empty] | 11 | 2 | [14 empty] | 1 | 32 | [16 empty] | 3 | 14 | [26 empty] | 3 | 24 | [8 empty] | 95 | 468
| Tottenham SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [22 empty] | 0.2 | 2.5 | [128 empty] | 0.2 | 2.5
| Tottenham SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [16 empty] | 24 | 12 | [6 empty] | 71 | 26 | [24 empty] | 30 | 15 |  |  |  |  | 8 | 12 | [18 empty] | 12 | 10 |  |  | 10 | 22 | 4 | 7 |  |  | 20 | 17.36 |  |  | 4 | 14 | [16 empty] | 15 | 5 | [14 empty] | 1 | 20 | [20 empty] | 1 | 1 |  |  |  |  | 200 | 161.36

## Maintenance Plan
Ellipse Plans
Engineer | Work Group Set | MNT Code & Desc | MNT Unit of Measure Code & Desc | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2014/15 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2015/16 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2016/17 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2017/18 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2018/19 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2019/20 |  | 2020/21 |  | 2020/21 |  | 2020/21 |  | 2020/21 |  | Total Units | Total Hours
|  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 8 |  | 10 |  | 11 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 1 |  | 2 |  | 3 |  | 4
|  |  |  | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours | Units | Hours
Barking TME | Barking SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber |  |  |  |  | 56 | 36 |  |  | 400 | 32 | 202.2 | 36 | 10 | 3 | 146 | 63.75 | 230.1 | 176 | [8 empty] | 29.4 | 33.25 | 26 | 70 | [6 empty] | 106.4 | 71.75 | 50.4 | 41 | 2.6 | 3.83 | 4.4 | 40.25 | 16.7 | 53.24 |  |  | 41 | 21.5 |  |  |  |  | 10 | 24 |  |  |  |  | 20 | 7 |  |  |  |  | 3 | 12 |  |  |  |  | 3.7 | 40 | 2.2 | 10 |  |  | 1.5 | 9 | [8 empty] | 1.1 | 29 | 70.6 | 33.75 |  |  |  |  | 2 | 1.5 | [6 empty] | 1.1 | 7.5 | 3 | 8 |  |  |  |  | 0.1 | 6 | 44 | 16.5 |  |  | 8 | 15 | 6.3 | 30 |  |  | 6 | 12 | 2.2 | 10.5 | 12 | 4 | 15.6 | 37 | 2.2 | 24 | 20 | 15.16 |  |  | 3 | 6 | 27 | 19 | 1 | 0.25 | 16 | 27 | 20 | 8 | 8.8 | 5 | 11 | 5 | 1642.6 | 1103.73
| Leigh On Sea SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [88 empty] | 1 | 30 | [62 empty] | 1 | 30
Ely TME | Ely SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [6 empty] | 11.4 | 21 | 23.4 | 37.5 | 21.2 | 32 |  |  |  |  | 38.4 | 66.5 |  |  |  |  | 54.1 | 138 | 4 | 28 | 123 | 65.33 | [124 empty] | 275.5 | 388.33
| Ely SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [6 empty] | 9 | 54 |  |  |  |  | 3 | 5 |  |  |  |  | 1 | 13 | 4 | 60 | [20 empty] | 2 | 12 | [8 empty] | 5 | 11 |  |  | 16 | 35 | [80 empty] | 1 | 10 | [12 empty] | 41 | 200
| March SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 2 | 73 | 25 | 50 | 9 | 22.5 |  |  | 8 | 16 |  |  | 25 | 58 | 11 | 18 |  |  | 36 | 51.5 |  |  | 100.1 | 184 | 48 | 92 |  |  | 12 | 10 |  |  | 6 | 13 | [8 empty] | 20 | 45 | [12 empty] | 2 | 3 | [6 empty] | 2 | 40 |  |  | 2 | 12 | 68 | 51 | [10 empty] | 2 | 22 | [6 empty] | 35 | 29 |  |  |  |  | 1 | 10 | 178.2 | 49 | 30 | 10 | 18 | 19 |  |  |  |  | 60 | 20 | [14 empty] | 2 | 20 | [6 empty] | 50 | 25.5 | 116 | 43 |  |  |  |  | 2 | 12 | 4 | 11 | 162 | 77 | 206 | 100 | 21 | 9.5 |  |  | 1263.3 | 1196
Ipswich S&TME | Norwich SM(SIGNALS) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [6 empty] | 1 | 6 | [144 empty] | 1 | 6
Ipswich TME | Colchester SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [8 empty] | 4 | 3 |  |  |  |  | 1 | 3 | 4 | 1 | 4 | 3 | [16 empty] | 4 | 4 | [6 empty] | 4 | 22 |  |  | 3 | 11 | 4 | 10 | [26 empty] | 22 | 6 |  |  |  |  | 2 | 4 |  |  |  |  | 33 | 22 | 18 | 11.75 |  |  | 30 | 10 | [6 empty] | 2 | 0.5 | 9 | 21 | 11 | 4 | 6 | 104 | 160 | 30 | [34 empty] | 15 | 9 |  |  | 336 | 279.25
| Ipswich SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [20 empty] | 2 | 70 | [16 empty] | 0.2 | 10 | [52 empty] | 80 | 72 | [8 empty] | 11 | 10 | 51 | 89 | 44 | 22 | 28 | 28.02 | 2 | 198 | 9 | 2 | 140 | 68 |  |  | 44 | 30 | 1 | 20 |  |  |  |  | 83 | 19 | [8 empty] | 3 | 16 |  |  |  |  | 1 | 32 | [8 empty] | 499.2 | 686.02
| Ipswich SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber |  |  | 3.5 | 14 |  |  | 10 | 14 |  |  | 4.5 | 11 |  |  | 4 | 7 | 2 | 3 | [12 empty] | 4 | 4 |  |  | 2 | 6 | [50 empty] | 4.8 | 58 |  |  |  |  | 12 | 15 | 2.2 | 5 | [6 empty] | 4 | 13 |  |  |  |  | 1 | 2 | [6 empty] | 6 | 20 | 1 | 1 | [24 empty] | 4 | 10.83 | [6 empty] | 65 | 183.83
| Ipswich SM(W&G) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [54 empty] | 3 | 4 | [96 empty] | 3 | 4
Norwich TME | Lowestoft SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [8 empty] | 3.2 | 3.5 | 10 | 8 |  |  | 3 | 2.33 | 2.2 | 3.5 |  |  |  |  | 1 | 2 |  |  | 0.6 | 10 | [10 empty] | 5.8 | 10 | [8 empty] | 3.6 | 17 |  |  | 1 | 5 | 6 | 133 |  |  |  |  | 3 | 4 | [22 empty] | 8 | 10 | [10 empty] | 6 | 33 |  |  | 30 | 25 | [16 empty] | 0.6 | 6 | 10 | 18 | 32 | 103 | 4 | 46 |  |  | 1 | 3 |  |  |  |  | 1 | 1 | 10 | 7 | 14 | 28 |  |  | 4 | 0.02 | [6 empty] | 6 | 0.02 | 166 | 478.37
| Norwich SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber |  |  | 6 | 25.5 | [6 empty] | 0.4 | 1 | [28 empty] | 12 | 50 | [16 empty] | 21 | 20 |  |  | 2 | 10 | [10 empty] | 2 | 4 | [8 empty] | 1 | 2 | [32 empty] | 2 | 12 | [14 empty] | 22 | 6 | 6 | 25 |  |  | 40 | 9 | 22 | 20.5 |  |  | 41 | 28 | 5.2 | 11 | 6 | 5 | 188.6 | 229
| Norwich SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 12 | 8 | 51.4 | 25 |  |  |  |  | 49 | 12 | [6 empty] | 30 | 12.5 | 40 | 17 | [16 empty] | 0.8 | 12 |  |  | 17 | 33 | 16 | 12.01 | 1 | 9 | [18 empty] | 7 | 8.25 | [6 empty] | 10 | 6 | [12 empty] | 36.5 | 23 | 1 | 1 |  |  | 400 | 40 | [6 empty] | 20 | 18.02 |  |  |  |  | 2 | 1 | [6 empty] | 72 | 24 |  |  | 1 | 18 |  |  |  |  | 126 | 103.66 | 16 | 53.25 |  |  |  |  | 20 | 53.4 | 20 | 1 | [16 empty] | 948.7 | 491.09
Romford TME | Liverpool Street SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [8 empty] | 4 | 0.01 | [104 empty] | 2 | 1 | 29 | 11.75 | [24 empty] | 15 | 180 | [8 empty] | 50 | 192.76
| Shenfield SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 41.8 | 47 | 12 | 24.5 | [8 empty] | 4.4 | 42 | [32 empty] | 2 | 2 |  |  | 3.3 | 22 | [8 empty] | 6.6 | 1.5 | [90 empty] | 70.1 | 139
| Stratford SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [140 empty] | 0.4 | 4 | [10 empty] | 0.4 | 4
Tottenham TME | Broxbourne SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [26 empty] | 2 | 10 | [34 empty] | 10 | 6 | [16 empty] | 50 | 1 | [60 empty] | 2 | 4 | [8 empty] | 64 | 21
| Camden SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | 21 | 265 |  |  |  |  | 2 | 40 | 44 | 24 | [18 empty] | 4 | 56 | [20 empty] | 4 | 10 | [18 empty] | 2 | 1 | [8 empty] | 11 | 2 | [14 empty] | 1 | 32 | [16 empty] | 3 | 14 | [26 empty] | 3 | 24 | [8 empty] | 95 | 468
| Tottenham SM(OFFTRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [22 empty] | 0.2 | 2.5 | [128 empty] | 0.2 | 2.5
| Tottenham SM(TRACK) | MNT030 - Maintenance of Longitudinal Timber | TBR - Timber | [16 empty] | 24 | 12 | [6 empty] | 71 | 26 | [24 empty] | 30 | 15 |  |  |  |  | 8 | 12 | [18 empty] | 12 | 10 |  |  | 10 | 22 | 4 | 7 |  |  | 20 | 17.36 |  |  | 4 | 14 | [16 empty] | 15 | 5 | [14 empty] | 1 | 20 | [20 empty] | 1 | 1 |  |  |  |  | 200 | 161.36