## Alternative_Diversions_-Sabrina
FOC | Weeks | Headcode | Day of Run | Origin | Time of Run | Destination | Arrival Time | Comment | Planner Name | Status | Location BTB | Planner Comments | In Progress
FL | All | 6L68/6L80 | MSX | Tunstead | Various | Marks Tey / Bury St Edmunds | Various | Required for the first two weeks - why is there no path? Only access from one direction unless RR, would then bust terminal times. FL to speak to Commercial Team. |  | Not Started |  | Capacity is limited on the wrong road | On Hold
FL | All | 6E80/6M01/6M86 | MSX | Bow Depot / Bury St. Edmunds | Various | Barrow Hill / Tunstead | Various | Required for the second two weeks - why is there no path? Return can be diverted. FL to speak to Commercial Team. |  | Not Started |  | Capacity is limited on the wrong road | Completed
DBC | All | 6L88 | TO | Peak | 2300 | Brandon | 0627 | DB to talk to customer | Leann/Kevin | In Progress |  | KN/LE to update | Not Started
DBC | All | 6L88 | ThO | Peak | 2300 | Brandon | 0627 | DB to talk to customer | Leann/Kevin | In Progress |  | KN/LE to update
GBRf | 23/24 | 4H83 (1) | SX | March | 0.15764 | Middleton Towers | 0.22153 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Completed
GBRf | 23/24 | 6E85 (1) | SX | Middleton Towers | 0.34722 | Barnetby | 0.63194 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Completed
GBRf | 23/24 | 6E86 (1) | SX | Middleton Towers | 0.34722 | Monkton Brett | 0.68472 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) | George Barry | In Progress |  | Has a path for SLW for week 23/24 - WTT from Peterborough to Destination. Valid path from Welwyn G.C F.D to Peterborough. WIP from Origin to Welwyn G.C F.D.
GBRf | 23/24 | 4H98 (1) | MWFO | March | 0.34514 | Middleton Towers | 0.43264 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Completed
GBRf | 23/24 | 6L71 (2) | FSX | Bardon | 0.95069 | Chesterton | 0.24097 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started
GBRf | 23/24 | 6L17 (2) | FSX | Bardon | 0.975 | Harlow Mill | 0.25694 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started |  | FOC listed this as cancelled
GBRf | 23/24 | 6L71 (2) | FO | Bardon | 0.97986 | Chesterton | 0.21875 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started
GBRf | 23/24 | 6M14 (2) | MSX | Harlow Mill | 0.42847 | Bardon | 0.70764 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started |  | FOC listed this as cancelled
GBRf | 23/24 | 6H76 (3) | MO | Chesterton | 0.48264 | March | 0.60486 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started |  | Has a path for SLW for week 23/24
GBRf | 23/24 | 6H76 (3) | SO | Chesterton | 0.49306 | March | 0.51806 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started
GBRf | 23/24 | 6L37 (4) | SX | Hoo | 0.4125 | Whitemoor | 0.64792 | RR at Peterborough |  | Not Started
GBRf | 23/24 | 6L34 (4) | SX | Hoo | 0.82917 | Whitemoor | 0.0097222 | RR at Peterborough |  | Not Started
GBRf | 23/24 | 6O36 (4) | FSX | Whitemoor | 0.91806 | Hoo | 0.095833 | RR at Peterborough |  | Not Started
GBRf | 23/24 | 6O36 (4) | FO | Whitemoor | 0.91806 | Hoo | 0.095833 | RR at Peterborough |  | Not Started
GBRf | 25/26 | 4H83 (1) | SX | March | 0.15764 | Middleton Towers | 0.22153 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Completed
GBRf | 25/26 | 4H98 (1) | MWFO | March | 0.34514 | Middleton Towers | 0.43264 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Completed
GBRf | 25/26 | 6E85 (1) | SX | Middleton Towers | 0.34722 | Barnetby | 0.63194 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Completed
GBRf | 25/26 | 6E86 (1) | SX | Middleton Towers | 0.34722 | Monkton Brett | 0.68472 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started
GBRf | 25/26 | 6L17 (2) | FSX | Bardon | 0.975 | Harlow Mill | 0.25694 | Require 1 path for both destinations through SLW (currently only have 1), RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started |  | FOC listed this as cancelled
GBRf | 25/26 | 6L71 (2) | FO | Bardon | 0.97986 | Chesterton | 0.21875 | Require 1 path for both destinations through SLW (currently only have 1), RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started |  | Has a path for SLW for week 25/26
GBRf | 25/26 | 6M14 (2) | MSX | Harlow Mill | 0.42847 | Bardon | 0.70764 | Require 1 path for both destinations through SLW (currently only have 1), RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started |  | FOC listed this as cancelled
GBRf | 25/26 | 6H76 (2) | MO | Chesterton | 0.48264 | March | 0.60486 | Require 1 path for both destinations through SLW (currently only have 1), RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started |  | Has a path for SLW for week 25/26
GBRf | 25/26 | 6H76 (2) | SO | Chesterton | 0.49306 | March | 0.51806 | Require 1 path for both destinations through SLW (currently only have 1), RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started
GBRf | 25/26 | 6M86 (3) | SuO | March | 0.81042 | Peak Forest | 0.99444 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started
GBRf | 25/26 | 4M86 (3) | SX | Ely Papworth | 0.70972 | Peak Forest | 0.93264 | RR Hitchin/Welwyn (bar W10, done before, route conductor required) |  | Not Started
GBRf | 25/26 | 6L37 (4) | SX | Hoo | 0.4125 | Whitemoor | 0.64792 | RR at Peterborough |  | Not Started
GBRf | 25/26 | 6L34 (4) | SX | Hoo | 0.82917 | Whitemoor | 0.0097222 | RR at Peterborough |  | Not Started
GBRf | 25/26 | 6O36 (4) | FSX | Whitemoor | 0.91806 | Hoo | 0.095833 | RR at Peterborough |  | Not Started
GBRf | 25/26 | 6O36 (4) | FO | Whitemoor | 0.91806 | Hoo | 0.095833 | RR at Peterborough |  | Not Started
Note on L16: Eames Leann: Need loaded path too

## London_Diversions_-_Anglia_Team
FOC | Weeks | Headcode | Day of Run | Origin | Time of Run | Destination | Arrival Time | Comment | Planner Name | Status | Conflicts Noted with Other Services | Other Comments | In Progress
GBRf | 23/24 | 4Z27 | MSX | Masborough | 0.038194 | Felixstowe | 0.35417 | To divert via London |  | In Progress | Possible path found to Ipswich requires amendments to 12 GA services | Need all other info to complete validation of Branch and Ipswich Yard | On Hold
GBRf | 23/24 | 4L43 | MSX | Doncaster | 0.12292 | Felixstowe | 0.46181 | To divert via London |  | In Progress | Possible path found to Ipswich requires 2 services to be cancelled ROG's 0L53HA and GA driver Trainer 5G81HA with amendments to 3 other GA services Need all other info to complete validation of Branch and Ipswich Yard. Can only run at 75C66S12 vice 75C66S16 | Need all other info to complete validation of Branch and Ipswich Yard | Not Started
GBRf | 25/26 | 4L43 | MSX | Doncaster | 0.12292 | Felixstowe | 0.46181 | To divert via London |  | In Progress | Possible path found to Ipswich requires 2 services to be cancelled ROG's 0L53HA and GA driver Trainer 5G81HA with amendments to 3 other GA services Need all other info to complete validation of Branch and Ipswich Yard. Can only run at 75C66S12 vice 75C66S16 | Need all other info to complete validation of Branch and Ipswich Yard | Completed
GBRf | 25/26 | 4E14. | MSX | Felixstowe | 0.17014 | Doncaster | 0.43542 | To divert via London |  | Not Started
DBC | All | 6L74 | ThO | Mountsorrel | 0.18056 | Harlow Mill | 0.39583 | To divert via London |  | Not Started
GBRf | 25/26 | 4M07 | MSX | Felixstowe | 0.19167 | Birch Coppice | 0.44444 | To divert via London |  | Not Started
DBC | All | 4M79 | TO | Felixstowe | 0.33333 | EMG | 0.67986 | To divert via London |  | In Progress | Possible path found dependant on what is happening on the ECML and MML | Need all other info to complete validation of Branch and Ipswich Yard
DBC | All | 4M79 | WTHFO | Felixstowe | 0.33333 | EMG | 0.56597 | To divert via London |  | In Progress | Possible path found dependant on what is happening on the ECML and MML and needs to use path of 5E37KP on GEML, also can only run TTHF0 as 6O79 uses path WO. Both 4M79 and 6O79 are DB Cargo paths | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 23/24 | 4L28 | MO | Doncaster | 0.35972 | Felixstowe | 0.625 | To divert via London, validate Y path from Tinsley also |  | In Progress | Possible path found to Ipswich dependant on LNE Sept TT. Can only run as 75C66S12 vice 75C66S16 for path on GE (Brentwood Bank) without major changes to GA TT. Consequencial changes have Manea Bridge diversion test path 4L28 in train note | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 23/24 | 4L28 | TWTHO | Doncaster | 0.35972 | Felixstowe | 0.625 | To divert via London, validate Y path from Tinsley also |  | In Progress | Possible path found to Ipswich dependant on LNE Sept TT. Can only run as 75C66S12 vice 75C66S16 for path on GE (Brentwood Bank) without major changes to GA TT. Consequencial changes have Manea Bridge diversion test path 4L28 in train note | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 23/24 | 4L28 | FO | Doncaster | 0.35972 | Felixstowe | 0.625 | To divert via London, validate Y path from Tinsley also |  | In Progress | Possible path found to Ipswich dependant on LNE Sept TT. Can only run as 75C66S12 vice 75C66S16 for path on GE (Brentwood Bank) without major changes to GA TT. Consequencial changes have Manea Bridge diversion test path 4L28 in train note | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 25/26 | 4L28 | MO | Doncaster | 0.35972 | Felixstowe | 0.625 | To divert via London, validate Y path from Tinsley also |  | In Progress | Possible path found to Ipswich dependant on LNE Sept TT. Can only run as 75C66S12 vice 75C66S16 for path on GE (Brentwood Bank) without major changes to GA TT. Consequencial changes have Manea Bridge diversion test path 4L28 in train note | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 25/26 | 4L28 | TWTHO | Doncaster | 0.35972 | Felixstowe | 0.625 | To divert via London, validate Y path from Tinsley also |  | In Progress | Possible path found to Ipswich dependant on LNE Sept TT. Can only run as 75C66S12 vice 75C66S16 for path on GE (Brentwood Bank) without major changes to GA TT. Consequencial changes have Manea Bridge diversion test path 4L28 in train note | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 25/26 | 4L28 | FO | Doncaster | 0.35972 | Felixstowe | 0.625 | To divert via London, validate Y path from Tinsley also |  | In Progress | Possible path found to Ipswich dependant on LNE Sept TT. Can only run as 75C66S12 vice 75C66S16 for path on GE (Brentwood Bank) without major changes to GA TT. Consequencial changes have Manea Bridge diversion test path 4L28 in train note | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 23/24 | 4M29 | SX | Felixstowe | 0.43611 | Birch Coppice | 0.71458 | To divert via London |  | In Progress | Possible path found dependant on what is happening on LNW in September. Needs to use Northampton Goods loop at same time as 4M22EH. Needs dicussions with GA empty Stocks 5F96HD and 5V97HA | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 25/26 | 4M29 | SX | Felixstowe | 0.43611 | Birch Coppice | 0.71458 | To divert via London |  | In Progress | Possible path found dependant on what is happening on LNW in September. Needs to use Northampton Goods loop at same time as 4M22EH | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 25/26 | 4M29 | SX | Felixstowe | 0.43611 | Birch Coppice | 0.71458 | To divert via London |  | In Progress | Possible path found dependant on what is happening on LNW in September. Needs to use Northampton Goods loop at same time as 4M22EH | Need all other info to complete validation of Branch and Ipswich Yard
GBRf | 23/24 | 4Z81 | SX | Masborough | 0.48333 | Felixstowe | 0.80347 | To divert via London |  | In Progress
GBRf | 25/26 | 4E20. | SX | Felixstowe | 0.55625 | Masborough | 0.87222 | To divert via London |  | Not Started
GBRf | 23/24 | 4L14 | SX | Doncaster | 0.62153 | Felixstowe | 0.97569 | To divert via London |  | Not Started
FL | All | 4L53 | SX | Doncaster | 0.6875 | Felixstowe | 0.96528 | To divert via London |  | On Hold | Conflicts on LN101 and no path currently on GE
GBRf | 25/26 | 4E43. | SX | Felixstowe | 0.69653 | Doncaster | 0.97431 | To divert via London |  | Not Started
DBC | All | 4L76 | FO | EMG | 0.82708 | Felixstowe | 0.074306 | To divert via London |  | In Progress | Path valid to Ipswich | Need all other info to complete validation of Branch
DBC | All | 4L76 | FSX | EMG | 0.82847 | Felixstowe | 0.064583 | To divert via London |  | In Progress | Path valid to Ipswich | Need all other info to complete validation of Branch
GBRf | 25/26 | 4E28. | SX | Felixstowe | 0.86458 | Doncaster | 0.079167 | To divert via London, validate Y path to Tinsley also |  | Not Started
DBC | All | 4E45. | FSX | Felixstowe | 0.92083 | Wakefield | 0.20833 | To divert via London |  | On Hold | No path Crofton West Junction to Wakefield Europort. For consequential changes Train note contains Manea Bridge diversion test path 4E55 | Need all other info to complete validation of Branch
GBRf | 23/24 | 0L33 | MO | Peterborough | 05:05 | Felixstowe | 0.36389 | To divert via London |  | Not Started
FL | All | 6L49 | TO | Lindsey Oil | 0.85069 | Ipswich Yard | 0.10417 | SLW or via London? |  | Not Started
FL | All | 4L87 | MO | Leeds | 0.36806 | Felixstowe | 0.83611 | SLW or via London? |  | Not Started
FL | All | 4L87 | MSX | Leeds | 0.36875 | Felixstowe | 0.83611 | SLW or via London? |  | Not Started
FL | All | 4L40 | MSX | Doncaster | 0.125 | Felixstowe | 0.31528 | Can this go through SLW? (March 05.15) |  | Not Started | George Mackintosh examining whether the block can be eased to allow the train to pass. To also look for a route via London in the event that this is not possible (dummy path?) This headcode therefore also features on the 'Outstanding' tab.
FL | All | 4L83 | SX | Leeds | 0.11597 | Felixstowe | 0.36528 | Can this go through SLW? (March 06.27) FL to discuss early dep. |  | Not Started | George Mackintosh examining whether the block can be eased to allow the train to pass. To also look for a route via London in the event that this is not possible (dummy path?) This headcode therefore also features on the 'Outstanding' tab.
FL | All | 4L78 | FSX | Tees Dock | 0.61875 | Felixstowe | 0.063194 | Can this go through SLW? (March 22.49) |  | Not Started | George Mackintosh examining whether the block can be eased to allow the train to pass. To also look for a route via London in the event that this is not possible (dummy path?) This headcode therefore also features on the 'Outstanding' tab.
FL | All | 4L78 | FO | Tees Dock | 0.61875 | Felixstowe | 0.070139 | Can this go through SLW? (March 22.49) |  | Not Started | George Mackintosh examining whether the block can be eased to allow the train to pass. To also look for a route via London in the event that this is not possible (dummy path?) This headcode therefore also features on the 'Outstanding' tab.
FL | All | 4L10 | MTWFO | EMG | 0.77431 | Felixstowe | 0.16181 | Can this go through SLW? (March 23.37) |  | Not Started | George Mackintosh examining whether the block can be eased to allow the train to pass. To also look for a route via London in the event that this is not possible (dummy path?) This headcode therefore also features on the 'Outstanding' tab.
FL | All | 4L10 | ThO | EMG | 0.77431 | Felixstowe | 0.11389 | Can this go through SLW? (March 23.37) |  | Not Started | George Mackintosh examining whether the block can be eased to allow the train to pass. To also look for a route via London in the event that this is not possible (dummy path?) This headcode therefore also features on the 'Outstanding' tab.

## End-to-End_-_National
FOC | Weeks | Headcode | Day of Run | Origin | Time of Run | Destination | Arrival Time | Comment | Planner Name | Status | Location BTB | Other Comments | In Progress
FL | All | 4E63. | MSX | Felixstowe | 0.23472 | Doncaster | 0.45556 | End-to-end timings required. Is this WTT from Spalding? | Asher Hussain | In Progress |  | Input complete | On Hold
FL | All | 4E23. | MSX | Felixstowe | 0.24306 | Leeds | 0.60278 | End-to-end timings required. Is this WTT from Doncaster? | Asher Hussain | In Progress |  | Input complete | Completed
FL | All | 4M81 | SX | Felixstowe | 0.33403 | Crewe BH | 0.61944 | End-to-end timings required. Is this WTT from Pboro? | Asher Hussain | Completed | Uffington SB | Valid | Not Started
FL | All | 4E56. | SX | Felixstowe | 0.65694 | Doncaster | 0.87431 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
FL | All | 4E64. | SX | Felixstowe | 0.73958 | Tees Dock | 0.072917 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
FL | All | 4E59. | SX | Felixstowe | 0.77222 | Leeds | 0.082639 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
DBC | All | 6L90 | MO | Peterborough | 0.20556 | Norwich | 0.32569 | End-to-end timings required. Note - works 6M58 1559 dep - 75 mins reduced termninal time | Asher Hussain | In Progress |  | Input complete
DBC | All | 6L86 | MO | Mountsorrel | 0.20486 | Chesterton Jn | 0.36806 | End-to-end timings required. Note - works 6M87 1452 dep - 71 mins reduced termninal time | Asher Hussain | In Progress |  | Input complete
DBC | All | 6L47 | TTHO | Mountsorrel | 0.34583 | Trowse | 0.54028 | End-to-end timings required. Note - works 6M50 1942 dep - 18 mins reduced termninal time | Asher Hussain | In Progress |  | Input complete
DBC | All | 4L45 | MO | Wakefield | 0.41944 | Felixstowe | 0.68958 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
DBC | All | 4L45 | MSX | Wakefield | 0.41944 | Felixstowe | 0.68958 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
DBC | All | 6M87 | MO | Chesterton | 0.61944 | Mountsorrel | 0.73681 | End-to-end timings required - off 6L86 (offered) | Asher Hussain | In Progress |  | Input complete
DBC | All | 6M58 | MO | Norwich | 0.66597 | Peak | 0.050694 | End-to-end timings required - off 6L90 (offered) | Asher Hussain | In Progress |  | Input complete
DBC | All | 6M45 | MO | Barham | 0.73958 | Mountsorrel | 0.95278 | End-to-end timings required - off 6L47 (offered) | Asher Hussain | Completed | Peterborough | Valid
DBC | All | 6M45 | WO | Barham | 0.73958 | Mountsorrel | 0.95278 | End-to-end timings required - off 6L47 (offered) | Asher Hussain | Completed | Peterborough | Valid
DBC | All | 6L85 | TO | Arpley | 0.11667 | Middleton Towers | 0.47778 | End-to-end timings required. Note - works 6M88 1509 dep - run later MT to Kings Lynn to absorb | Asher Hussain | In Progress |  | Input complete
DBC | All | 6L85 | ThO | Arpley | 0.11667 | Middleton Towers | 0.47778 | End-to-end timings required. Note - works 6M88 1509 dep - run later MT to Kings Lynn to absorb | Asher Hussain | In Progress |  | Input complete
DBC | All | 4M87 | TO | Chesterton Jn | 1452 | Mountsorrel | 1741 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
DBC | All | 6M50 | TO | Trowse | 1942 | Mountsorrel | 2252 | End-to-end timings required - off 6L47 (offered) | Asher Hussain | Completed | Melton Mowbray down loop | Valid
DBC | All | 6M50 | ThO | Trowse | 1942 | Mountsorrel | 2252 | End-to-end timings required - off 6L47 (offered) | Asher Hussain | Completed | Melton Mowbray down loop | Valid
DBC | All | 6M88 | TO | Middleton Towers | 1509 | Ince & Elton | 0716 | End-to-end timings required - off 6L85 (offered) | Asher Hussain | In Progress |  | Input complete
DBC | All | 6M88 | ThO | Middleton Towers | 1509 | Ince & Elton | 0716 | End-to-end timings required - off 6L85 (offered) | Asher Hussain | In Progress |  | Input complete
DBC | All | 6L53 | WO | Mountsorrel | 0336 | Chesterton Jn | 0657 | End-to-end timings required. Note - works 6M70 1229 dep - 98 mins reduced termninal time | Asher Hussain | In Progress |  | Input complete
DBC | All | 6L53 | FO | Mountsorrel | 0336 | Chesterton Jn | 0657 | End-to-end timings required. Note - works 6M70 1229 dep - 98 mins reduced termninal time | Asher Hussain | In Progress |  | Input complete
DBC | All | 6M70 | WO | Chesterton Jn | 1229 | Mountsorrel | 1627 | End-to-end timings required - off 6L53 (offered) | Asher Hussain | Completed | Peterborough | Valid
DBC | All | 6M70 | FO | Chesterton Jn | 1229 | Mountsorrel | 1627 | End-to-end timings required - off 6L53 (offered) | Asher Hussain | Completed |  | Valid
DBC | All | 6M21 | ThO | Harlow Mill | 1649 | Mountsorrel | 2015 | End-to-end timings required - off 6L74 (offered) | Asher Hussain | In Progress |  | Input complete
DBC | All | 6L43 | FO | Mountsorrel | 0851 | Kennett | 1350 | End-to-end timings required - works 6M44 (offered) | Asher Hussain | On Hold |  | Not running
DBC | All | 6M44 | FO | Kennett | 1851 | Mountsorrel | 2252 | End-to-end timings required - off 6L43 (offered) | Asher Hussain | Completed | Peterborough | Valid
GBRf | 23/24 | 4L04 | SX | Hams Hall | 0.60833 | Felixstowe | 0.90764 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
GBRf | 23/24 | 4L07 | SX | Birch Coppice | 0.59306 | Felixstowe | 0.84375 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
GBRf | 23/24 | 4E20. | SX | Felixstowe | 0.55625 | Masborough | 0.87222 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
GBRf | 23/24 | 4E43. | SX | Felixstowe | 0.69653 | Doncaster | 0.97431 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
GBRf | 23/24 | 4M07 | MSX | Felixstowe | 0.19167 | Birch Coppice | 0.44444 | End-to-end timings required | Asher Hussain | In Progress |  | Input complete
GBRf | 23/24 | 4E28. | SX | Felixstowe | 0.86458 | Doncaster | 0.079167 | End-to-end timings required. Could run as 4E29 via London FSX. Validate with Y path to Tinsley, 02:51 arrival. | Asher Hussain | In Progress |  | Input complete
GBRf | 25/26 | 4L04 | SX | Hams Hall | 0.60833 | Felixstowe | 0.90764 | End-to-end timings required. Later on the Felixstowe branch. Requires confirmation that this works. | Asher Hussain | In Progress |  | Input complete
GBRf | 25/26 | 4L14 | SX | Doncaster | 0.62153 | Felixstowe | 0.97569 | End-to-end timings required. Schedule inverts at Boss Hall Jn. | Asher Hussain | On Hold |  | Not running
GBRf | 25/26 | 4Z27 | MSX | Masborough | 0.038194 | Felixstowe | 0.35417 | End-to-end timings required. Schedule inverts at Boss Hall Jn. | Asher Hussain | On Hold |  | Not running
GBRf | 25/26 | 4E21. | SX | Felixstowe | 0.47222 | Doncaster | 0.71597 | End-to-end timings required. Circa 45 mins later north of Peterborough. No path identified | Asher Hussain | Completed | Lincoln | Valid

## SO_SLW_-_Sabrina
FOC | Weeks | Headcode | Day of Run | Origin | Time of Run | Destination | Arrival Time | Comment | Planner Name | Status | SLW or London? | Location BTB | Other Comments | In Progress
FL | All | 4L83 | SO | Leeds | 0.11528 | Felixstowe | 0.50278 | To run via SLW. If not possible, run via Spalding, Peteterbo (C stop), Hertford North, NLL & GEML |  | Completed | London |  | diversion was originally requested | On Hold
FL | All | 4E63. | SO | Felixstowe | 0.21875 | Doncaster | 0.43958 | To run via SLW. If not possible, run via GEML, NLL, Hertford North, Peterbro (C Stop) & Spalding |  | Completed | London |  | diversion was originally requested | Completed
FL | All | 4E24. | SO | Felixstowe | 0.25903 | Leeds | 0.53819 | To run via SLW. If not possible, run via GEML, NLL, Hertford North, Peterbro (C Stop) & Spalding |  | Completed | London |  | diversion was originally requested | Not Started
FL | All | 4M67 | SO | Felixstowe | 0.50903 | Crewe BH | 0.7625 | To run via SLW. If not possible, run via GEML, NLL, Wembey (C stop) & WCML |  | Completed | London |  | diversion was originally requested
GBRf | 23/24 | 4L29 | SO | Birch Coppice | 0.33333 | Felixstowe | 0.65208 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 23/24 | 0E06. | SO | Felixstowe | 0.69931 | Peterborough | 0.86319 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 23/24 | 4M07 | SO | Felixstowe | 0.19097 | Birch Coppice | 0.45139 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 23/24 | 4Z27 | SO | Masborough | 0.053472 | Felixstowe | 0.36736 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 23/24 | 4E14. | SO | Felixstowe | 0.17014 | Doncaster | 0.44444 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 23/24 | 4L43 | SO | Doncaster | 0.21181 | Parkeston | 0.53889 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 23/24 | 4Z81 | SO | Masborough | 0.48333 | Felixstowe | 0.84722 | Look to route through the SLW, validate with Y path to Parkeston 19:00 arrival |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 23/24 | 4E20. | SO | Felixstowe | 0.55625 | Masborough | 0.82292 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 4L29 | SO | Birch Coppice | 0.33333 | Felixstowe | 0.65208 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 0E06. | SO | Felixstowe | 0.69931 | Peterborough | 0.86319 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 4M07 | SO | Felixstowe | 0.19097 | Birch Coppice | 0.45139 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 4Z27 | SO | Masborough | 0.053472 | Felixstowe | 0.36736 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 4E14. | SO | Felixstowe | 0.17014 | Doncaster | 0.44444 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 4L43 | SO | Doncaster | 0.21181 | Parkeston | 0.53889 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 4Z81 | SO | Masborough | 0.48333 | Felixstowe | 0.84722 | Look to route through the SLW, validate with Y path to Parkeston 19:00 arrival |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
GBRf | 25/26 | 4E20. | SO | Felixstowe | 0.55625 | Masborough | 0.82292 | Look to route through the SLW |  | Not Started |  |  | Originally asked to be diverted. Was already bid as diverted at the time
SCO | 24 | 6X04 | SO |  |  |  |  | Route back to Whitemoor |  | Not Started
SCO | 24 | 0Y09 | SO |  |  |  |  | Route back to Whitemoor AM |  | Not Started
SCO | 25 | 6T64 | SO |  |  |  |  | Out of Whitemoor |  | Not Started
SCO | 26 | 6T63 | SO |  |  |  |  | Out of Whitemoor |  | Not Started
SCO | 26 | 6T64 | SO |  |  |  |  | Out of Whitemoor |  | Not Started

## Outstanding_-_Sabrina
FOC | Weeks | Headcode | Day of Run | Origin | Time of Run | Destination | Arrival Time | Comment | Location BTB | Status | Allocated To | Planner Comments |  | In Progress
FL | All | 4L40 | MSX | Doncaster | 0.125 | Felixstowe | 0.31528 | Can this go through SLW? (March 05.15) |  | In Progress | George Mackintosh to understand if the block can be eased to allow the train to pass. Also features on the London tab so a dummy can be made in the event of this not being possible. |  |  | On Hold
FL | All | 4L83 | SX | Leeds | 0.11597 | Felixstowe | 0.36528 | Can this go through SLW? (March 06.27) FL to discuss early dep. |  | In Progress | George Mackintosh to understand if the block can be eased to allow the train to pass. Also features on the London tab so a dummy can be made in the event of this not being possible. |  |  | Completed
FL | All | 4L78 | FSX | Tees Dock | 0.61875 | Felixstowe | 0.063194 | Can this go through SLW? (March 22.49) |  | In Progress | George Mackintosh to understand if the block can be eased to allow the train to pass. Also features on the London tab so a dummy can be made in the event of this not being possible. |  |  | Not Started
FL | All | 4L78 | FO | Tees Dock | 0.61875 | Felixstowe | 0.070139 | Can this go through SLW? (March 22.49) |  | In Progress | George Mackintosh to understand if the block can be eased to allow the train to pass. Also features on the London tab so a dummy can be made in the event of this not being possible.
FL | All | 4L10 | MTWFO | EMG | 0.77431 | Felixstowe | 0.16181 | Can this go through SLW? (March 23.37) |  | In Progress | George Mackintosh to understand if the block can be eased to allow the train to pass. Also features on the London tab so a dummy can be made in the event of this not being possible.
FL | All | 4L10 | ThO | EMG | 0.77431 | Felixstowe | 0.11389 | Can this go through SLW? (March 23.37) |  | In Progress | George Mackintosh to understand if the block can be eased to allow the train to pass. Also features on the London tab so a dummy can be made in the event of this not being possible.
FL | All | 6E50. | TO | Ipswich Yard | 0.38472 | Lindsey Oil | 0.68403 | SLW or via London? |  | Completed | Sabrina Medford | FOC requested diversion
GBRf | 23/24 | IM | Various |  |  |  |  | Can 6E88 (MWFO), 6M76 (MSX) or 4M86 (SX) be swapped for an intermodal before we look to divert via London? |  | Completed | Sabrina Medford | All down trains have a path for 23/24. Not sure what to swap
GBRf | 25/26 | IM | Various |  |  |  |  | Can 6E88 (MWFO), 6L71 (FSX), 6M76 (MSX) or 6X35 (FSX) be swapped for an intermodal before we look to divert via London? |  | Completed | Sabrina Medford | 6E88-closest IM path is 6E80 6L71 is up path. All up trains have a path 6M76-closest IM path is 4M81 6X35-closest IM path is 4L10 | end to end retimes would be needed if any head codes are swapped

## DECISION_CRITERIA
Appendix A - Decision Criteria
Issue being decided upon:
Decision Criteria | Evidence | NR Opinion | Weighting | Decision
a) maintaining, developing and improving the capability of the network |  |  | Low/Medium/High/Neutral
b)that the spread of services reflects demand
c)maintaining and improving train service performance
d)that journey times are as short as reasonably possible
e)maintaining and improvng an integrated system of transport for passengers and goods
f)the commercial interests of Network Rail (apart from the terms of any maintenance contract entered into or proposed by Network Rail) or any Timetable Participant of which Network Rail is aware
g) seeking consistnecy with any ESG output.
h)that, as far as possible, International Paths included in the New Working Timetable at D-48 are not subsequently changed
i)mitigating the effect on the environment
h)enabling operators of trains to use their assets efficiently
k)avoiding changes, as far as possible, to a Strategic Train Slot other than changes which are consistent with the intended purpose of the Strategic Path to which the Strategic Train Slot relates
l)no International Freight Train Slot included in section A of an International Freight Capacity Notice shall be changed