See e-mail distribution list

Wednesday 2nd April 2008

#### ROTR Changes for WCRM Enhancements

Dear All,

Further to my letter also of the 2nd April, outlined below is confirmation of possessions that Network Rail will shortly be issuing period possession plan amendments too. These amendments will focus on the cancelling existing possession opportunities planned on diversionary routes due to the decision to take additional access on the WCML to complete infrastructure works to support the December 2008 timetable improvements.

Week 9

Midweek (M/T, T/W & W/Th): Trent Valley Jn to Stechford

Midweek (M/T, T/W & W/Th): Stechford to Aston South Jn

Midweek (M/T, T/W & W/Th):  Aston South Jn to Bescot Jn.

Week 21

Weekend: P2008/8708652 33hrs Fasts BLOCKED Watford Sth Jn and Bletchley Sth Jn - will need to reduce to Watford to Ledburn Jn (4 lines access required Bletchley),

Weekend: P2008/863603 52hrs all BLOCKED Coventry Nth Jn and Proof House Jn,

Weekend: P2008/1035393 Mill Lane Jn and Daventry 36 hrs,

Weekend: P2008/863737 – Leamington Spa and Coventry – 52hrs,

Weekend: P2008/934757 27hrs Marylebone to Neasden Jn,

Weekend: P2008/957402 52hrs Wembley and Northolt Jn,

Weekend: P2008/862492 12hrs High Wycombe and Bicester North,

Weekend: P2008/862507 12hrs Aylesbury.

continued . . .

continued . . . .

Week 22

Section 4 weekend Derby to Barton South Jn

Section 4 midweek between South Ruislip and Aynho Jn.

Section 5 midweek M/T, T/W Leamington to Bordesley Jn

Weeks 22 to 24

Week 22, 23 and 24 Section 4 Possessions Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn.

Week 22 P2008/915664 Stechford-New St 29 hrs

Week 22 P2008/1023484 Aston North-Tame Bridge 29 hrs

Week 22 P2008/862449 Bescot Jn-Bushbury Jn 29 hrs

Week 23 P2008/915667 Stechford-New St 29 hrs

Week 23 P2008/1023393 Aston North-Tame Bridge 29 hrs

Week 23 P2008/1037868 Bescot Jn-Bushbury Jn 29 hrs

Week 24 P2008/870254 At Stafford - 18hrs (11hrs all BLOCKED)

Week 24 P2008/915691 Stechford North Jn and Birmingham New Street – 52hrs

Week 24 P2008/934508 Wolves North Jn and Penkridge – 18hrs

Week 31

Section 5 Possessions W/Th Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn.

P862844 Oxford-Aynho 2300 Sat-0500 Mon

Week 37

All lines BLOCKED at Claydon (S&C) on GEML.

If you require further information or if I can help further, please give me a call.

## Matt Allen

Yours sincerely,

Matt Allen, Network Access Unit Manager.