SUBMISSION BY ENGLISH, WELSH AND SCOTTISH RAILWAY Ltd TO THE ACCESS DISPUTES COMMITTEE

DISRUPTIVE POSSESSIONS: ADRR Ref No’s:

TTP110: West Coast ‘final’ PSN dated 6th October 2006

TTP161: 2008 Rules of the Route version 6 dated 31st August 2007.

TTP168: Network Rail Decision Document dated Friday 19th October 2007.

TTP174: Proposal for a blockade of the Stoke area in Week 22 2008.

TTP210/EWS: Network Rail Decision Document dated Wednesday 2nd April 2008

1.	DETAILS OF PARTY TO THE DISPUTE

English Welsh and Scottish Railway Ltd McBeath House 310 Goswell Road Islington LONDON EC1V 7LL Contact: Nick Gibbons

2	THE PARTIES’ RIGHTS TO BRING THIS REFERENCE

2.1	 This matter is referred to a Timetabling Panel for determination in accordance

with Condition D5.1.2(a) of the Network Code.

3	CONTENTS OF REFERENCE

The Parties have together produced this joint reference and it includes:-

(a)	The subject matter of the dispute in Section 4:

(b)	A summary of the issues in dispute in Section 5:

(c)	A detailed explanation of the issues related to the dispute in Section 6

(d)	Any further issues in Section 7

- The decisions of principle sought from the panel in Section 8

(f)	Appendices and other supporting material

4	SUBJECT MATTER OF DISPUTE

4.1	This dispute is in relation to proposals for disruptive possessions made by Network Rail in a number of documents for delivery of works on the West Coast Main Line. This dispute document brings all of these outstanding disputes together: The details of these disputes are shown in date order with the relevant TTP reference as follows:

Week 9:

(a)  This dispute is in relation to a possession proposal made by Network Rail for a disruptive possession in Week 9 of 2008 of an ALB of Rugby from 0300 Sat 24th May to 0530 Tue 27th May 2008. This possession is disputed under reference TTP168. This is an extension of an agreed possession published in the West Coast PSN ‘final’ of 6th Oct 2006 paragraph 1.31 (appendix A).

(b)  This dispute is in relation to a possession proposal made by Network Rail for a disruptive possession in Week 9 of 2008 of an ALB of the ‘Trent Valley’ from 0030 Sat 24th May to 0530 Thu 29th May 2008. This possession is disputed under TTP210/EWS. This is an extension of a possession disputed under reference TTP168 (appendix C).

Weeks 18-22

This dispute is in relation to a possession proposal made by Network Rail for a disruptive blockade from Week 18 to Week 22 of 2008 for an ALB of the ‘Up Birmingham flyover’ and associated lines at Rugby from 0530 Mon 28th July to 0500 Wed 27th Aug 2008. This blockade is disputed under reference TTP161. This is similar to possession published in the West Coast PSN ‘final’ of 6th Oct 2006 paragraph 1.32/.2.42 and disputed under reference TTP110 (appendix E).

Week 22

(a) This dispute is in relation to a possession proposal made by Network Rail for a disruptive possession in Week 22 of 2008 for an ALB at Rugby from 0130 Sat 23rd Aug to 0500 Wed 27th Aug 2008. This possession disputed under TTP210/EWS. This is an extension to a possession disputed both under reference TTP168 and in the West Coast PSN ‘final’ of 6th Oct 2006 paragraph 1.33 and disputed under reference TTP110 (appendix F).

(b) This dispute is in relation to a possession proposal made by Network Rail for a disruptive blockade in Week 22 for an ALB between Stone Jn and Kidgsrove from 2330 Fri 22nd Aug to 0530 Mon 1st Sep 2008. This blockade is disputed under both references TTP174 and TTP161 (appendix G).

Weeks 22-24

This dispute is in relation to a possession proposal made by Network Rail for a disruptive blockade from Week 22 to Week 24 of 2008 for an ALB at Nuneaton from 0030 Sat 23rd Aug to 0530 Mon 8th Sep 2008. This blockade is disputed under reference TTP210/EWS. This is an extension of a possession disputed under reference TTP168 (appendix H).

Week 23

This dispute is in relation to a possession proposal made by Network Rail for a disruptive possession in Week 23 of 2008 of an ALB of the WCML between Bletchley Station North Jn and ‘Site of the former Castlethorpe Station’ from 0600 Sat 30th Aug to 0300 Mon 1st Sep 2008. This possession is disputed under reference TTP161 (appendix I).

Weeks 25 to 29

This dispute is in relation to possession proposals made by Network Rail for disruptive possessions in Weeks 25 to 29 of 2008 of ALB’s of the WCML between Crewe North Jn and Acton Grange/Ditton East Jn from 0020 Sat to 0215 Mon.

These possessions are disputed under references TTP210/EWS (weeks 25 and 26) and TTP161 (weeks 27, 28 and 29). These are reductions of possessions disputed in the West Coast PSN ‘final’ of 6th Oct 2006 paragraph 3.9 (Week 25) and 3.10 (Weeks 27 to 30) disputed under reference TTP110 (appendix J).

Week 31

This dispute is in relation to a possession proposal made by Network Rail for a disruptive possession in Week 31 of 2008 for an ALB at Nuneaton from 0030 Sat 25th Oct to 0530 Tue 28th Oct 2008. This possession is disputed under reference TTP210/EWS (appendix L).

Weeks 40-41 (2009)

This dispute is in relation to a possession proposal made by Network Rail for a disruptive possession in Week 40-41 of 2009 of an ALB of the WCML between Denbigh Hall North Jn and Hanslope Jn from 0001 Thu 1st Jan to 0300 Mon 5th Jan 2009. This possession is disputed under reference TTP210/EWS (appendix M).

Weeks 3 and 6 (2009)

This dispute is in relation to a possession proposal made by Network Rail for disruptive possessions in Weeks 3 and 6 of 2009 of an ALB of the WCML between Northampton South Jn/Kilsby and Hillmorton Jn from 0730 Sat 11th Apr to 1200 Mon 13th Apr 2009 (Week 3) and from 0730 Sat 2nd May to 1200 Mon 4th May 2009 (Week 6). This possession is disputed under reference TTP210/EWS (appendix N).

4.2	The Dispute arises from a decision of Network Rail’s which may be referred to the Timetabling Panel under Condition D2.1.6 of the Network Code.

4.3	Copied and annexed to this Reference are:

- Appendix A: Relevant part of Network Rail Decision Document dated Friday 19th October 2007 showing disputed item in week 9 and an extract from West Coast ‘final’ PSN dated 6th October 2006 detailing paragraph 1.31 showing original ‘agreed’ possession.

- Appendix B: EWS services passing Rugby between 0130 Sat and 0700 Sat (relevant to weeks 9 (6.1) and 22 (6.4)).

- Appendix C: Relevant part of Network Rail Decision Document dated Wednesday 2nd April 2008 showing disputed item in week 9 and an extract from the Network Rail Decision Document dated 19th October 2007 showing the originally disputed item.

- Appendix D: EWS services affected by proposed ALB blocks at Nuneaton (relevant to weeks 9 (6.2), 22-24 (6.6) and 31 (6.9)).

- Appendix E: Relevant part of Section 4 of Rules of the Route Version 6.3 for 2008 and also Section 7 Version 6 showing disputed item in weeks 18-22 and an extract from West Coast ‘final’ PSN dated 6th October 2006 detailing paragraph 1.32 showing the originally disputed item.

- Appendix F: Relevant part of Network Rail Decision Document dated Wednesday 2nd April 2008 showing disputed item in week 22 and also extracts from  the Network Rail Decision Document dated 19th October 2007 and the West Coast ‘final’ PSN dated 6th October 2006 detailing paragraph 1.33 showing originally disputed items.

- Appendix G: Relevant part of Section 7 of Rules of the Route Version 6 for 2008 showing disputed item in week 22.

- Appendix H: Relevant part of Network Rail Decision Document dated Wednesday 2nd April 2008 showing disputed item in weeks 22-24 and also extracts from the Network Rail Decision Document dated 19th October 2007.

- Appendix I: Relevant part of Section 7 of Rules of the Route Version 6 for 2008 showing disputed item in week 23.

- Appendix J: Relevant part from West Coast ‘final’ PSN dated 6th October 2006 detailing paragraphs 3.9 and 3.10 showing original disputed possessions in weeks 25 and 27 to 30.

- Appendix K: Relevant part of Network Rail Decision Document dated Wednesday 2nd April 2008 showing disputed item in weeks 25 and 26 and extracts of Section 7 of Rules of the Route Version 6 for 2008,  Version 6.1, Version 6.3 and LNW DPPP week 27 in relation to the disputed items in weeks 27 to 29.

- Appendix L: EWS services passing Weaver Jn between 0020 Sat and 0700 Sat (relevant to weeks 25 and 26 (6.8)).

- Appendix M:  Relevant part of Network Rail Decision Document dated Wednesday 2nd April 2008 showing disputed item in week 31.

- Appendix N: Relevant part of Network Rail Decision Document dated Wednesday 2nd April 2008 showing disputed item in weeks 40-41.

- Appendix O: Relevant part of Network Rail Decision Document dated Wednesday 2nd April 2008 showing disputed item in weeks 3 and 6.

- Appendix P: Minutes of  a meeting between Network Rail and operators at ‘Crewe Hall’ on Wednesday 12th March to discuss revised possession proposals.

5	SUMMARY OF DISPUTE

5.1	This one dispute brings together in one document a number of disputes that

relates to proposals made by Network Rail to enable the completion of work on

the West Coast Main Lines’ December 2008 timetable. Following the well

documented request for additional hours (TTP195) and the subsequent overrun of the

planned engineering work at Rugby during Christmas/New Year 2007/08 Network

Rail circulated to operators a number of scenarios for possessions that would be

required for delivery of the project. Following a meeting at ‘Crewe Hall’ on Wednesday 12th March (appendix P) Network Rail produced a final set of proposals which were put to operators in a document entitled ‘NAUM_13 WCRM changes proposal’. These proposals were published later the same day; the 12th March 2008. Network Rail’s subsequent decision document was published on the 2nd April 2008, the disputed items shown in the appendices of this document. Prior to the publication of this document EWS had a number of outstanding disputes from previous West Coast Main Line proposals, indeed some of these were subsequently revised in the decision document of the 2nd April 2008.

5.2 	The detailed nature of each dispute is shown in section 6 below.

6 	DETAILED EXPLANATION OF DISPUTES

  - Week 9: ALB at Rugby 0300 Sat 24th May to 0530 Tue 27th May 2008.

(Full possession details in appendix A)

This ‘Late Spring Bank Holiday’ possession was originally proposed in the PSN

as being from 1600 Sat to 0300 Tue. This proposal was acceptable to EWS. Subsequently this proposal was revised, in the decision document of 19th October 2007 to 0300 Sat to 0530 Tue. EWS has consistently requested Network Rail that the ALB at Rugby should start at 0700 Sat, this is to allow the passage of 2 critical trains; 6X66 2000 FO Mossend to Wembley which passes Rugby at 0428 SO and 4O33 0339 SO Trafford Park to Dollands Moor which passes Rugby at 0628 SO. Both these trains are booked for electric haulage and have Level 1 rights. A 0300 Sat start affects a number of EWS services which are shown in appendix B with their relevant access rights. Previous similar blocks have provided access on one line through Rugby BT/ET which is acceptable to EWS.

  - Week 9: Atherstone and Armitage Jn 0030 Sat 24th May to Thu 29th May 2008.

(Full possession details in appendix C)

This ‘Late Spring Bank Holiday’ possession was originally confirmed in Network Rail’s

decision document of 19th October 2007 as being from 0030 Sat to 0530 Wed. This proposal was unacceptable to EWS as Tuesday 27th May is a ‘normal’ SX timetable day for EWS traffic and we must have confidence that all daytime services that are required to run are able to be accommodated via the Coventry Corridor diversionary route noting that previous blocks of this kind (in week 52) have provided 2 ½ freight paths per hour and a maximum train length of 84 slu for trains which can run via Nuneaton and the Trent Valley up to 118 slu. Subsequently Network Rail’s decision document of 2nd April revised the possession to finish 24 hours later at 0530 Thursday. The original objections to the possession hold true as 2 ‘normal’ SX timetable days are now affected as opposed to one. Trains affected are shown in appendix D with their relevant access rights.

6.3	Weeks 18-22: Up Birmingham flyover at Rugby blockade 0530 Mon 28th July to

0500 Wed 27th Aug 2008.

(Full possession details in appendix E)

This blockade has consistently been disputed by EWS as Network Rail have agreed to provide WTT timings for the whole of its duration and at this time, those timings have not been forthcoming.

6.4	Week 22: ALB at Rugby 0130 Sat 23rd August to 0500 Wed 27th Aug 2008.

(Full possession details in appendix F)

This ‘Late Summer Bank Holiday’ possession was originally confirmed in Network

Rail’s decision document of 19th October 2007 as being from 0300 Sat to 0530 Tue.

This proposal was unacceptable to EWS as we have consistently requested a 0700 Sat start as per 6.1 above (for trains affected with their relevant access rights see appendix B). Subsequently Network Rail’s decision document of 2nd April revised the possession to start 1 ½ hours earlier at 0130 Sat and finish 23 ½ hours later at 0500 Wednesday. Tuesday 26th Aug and Wed 27th Aug are ‘normal’ SX timetable days and an ALB of Rugby gives no diversionary route for W10 traffic and pushes other diversionary traffic onto already congested routes. We wish to deliver W10 traffic to our customers on these days and to not be able to do so is unacceptable.

6.5	Week 22: Stoke blockade 2330 Fri 22nd Aug to 0530 Mon 1st Sep 2008.

(Full possession details in appendix G)

EWS serves the Imerys terminal at Cliffe Vale twice per week on Mondays and Thursdays. The timing of this train is critical to Imerys’ production at this site. This blockade allows access to Cliffe Vale from 0530 to 2330 on Friday 29th Aug 2008. EWS met with Network Rail on Monday 17th March 2008 to discuss this blockade and Network Rail confirmed that access could not be made available outside this window due to the nature of the planned work. Our customer has stated that they are able to service the site with one train only during this week but that train will need to run earlier in the week than Friday. Network Rail has asked if an additional train can be run on the Friday of the week before. However this is not possible as the wagons from the previous Thursday train will not be able to return to Cornwall to be loaded in time for an additional Friday service. Additional specialised wagons are not available.

6.6	Weeks 22-24: Nuneaton blockade 0030 Sat 23rd Aug to 0530 Mon 8th Sep 2008.

(Full possession details in appendix H)

This blockade possession was originally confirmed in Network Rail’s decision document of 19th October 2007 as being for a 9 day blockade. Subsequently Network Rail’s decision document of 2nd April revised the possession to be a 16 day blockade.

A large number of ‘normal’ SX timetable days (9) for EWS traffic are affected and as on the Tuesday and Wednesday of week 9 and we must have confidence that all daytime services that are required to run are able to be accommodated via the Coventry Corridor diversionary route noting that previous blocks of this kind (in week 52) have provided 2 ½ freight paths per hour and a maximum train length of 84 slu for trains which can run via Nuneaton and the Trent Valley up to 118 slu. Trains affected are again shown in appendix D with their relevant access rights.

  - Week 23: ALB of the WCML Bletchley to ‘site of Castlethorpe’ station 0600 Sat

30th Aug to 0300 Mon 1st Sep 2008.

(Full possession details in appendix I)

Network Rail originally proposed an ALB at Rugby in week 23 starting at 0300 Sat in Rules of the Route. As with other blocks EWS requested a 0700 Sat start to allow passage of critical trains 6X66 and 4O33 (appendix B). This possession was disputed under TTP161 and subsequently in Network Rail’s decision document of 2nd April the possession was revised to allow access through Rugby BT/ET until 1700 Sat and the possession was removed from dispute. Unfortunately this possession at Bletchley is an ALB from 0600 Sat which does not allow passage of those critical trains, EWS has requested a route through the possession until 0800 Sat.

  - Weeks 25 to 29: Crewe Nth to Preston Brook Tnl/Ditton East 0020 Sat to

0215 Mon

(Full possession details in appendices J and K)

These possessions were originally proposed in the PSN as being in weeks 25, 27, 28, 29 and 30 from 2230 Fri to 0215 Monday (appendix J). Subsequently these possessions have been altered as follows (appendix K):

- Week 25: This possession was disputed under reference TTP161, this possession was subsequently cancelled and replaced by a revised proposal confirmed in Network Rail’s decision document of 2nd April.

- Week 26: This possession is a new proposal confirmed in Network Rail’s decision document of 2nd April.

- Week 27: This possession is disputed under reference TTP161. By version 6.3 the limits of this possession had been revised to Winsford Sth Jn to Preston Brook Tunnel/Halton Jn with the proposed times of 0020 Sat until 0215 Mon remaining the same. In addition there are a number of other possessions under cover including P2008/872156, which is disputed under reference TTP161. In addition further possessions P2008/1003585 from version 6.1 of rules of the route published on 8th February 2008 and P2008/1055860 which was introduced as a new possession at the LNW DPPP meeting of 14th March 2008 are disputed. Both these possessions (P2008/1003585 and P2008/1055860) were declined by EWS at that DPPP meeting as they were ‘under cover’ of the disputed ‘main’ possession. All these possessions are detailed in appendix J.

- Week 28: This possession was disputed under reference TTP161. In version 6.1 the limits of this possession had been revised to Hartford Jn to Acton Grange /Halton Jn with times on NW1001 remaining the same but the times between Weaver Jn and Halton Jn extended to 0500 Mon. The possession in its final form is shown in appendix J as taken from version 6.3.

- Week 29: This possession was disputed under reference TTP161. In version 6.1 the limits of this possession had been revised to Crewe Nth Jn to Acton Grange/Runcorn with times extended to 0445 Mon between Crewe Nth and Weaver Jn and until 0500 Mon between Weaver Jn and Runcorn. The possession in its final form is shown in appendix J as taken from version 6.3.

In the past EWS has requested possessions of this kind to have times of 0700 Sat to 0215 Mon with elements of SLW at the outset on the Saturday , this is to allow critical EWS gauge, EXLO and other traffic to pass before the main body of the block. The diversionary route via Manchester is not ‘fit for purpose’ for electric services, gauge or EXLO traffic. A list of affected trains is shown in appendix L. This arrangement is acceptable to EWS in these weeks.

6.9	Week 31: ALB at Nuneaton 0030 Sat 25th Oct to 0530 Tue 28th Oct 2008.

(Full possession details in appendix M)

This possession was a new proposal confirmed in Network Rail’s decision document of 2nd April and is unacceptable to EWS in that Week 31 is not a Bank Holiday and Mon 27th Oct is a ‘normal’ SX timetable days for EWS traffic. As with the possession in week 9 and the blockade in weeks 22-24 EWS must have confidence that all daytime services that are required to run are able to be accommodated via the Coventry Corridor diversionary route noting that previous blocks of this kind (in week 52) have provided 2 ½ freight paths per hour and a maximum train length of 84 slu for trains which can run via Nuneaton and the Trent Valley up to 118 slu. Trains affected are again shown in appendix D with their relevant access rights.

6.10	Weeks 40-41: ALB of the WCML Denbigh Hall Jn to Hanslope Jn 0001 Thu 1st

Jan to 0300 Mon 5th Jan 2009.

(Full possession details in appendix N)

This possession is a new proposal confirmed in Network Rail’s decision document of 2nd April. An ALB of the WCML is not acceptable to EWS at these times. Network Rail has proposed an ALB of Milton Keynes at Christmas 2008 from 2300 Wed 24/12 to 0300 Mon 29/12. EWS will seek to resume services to customers ASAP after this blockade and then for this to be followed by another blockade just 2 days later is not acceptable. Friday 2nd Jan 2009 is a ‘normal’ SX timetable day and an ALB of the WCML gives no diversionary route for W10 traffic and pushes other diversionary traffic onto already congested routes. We wish to deliver W10 traffic to our customers on this day and to not be able to do so is unacceptable.  It should also be noted that despite constant reassurances and promises EWS still has no visibility of a freight timetable post-December 2008 and as such cannot agree any possessions until that timetable is forthcoming.

6.11	Weeks 3 and 6: ALB of the WCML Northampton Sth/Kilsby to Hillmorton Jn

0730 Sat to 1200 Mon (both weekends).

(Full possession details in appendix O)

These possessions are new proposals confirmed in Network Rail’s decision document of 2nd April. Although EWS has accepted ALB with these times in the past it should be noted that despite constant reassurances and promises EWS still has no visibility of a freight timetable post-December 2008 and as such cannot agree any possessions until that timetable is forthcoming.

7	FURTHER ISSUES

xxxxxxxxxxxxxxxxxxxxxxxxxx

8	DECISION SOUGHT FROM THE PANEL

- EWS seeks the panel to determine that, by proposing a series of extremely intrusive possessions to block this major passenger and freight artery, Network Rail is imposing restrictions to the network that reduce EWS’s ability to serve its’ customers to an unacceptable level. The proposed capacity, length and diversionary restrictions effectively results in services, with Firm Contractual Rights, being unable to run or severely amended such that EWS will not be able to effectively serve its’ customers needs or requirements.

- EWS seeks that Network Rail be directed to repackage the works to be less intrusive than currently proposed.

xxxxxxxxxxxxxxxxxxxxxxxxxxx

9 	signature

For and on behalf of

ENGLISH, WELSH & SCOTTISH RAILWAY LIMITED

Signed

__________________________________________

Print name NICK GIBBONS

Position: NATIONAL PLANNING MANAGER

Date: 23RD APRIL 2008

APPENDICES:

APPENDIX A:

Network Rail Decision Document dated Friday 19th October 2007 (part)

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/835328

Week 9 Saturday 24th to Tuesday 27th May 2008

At/Between: Blisworth and Shilton

Lines: All BLOCKED

and

At/Between: Daventry South Jn and Hillmorton Jn

Lines: Down and Up Northampton BLOCKED

and

At/Between: Rugby Trent Valley Jn and Coventry South Jn

Lines: Down and Up Coventry BLOCKED

Times: 0300 Sat to 0530 Tue

Work: Signalling Commissioning (Rugby, Long Lawford, Newbold and Brinklow SSI transfer to Rugby SCC)

Traffic Remarks: 0300 SAT TO 1600 SAT TRAINS TO START/TERMINATE FROM THE SOUTH AT NORTHAMPTON. 1600 SAT TO 2300 SAT TRAINS TO START/TERMINATE FROM THE SOUTH AT BLETCHLEY. 2300 SAT TO 0530 TUE TRAINS TO SHUTTLE BETWEEN EUSTON AND WATFORD VIA DC LINES ONLY. 0300 SAT TO 0530 TUE TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. NO ACESS NORTHAMPTON STATION, NORTHAMPTON UP SIDE YARD, KINGS HEATH TMD AND DAVENTRY IRFT. 0300 SAT TO 0530 TUE TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

## Extract from West Coast ‘final’ PSN dated 6th October 2006.

## 1.31 Hillmorton/Daventry South to Shilton/Brandon  – 59hr All lines block at

## Spring Bank Holiday 2008

1600 Saturday 24th to 0300 Tuesday 27th May 2008 (Week 9)

All lines blocked

Rugby Remodelling, station rebuilding [EE40]					PG

APPENDIX B:

EWS services at Rugby 0130 to 0300 Saturdays (week 22)

02:05 6A74 BESCOT DS 01:09 		WEMBLEYYD 05:08 WTT SO 	Level 1 Rights

(see below)

02:37 6V58 PK FOREST 21:54 		ACTONYARD 05:11 WTT FO	Level 1 Rights

EWS services at Rugby 0300 to 0700 Saturdays (week 9 and 22)

Access Rights

03:14 6A74 BESCOT DS 02:18 		WEMBLEYYD 05:08 WTT SO	Level 1 Rights

(for earlier service)

03:47 6X41 DAGENHMDK 00:32 	WASHWDUPS 05:31 WTT SO 	Level 1 Rights

04:28 6X66 MOSSEND   18:20 		WEMBLEYYD 06:25 WTT FO    	Level 1 Rights

04:40 4A27 TRAFFDPRK 02:05 	WEMBLEYYD 06:09 WTT SO   	Level 1 Rights

04:58 6B10 PK FOREST 23:36 		BLETCHYFD 06:19 WTT FO     	Level 1 Rights

05:03 4M38 MOSSUPREC 23:02 	DAVTRYREC 05:17 WTT FO    	Level 1 Rights

05:57 6A15 BESCOT ES 05:10 		FORDERS   10:11 WTT SO  	NDS service

06:13 6B30 MNTSOREL  03:29 		NTHPTN FD 06:48 WTT SO	Level 1 Rights

06:28 4O33 TRAFFDPRK 03:39 	DOLLANDSM 11:12 WTT SO    	Level 1 Rights

06:48 4M76 TILBRYTCS 03:00 		HAMSHALRC 08:24 WTT SO	Level 1 Rights

06:53 6G56 WEMBLEYYD 03:48 	BESCOT DS 08:17 WTT SO      	Level 1 Rights

APPENDIX C:

Network Rail Decision Document dated Wednesday  2nd April 2008 (part)

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/ 835272

Week 9 Saturday 24th to Thursday 29th May 2008

At/Between: Atherstone and Armitage Jn

Lines: All BLOCKED

Times: 0030 Sat to 0530 Thu

Work: Track & OLE in Preparation for signalling commissioning

Traffic Remarks: TRAINS TO BE DIVERTED VIA THE WEST MIDLANDS. ACCESS RUGELEY POWER STATION FROM THE HEDNESFORD DIRECTION ONLY.

Network Rail Decision Document dated Friday 19th October 2007 (part)

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/834696

Week 9 Saturday 24th to Wednesday 28th May 2008

At/Between: Shilton and Polesworth

Lines: All BLOCKED

and

At/Between: Hawksbury Lane SB and Nuneaton South Jn

Lines: Down and Up BLOCKED

Times: 0030 Sat to 0530 Wed

and

At/Between: Croft Sidings and Abbey Jn

Lines: Down and Up Hinckley BLOCKED

and

At/Between: Nuneaton North Jn and Daw Mill

Lines: All BLOCKED

Times: 0030 Sat to 0530 Tue

Work: Nuneaton S&C Renewals

Traffic Remarks: TRAINS TO BE DIVERTED VIA WEST MIDLANDS OR TRENT, BURTON ON TRENT AND TAMWORTH. NO ACESS NUNEATON STATION. ACCESS DAW MILL COLLIERY FROM THE WHITACRE JN DIRECTION ONLY. ACCESS AVAILABLE BEDWORTH CALOR GAS SIDING FROM THE COVENTRY DIRECTION ONLY. BIRMINGHAM TO PETERBOROUGH SERVICES TO START/TERMINATE AT LEICESTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN BIRMINGHAM AND LEICESTER AND COVENTRY AND NUNEATON.

APPENDIX D:

EWS services affected between the ‘peak passenger usage’ hours of 0700-2000 by the proposed possession extension.

(a) Trains booked to run between Rugby Trent Valley Jn and Stechford – times are passing Birmingham Int.

06:54   07:06 6G56 WEMBLEYYD 03:48 BESCOT DS 07:44  WTT MSX 	Level 1 rights

PASS  09:48 6B61 BESCOT DS 09:15 DAVTRYREC 10:33   WTT SX     Rights applied for

PASS  12:10 6G62 DAVTRYREC 11:26 	BESCOT DS 12:42   WTT SX    	Rights applied for

PASS  12:44 6A15 BESCOT ES 12:16 	FORDERS   16:39    WTT MSX 	NDS service

PASS  15:44 6X42 BESCOT DS 15:14 	WEMBLEYYD 18:54 WTT MSX Level 1 rights

PASS  20:39 6G15 FORDERS   16:55 	BESCOT ES 21:22   WTT MSX 	NDS service

(b) Trains booked to run via the Trent Valley that will require to be diverted – times are passing Tamworth Low Level.

PASS  06:51 6F94 WEMBLEYYD 04:41 WARRTNARP 09:11 WTT WSX Level 1 Rights

PASS  07:13 4L27 TRAFFDPRK 04:23 	FELXDKEWS 18:16  WTT MSX 	 Level 1 Rights

PASS  12:17 6H55 BLETCHYFD 10:03 	PK FOREST 16:25   WTT MSX  Level 1 Rights

PASS  14:01 4H24 WEMBLEYYD 11:31	TRAFFDPRK 16:14  WTT SX    	Level 1 Rights

PASS  14:10 4A10 TRAFFDPRK 12:02 	WEMBLEYYD 16:25 WTT SX    	Level 1 Rights

PASS  15:44 4M66 SOTNWTDKS 11:15	FOUNDRY L 17:49   WTT SX    	No access Rights

PASS  16:02 6H50 WILSDN ET 13:10 	TUNSTEAD  19:27   WTT TO    	Level 1 Rights

PASS  18:24 6L48 GARSTONYD 16:24 	DAGENHMDK 23:06 WTT SX    Level 1 Rights*

PASS  19:52 4S46 DAVTRYREC 19:15 	MOSSUPREC 01:28 WTT SX    	Level 1 Rights

PASS  20:17 6X77 WEMBLEYYD 17:31	MOSSUPREC 04:58WTT MTTHO Level 1 Rights

PASS  08:45 4M14 DOLLANDSM 02:56	TRAFFDPRK 11:13 WTT MSX   Level 1 Rights

PASS  09:48 4M18 DOLLANDSM 03:17	TRAFFDPRK 12:45 VAR TTHO 	Level 1 Rights

PASS  16:10 4O67 TRAFFDPRK 14:02 	DOLLANDSM 21:46 WTT SX     Level 1 Rights

PASS  18:05 4M32 DOLLANDSM 12:35	TRAFFDPRK 20:32 WTT TFO   	No access Rights**

PASS  20:40 4O23 TRAFFDPRK 18:03 	DOLLANDSM 03:59 WTT FSX   Level 1 Rights

* access rights are a 2224 departure

** new service

APPENDIX E:

Extract from 2008 Rules of the Route version 6.3 section 4 showing ‘Up Birmingham flyover’ blockade.

Extract from 2008 Rules of the Route version 6 section 7.

## Extract from West Coast ‘final’ PSN dated 6th October 2006.

## 1.32 High Oaks/Long Lawford to Rugby South Jn  – 1 month block

## between weeks 18 and 21, Stage F.

2300 Friday 25th July to 0300 Saturday 23rd August 2008

Up Trent Valley Slow and Up Birmingham Blocked (CONTINUOUSLY)

ALSO former platform 2.

Work on Birmingham Flyover, Rugby Remodelling [EE40]			PG

APPENDIX F:

Network Rail Decision Document dated Wednesday  2nd April 2008 (part)

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/836253

Week 22 Saturday 23rd to Wednesday 27th August 2008

At/Between: Hillmorton Jn and Shilton

Lines: All BLOCKED

and

At/Between: Rugby Trent Valley Jn and Coventry South Jn

Lines: Down and Up Coventry BLOCKED

Times: 0130 Sat to 0500 Wed

Work: Preparation for signalling commissioning

Traffic Remarks: 0130 SAT TO 1000 SAT TRAINS FROM THE SOUTH TO START/TERMINATE AT NORTHAMPTON, BETWEEN 1000 SAT TO 0100 SUN AT BLETCHLEY, 0830 SUN TO 1200 SUN AT WATFORD JN, FROM 1200 SUN TO 0300 TUE AT HEMEL HEMPSTEAD, FROM 0300 TUE TO 0500 WED AT NORTHAMPTON. 0300 SAT TO 0500 WED TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. 0300 SAT TO 1000 SAT AND 0300 TUE TO 0500 WED ACCESS NORTHAMPTON STATION, NORTHAMPTON UP YARD, KINGS HEATH TMD, DAVENTRY IRFT FROM THE SOUTH ONLY. 0300 SAT TO 0300 TUE NO ACCESS NORTHAMPTON STATION, NORTHAMPTON UP SIDE YARD, KINGS HEATH TMD AND DAVENTRY IRFT. 0300 SAT TO 0500 WED TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

Network Rail Decision Document dated Friday 19th October 2007 (part)

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/836253

Week 22 Saturday 23rd to Tuesday 26th August 2008

At/Between: Kilsby North and Rugby Trent Valley Jn (inc)

Lines: All BLOCKED

and

At/Between: Daventry South Jn and Hillmorton Jn

Lines: Down and Up Northampton BLOCKED

and

At/Between: Rugby Trent Valley Jn and Coventry South Jn

Lines: Down and Up Coventry BLOCKED

Times: 0300 Sat to 0530 Tue

Work: Signalling Commissioning (Nuneaton Interlockings – North, South, East, West and Atherstone).

Traffic Remarks: 0300 SAT TO 1000 SAT TRAINS FROM THE SOUTH TO START/TERMINATE AT NORTHAMPTON, BETWEEN 1000 SAT TO 0100 SUN AT BLETCHLEY, 0830 SUN TO 1200 SUN AT WATFORD JN, FROM 1200 SUN TO 0300 TUE AT HEMEL HEMPSTEAD. 0300 SAT TO 0600 TUE TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. 0300 SAT TO 1000 SAT AND 0300 TUE TO 0600 TUE ACCESS NORTHAMPTON STATION, NORTHAMPTON UP YARD, KINGS HEATH TMD, DAVENTRY IRFT FROM THE SOUTH ONLY. 0300 SAT TO 0300 TUE NO ACCESS NORTHAMPTON STATION, NORTHAMPTON UP SIDE YARD, KINGS HEATH TMD AND DAVENTRY IRFT. 0300 SAT TO 0530 TUE TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

## Extract from West Coast ‘final’ PSN dated 6th October 2006.

## 1.33 Hanslope Jn/Daventry South to Coventry South/Nuneaton South  – 74hr

## All lines block at August Bank Holiday weekend 2008, week 22, Stage G.

0300 Saturday 23rd to 0600 Tuesday 26th August 2008

All lines blocked

Rugby Remodelling, Signalling Commissioning [EE40]			PG

APPENDIX G:

Extract from 2008 Rules of the Route version 6 section 7 showing Stoke blockade.

APPENDIX H:

Network Rail Decision Document dated Wednesday  2nd April 2008 (part)

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/1006111

Week 22 to 24 Saturday 23rd August to Monday 8th September 2008

At/Between: Shilton and Colwich Jn

Lines: All BLOCKED

and

At/Between: Hawksbury Lane SB and Nuneaton South Jn

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Mon 8/9

and

At/Between: Croft Sidings and Abbey Jn

Lines: Down and Up Hinckley BLOCKED

and

At/Between: Nuneaton North Jn and Daw Mill

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Tue 26/8

Work: Signalling Commissioning (Nuneaton Interlockings – North, South, East, West and Atherstone).

Traffic Remarks: 0030 SAT 23/8 TO 0530 MON 8/9

TRAINS TO BE DIVERTED VIA WEST MIDLANDS. RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN COVENTRY AND NUNEATON. ACCESS AVAILABLE BEDWORTH CALOR GAS SIDING FROM THE COVENTRY DIRECTION ONLY.

0030 SAT 23/8 TO 0530 TUE 26/8

TRAINS TO BE DIVERTED VIA TRENT, BURTON ON TRENT AND TAMWORTH. NO ACESS NUNEATON STATION. ACCESS DAW MILL COLLIERY FROM THE WHITACRE JN DIRECTION ONLY. BIRMINGHAM TO PETERBOROUGH SERVICES TO START/TERMINATE AT LEICESTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN BIRMINGHAM AND LEICESTER AND COVENTRY AND NUNEATON.

0530 TUE 26/8 TO 0530 MON 8/9

AT NUNEATON ACCESS AVAILABLE BETWEEN ARLEY AND HINCKLEY VIA PLATFORMS 6 & 7.

Network Rail Decision Document dated Friday 19th October 2007 (part)

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 22/23 Saturday 23rd August to Monday 1st September 2008

At/Between: Rugby Trent Valley Jn and Polesworth

Lines: All BLOCKED

and

At/Between: Hawksbury Lane SB and Nuneaton South Jn

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Mon 1/9

and

At/Between: Croft Sidings and Abbey Jn

Lines: Down and Up Hinckley BLOCKED

and

At/Between: Nuneaton North Jn and Daw Mill

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Tue 26/8

Work: Signalling Commissioning (Nuneaton Interlockings – North, South, East, West and Atherstone).

Traffic Remarks: 0030 SAT 23/8 TO 0530 MON 1/9

TRAINS TO BE DIVERTED VIA WEST MIDLANDS. RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN COVENTRY AND NUNEATON. ACCESS AVAILABLE BEDWORTH CALOR GAS SIDING FROM THE COVENTRY DIRECTION ONLY.

0030 SAT 23/8 TO 0530 TUE 26/8

TRAINS TO BE DIVERTED VIA TRENT, BURTON ON TRENT AND TAMWORTH. NO ACESS NUNEATON STATION. ACCESS DAW MILL COLLIERY FROM THE WHITACRE JN DIRECTION ONLY. BIRMINGHAM TO PETERBOROUGH SERVICES TO START/TERMINATE AT LEICESTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN BIRMINGHAM AND LEICESTER AND COVENTRY AND NUNEATON.

0530 TUE 26/8 TO 0520 MON 1/9

AT NUNEATON ACCESS AVAILABLE BETWEEN ARLEY AND HINCKLEY VIA PLATFORMS 6 & 7.

APPENDIX I:

Extract from 2008 Rules of the Route version 6 section 7 showing ALB at Bletchley week 23.

## Appendix J:

## Extract from West Coast ‘final’ PSN dated 6th October 2006.

## 3.9 Crewe N Jn to Weaver Jn – 52hrs All line block in week 25.

2230 Friday 12th to 02:15 Monday 15th September 2008

Line of Route enhancements Remodelling and Resignalling			PG

## 3.10 Crewe N Jn to Weaver Jn – 52hrs All line block in weeks 27 – 30.

2230 Fridays 26th September, 3rd, 10th, and 17th October to 0215 Mondays 29th September, 6th, 13th and 20th October 2008.

Line of Route enhancements Remodelling and Resignalling			PG

APPENDIX K:

Week 25

Network Rail Decision Document dated Wednesday  2nd April 2008 (part)

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 25 Saturday 13th to Monday 15th September 2008

At/Between: Crewe North Jn and Preston Brook Tunnel

Lines: All BLOCKED

and

At/Between: Weaver Jn and Ditton East Jn

Lines: All BLOCKED

Times: 0020 Sat to 0215 Mon

Traffic Remarks: 0020 SAT TO 1200 SAT TRAINS TO BE DIVERTED VIA WILMSLOW, STOCKPORT, MANCHESTER AND CHAT MOSS. 1200 SAT TO 0215 MON TRAINS TIMETABLED VIA MANCHESTER. FRI/SAT SLEEPERS TO DIVERT VIA ECML.

Extract from 2008 Rules of the Route version 6 showing original cancelled possession.

Week 26

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 26 Saturday 20th to Monday 22nd September 2008

At/Between: Crewe North Jn and Preston Brook Tunnel

Lines: All BLOCKED

and

At/Between: Weaver Jn and Ditton East Jn

Lines: All BLOCKED

Times: 0020 Sat to 0215 Mon

Traffic Remarks: 0020 SAT TO 1200 SAT TRAINS TO BE DIVERTED VIA WILMSLOW, STOCKPORT, MANCHESTER AND CHAT MOSS. 1200 SAT TO 0215 MON TRAINS TIMETABLED VIA MANCHESTER. FRI/SAT SLEEPERS TO DIVERT VIA ECML.

Extract from 2008 Rules of the Route version 6.

Week 27

Extract from 2008 Rules of the Route version 6.3 showing Week 27 possession in its final form.

Extract from 2008 Rules of the Route version 6 showing Week 27 possession.

Extract from 2008 Rules of the Route version 6.1 showing disputed ‘under cover possession’ Winwick Jn to Springs Branch Jn (PPS Ref: P2008/872156)

Extract from 2008 Rules of the Route version 6.1 showing disputed ‘under cover possession’ Preston Brook Tnl to Winwick Jn (PPS Ref: P2008/1003585)

Extract from 2008 Week 27 DPPP showing disputed ‘under cover possession’ Crewe Nth to Winsford Sth Jn (PPS Ref: P2008/1055860)

Week 28

Extract from 2008 Rules of the Route version 6.3 showing Week 27 possession in its final form with later finish

Extract from 2008 Rules of the Route version 6 showing Week 27 possession.

Week 29

Extract from 2008 Rules of the Route version 6.3 showing Week 27 possession in its final form with later finish

Extract from 2008 Rules of the Route version 6 showing Week 27 possession.

APPENDIX L:

EWS services at Weaver Jn 0020 to 0700 Saturdays (weeks 25 to 29)

00:31 4M67 GRANG MTH 17:40 	TRAFFDPRK 02:56 VAR FO	Level 1 Rights GAUGE

01:41 6M65 DIDCOT YD 19:12 		WARRTNARP 02:04 VAR FO	Level 1 Rights GAUGE

02:18 6X66 MOSSEND   18:20 		WEMBLEYYD 06:25 WTT FO	Level 1 Rights

EXLO

02:34 6V71 WARRTNARP 02:18 	ALEXDK JN 08:45 WTT SO	Level 1 Rights

03:08 4M38 MOSSUPREC 23:02 	DAVTRYREC 05:17 WTT FO	Level 1 Rights

GAUGE

03:31 6M18 NCMNK US  17:41 		EARLESSDG 05:55 WTT FO	Level 2 Rights

03:37 6G58 LPOOLBKTM 23:18 	IRONBRDGE 06:26 WTT FO	Level 1 Rights*

04:18 6X01 WASHWDUPS 01:42 	HALEWD    06:35 WTT SO	Level 1 Rights

EXLO

04:34 6X76 MOSSND DY 21:34 	BESCOT DS 06:31 WTT FO	Level 1 Rights

GAUGE

04:37 6C02 BASFDHALL 04:10 		CARLISLEY 09:37 WTT SO	NDS Service

05:13 6G61 LPOOLBKTM 03:35 	IRONBRDGE 07:57 WTT SO	Level 2 Rights

06:16 6X41 DAGENHMDK 00:32 	GARSTONYD 06:42 WTT SO 	No access Rights

EXLO

* for 6M13 between Warrington and Ironbridge

APPENDIX M:

Network Rail Decision Document dated Wednesday  2nd April 2008 (part)

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 31 Saturday 25th to Tuesday 28th October 2008

At/Between: Rugby Trent Valley Jn and Atherstone

Lines: All BLOCKED

and

At/Between: Hawkesbury Lane

Lines: All BLOCKED

and

At/Between: Croft to Daw Mill

Lines: All BLOCKED

Times: 0030 Sat to 0530 Tue

Work: Nuneaton stage 2 commissioning Firewall possessions

Traffic Remarks: TRAINS TO BE DIVERTED VIA THE WEST MIDLANDS. TRAINS TO BE DIVERTED VIA TRENT, BURTON ON TRENT AND TAMWORTH. NO ACESS NUNEATON STATION. ACCESS DAW MILL COLLIERY FROM THE WHITACRE JN DIRECTION ONLY. BIRMINGHAM TO PETERBOROUGH SERVICES TO START/TERMINATE AT LEICESTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN BIRMINGHAM AND LEICESTER AND COVENTRY AND NUNEATON.

APPENDIX N:

Network Rail Decision Document dated Wednesday  2nd April 2008 (part)

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 40/41 Thursday 1st to Monday 5th January 2009

At/Between: Denbigh Hall North Jn and Hanslope Jn

Lines: All BLOCKED

Times: 0001 Thu 1/1 to 0300 Mon 5/1

Work: Signalling commissioning firewall possessions

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT BLETCHLEY. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT NORTHAMPTON OR RUGBY. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

APPENDIX O:

Network Rail Decision Document dated Wednesday  2nd April 2008 (part)

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2009/xxxxxx

Week 3 Saturday 12th to Monday 14th April 2009

At/Between: Northampton South Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

and

At/Between: Kilsby and Hillmorton Jn (inc)

Lines: Down and Up Main BLOCKED

Times: 0730 Sat to 1200 Mon

Work: Signalling commissioning and re-control

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT MILTON KEYNES CENTRAL. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT RUGBY. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML. NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, NORTHAMPTON YARD, KINGS HEATH DEPOT AND DAVENTRY IRFT.

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2009/xxxxxx

Week 6 Saturday 2nd to Monday 4th May 2009

At/Between: Northampton South Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

and

At/Between: Kilsby and Hillmorton Jn (inc)

Lines: Down and Up Main BLOCKED

Times: 0730 Sat to 1200 Mon

Work: Signalling commissioning and re-control

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT MILTON KEYNES CENTRAL. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT RUGBY. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML. NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, NORTHAMPTON YARD, KINGS HEATH DEPOT AND DAVENTRY IRFT.

APPENDIX P:

Minutes of ‘Crewe Hall’ meeting Wednesday 12th March 2008.

#### LNW ROTR Changes for WCRM Enhancements (Proposal)

Dear All,

I have been approached by colleagues in the WCRM project for alterations to the possession access required to deliver WCRM enhancement. Outlined in the letter that follows are changes to the 2008 LNW ROTR.

LNW 2008 ROTR section 4 possession to be amended to read:

MD101 EUSTON TO ARMITAGE JN

101.7 Bletchley South Jn and Hanslope Jn, Weekend period ‘C’ amended to read: 2330 Fri to 0700 Sat Fasts BLOCKED and 2000 Sat to 0530 Mon Slows BLOCKED and 0020 Sun to 0935 Sun All BLOCKED Weekend electrical isolations of Bletchley DF Parcel Sidings to be lifted by 0830 Sun Weekend electrical isolations of Bletchley CS & TMD to be lifted by 0330 Mon (Network Rail Request). (proposed amendment in blue).

NOTE: 2215 Sat to 0400 Mon no slow access Bletchley station and no access Bletchley CS.

101.10 Hillmorton Jn and Trent Valley Jn, Weekend period ‘D’ amended to read 1000 Sat to 0935 Sun All BLOCKED, and weekend period ‘E’ amended to read 2210 Sat to 0945 Sun (Network Rail Request).

TS – must have West Midlands and Stafford – Crewe clear.

Freight – suggest 1600 -1600. VT must have start of service on Sunday.

JK - support for Dec 08. LMc will examine a line through for freight.

101.11 Trent Valley Jn and Nuneaton South Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (Network Rail Request).

101.12 Nuneaton South Jn and Nuneaton North Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (Network Rail Request).

101.13 Nuneaton North Jn and Tamworth Low Level, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (Network Rail Request).

101.14 Tamworth Low Level and Lichfield Trent Valley Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (Network Rail Request).

101.15 Lichfield Trent Valley Jn and Armitage Jn, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (Network Rail Request).

NOTE: Existing ROTR in period D1 are for the Trent Valley to be BLOCKED 1000 Sat to 0930 Sun.

TOC’s - What is intention with Coventry Corridor? MA will lift any Saturday blocks on the Corridor.

SN – will it be LTP or STP. JK - Will be discussed with Richard O’Brien.

GW ?what plan for West Midlands. TS – requires standard West Midlands diversions and into Paddington, via both routes.

CH - can he have Lichfield Chord until 1700 Saturday. 4M87.

Clashing Possessions:

Weeks 10, 11, 12, 13 Freightliner diversions cross country.

MD301 RUGBY TRENT VALLEY JN TO PENKRIDGE (VIA BIRMINGHAM)

301.1 Trent Valley Jn and Coventry South Jn, Weekend period ‘D’ amended to read 1000 Sat to 0500 Mon BLOCKED Electrical isolations Rugby to Coventry North to be lifted by 0450 Mon (Network Rail Request).

MD355 LICHFIELD TV JN TO LICHFIELD TRENT VALLEY

355.1 Lichfield TV Jn and Lichfield Trent Valley, Weekend period ‘D’ amended to read 1000 Sat to 0930 Sun All BLOCKED (Network Rail Request).

CH - 1700 start please. 4M87.

NW1001 ARMITAGE JN TO PRESTON FYLDE JN

1001.9 Crewe North Jn and Winsford South Jn, Weekend period ‘D’ amended to read 0001 Sun to 0910 Sun BLOCKED until Sunday 13th July 2008  and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008

1001.10 Winsford South Jn and Weaver Jn, Weekend period ‘D’ amended to read 0001 Sun to 0910 Sun BLOCKED until Sunday 13th July 2008 and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008

1001.11 Weaver Jn and Acton Grange Jn, Weekend period ‘D’ amended to read 2345 Sat to 0900 Sun BLOCKED until Sunday 13th July 2008 and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008

No freight problems. VT will examine. JQ content with times.

TS – does not want any access restrictions at Crewe.

NW2001 WEAVER JN TO LIVERPOOL LIME STREET

2001.1 Weaver Jn and Sutton Weaver GF, Weekend period ‘D’ amended to read 0001 Sun to 0945 Sun BLOCKED until Sunday 13th July 2008 and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008

2001.2 Sutton Weaver GF and Ditton East Jn, Weekend period ‘D’ amended to read 0010 Sun to 0925 Sun BLOCKED until Sunday 13th July 2008 and 2300 Sat to 1030 Sun BLOCKED from Saturday 19th July 2008

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/ 835272

Week 9 Saturday 24th to Thursday 29th May 2008

At/Between: Atherstone and Armitage Jn

Lines: All BLOCKED

Times: 0030 Sat to 0530 Thu

Work: Track & OLE in Preparation for signalling commissioning

Traffic Remarks: TRAINS TO BE DIVERTED VIA THE WEST MIDLANDS. ACCESS RUGELEY POWER STATION FROM THE HEDNESFORD DIRECTION ONLY.

Discrepancy between an additional day and additional two days. One day already in dispute!!

TS – answer is NO. NG - Freight is in dispute.

RN – W10 trials, what happened. TS - Paths for Tuesday are crap, why not similar 25th March.

KE – ?timetable capacity for midday arr/deps at Daventry.

Clashing Possessions:

Section 5 Possessions W/Th Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 12 Saturday 14th to Wednesday 18th June 2008

At/Between: Hillmorton Jn and Shilton/Brandon

Lines: All BLOCKED

Times: 0001 Sat to 0500 Tue

and

At/Between: Trent Valley Jn and Shilton

Lines: All BLOCKED

Times: 0500 Tue to 0500 Wed

Work: Stage G Signalling Commissioning Firewall

Traffic Remarks: 0001 SAT TO 0500 TUE TRAINS TO START/TERMINATE FROM THE SOUTH AT NORTHAMPTON. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML. 0500 TUE TO 0500 WED TRAINS TO BE DIVERTED VIA WEST MIDLANDS.

MH – Gardeners World weekend.

TS – already bid for this. Now re-bid required. Then what?

DS – must block bookings on 21st March if no decision.

Discussion on merits of firewall and differences between Passenger and Freight. Giving up (late) is no use to passengers.

NG – times no good for freight. 0700 start would suit all freight.

NG – must remove the clashing possessions, never to be re-instated.

Clashing Possessions:

P2008/993662 Brandon to Stechford Jn – 29hrs Sunday possession

P2008/993659 Galton Jn and Monmore Green – 29hrs Sunday possession

P2008/862843 Oxford and Ayhno Jn – 29hrs Sunday possession

P2008/860655 Grantham to Retford 1200 Sat to 1200 Sun BLOCKED

Section 4 midweek possessions be lifted between South Ruislip and Aynho Jn.

RN - ?Chester line Jn

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 15 Saturday 5th to Sunday 6th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 15 Saturday 5th to Monday 7th July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. FREIGHT TO BE RE-TIMED. NO ACCESS HARDENDALE AND HARRISON SIDINGS. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

GW concerned at overcrowding. NG – objects to possible S&C work losses.

LMc what about both routesblocked? No way because of coal.

CH – 01/04/08 Rugeley closure will be stockpiling during shutdown period.

CH/KE Ironbridge and Fiddlers would suggest 1600 start to 2359 Sun.

LMc might be able to reduce hours, but would mean more weekends.

TS – must get units to Carlisle for Monday.

NOTE:

Settle to Carlisle route BLOCKED

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 16 Saturday 12th to Sunday 13th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 16 Saturday 12th to Monday 14th July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NO ACCESS HARDENDALE AND HARRISON SIDINGS. FREIGHT TO BE RE-TIMED. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

NOTE:

Settle to Carlisle route BLOCKED

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 17 Saturday 19th to Sunday 20th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 17 Saturday 19th to Monday 21st July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NO ACCESS HARDENDALE AND HARRISON SIDINGS. FREIGHT TO BE RE-TIMED. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

NOTE:

Settle to Carlisle route BLOCKED

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 17 Sunday 20th to Monday 21st July 2008

At/Between: Crewe North Jn and Cheadle Hulme

Lines: All BLOCKED

Times: 0030 Sun to 0515 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA STOKE ON TRENT AND MACCLESFIELD OR VIA CHAT MOSS AND WCML. NORTHERN RAIL SERVICES TO DIVERT VIA STYAL AND START/TERMINATE AT WILMSLOW. RAIL REPLACEMENT ROAD SERVICES TO OPERATE.

NG – why after all the blockades.

CH – Can I have Slow lines to Sandbach and then Middlewich?

?Passenger use of goods lines. ACTION : JH to progress.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 18 Saturday 26th to Sunday 27th July 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

PPS Ref: P2008/xxxxxx

Week 18 Saturday 26th to Monday 28tht July 2008

At/Between: Carnforth North Jn and Penrith

Lines: All BLOCKED

Times: 0400 Sat to 0430 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT LANCASTER OR PENRITH, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NO ACCESS HARDENDALE AND HARRISON SIDINGS. FREIGHT TO BE RE-TIMED. SUN/MON SLEEPER TO BE DIVERTED VIA ECML

PPS Ref: P2008/xxxxxx

Week 18 Sunday 27th to Monday 28th July 2008

At/Between: Crewe North Jn and Cheadle Hulme

Lines: All BLOCKED

Times: 0030 Sun to 0515 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA STOKE ON TRENT AND MACCLESFIELD OR VIA CHAT MOSS AND WCML. NORTHERN RAIL SERVICES TO DIVERT VIA STYAL AND START/TERMINATE AT WILMSLOW. RAIL REPLACEMENT ROAD SERVICES TO OPERATE.

Clash with timing over the Potteries, Norton Bridge – Basford Hall block.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 19 Saturday 2nd to Sunday 3rd August 2008

At/Between: Preston Fylde Jn and Lancaster South Jn

Lines: All BLOCKED

Times: 2100 Sat to 1300 Sun

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO START/TERMINATE AT PRESTON OR LANCASTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/869953

Week 21 Friday 15th to Monday 18th August 2008

At/Between: Denbigh Hall North Jn and Hanslope Jn

Lines: Down and Up Slow BLOCKED

Times: 2200 Fri to 0800 Sat

and

At/Between: Denbigh Hall North Jn and Hanslope Jn

Lines: All BLOCKED

Times: 0800 Sat to 0300 Mon

Work: Install S&C

Traffic Remarks:

2200 FRI TO 0800 SAT

TRAINS TO BE TRAVEL OVER SLOW FAST LINES

2200 FRI TO 0300 MON

NO ACCESS MILTON KEYNES CENTRAL BAY PLATFORM AND WOLVERTON RAILCARE SIDINGS.

0800 SAT TO 0300 MON

TRAINS TO START/TERMINATE FROM THE SOUTH AT BLETCHLEY. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

NOTE:

Old Oak, Greenford, Sth Ruislip BLOCKED 2145 Sun to 0455 Mon

Freight counter propose that it is week 18, when Rugby is blocked and why not in week 22 when the other work is on. Signalling resources!!

TS – what about week 18 work in the North.

Clashing Possessions:

LNW: 52hr ROTR section 4 SPO Coventry Sth Jn to International Sth Jn, 27hrs International Sth to Proof House Jn, 26hrs Aston Nth Jn to Bescot Jn, 29hrs Bescot Jn to Bushbury Jn. P2008/8708652 33hrs Fasts BLOCKED Watford Sth Jn and Bletchley Sth Jn - will need to reduce to Watford to Ledburn Jn (4 lines access required Bletchley), P2008/863603 52hrs all BLOCKED Coventry Nth Jn and Proof House Jn, P2008/1023299 – Aston and Bescot Middle – 29hrs, P2008/1037050 – Darlaston Jn and Bushbury Jn – 29hrs, P2008/1023331 – Soho Road – 29hrs, P2008/863737 – Leamington Spa and Coventry – 52hrs,  P2008/934757 27hrs Marylebone to Neasden Jn, P2008/957402 52hrs Wembley and Northolt Jn, P2008/862492 12hrs High Wycombe and Bicester North, P2008/862507 12hrs Aylesbury. Acton West to Slough Relief lines BLOCKED 2145 Sat to 0455 Mon

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/836253

Week 22 Saturday 23rd to Wednesday 27th August 2008

At/Between: Hillmorton Jn and Shilton

Lines: All BLOCKED

and

At/Between: Rugby Trent Valley Jn and Coventry South Jn

Lines: Down and Up Coventry BLOCKED

Times: 0130 Sat to 0500 Wed

Work: Preparation for signalling commissioning

Traffic Remarks: 0130 SAT TO 1000 SAT TRAINS FROM THE SOUTH TO START/TERMINATE AT NORTHAMPTON, BETWEEN 1000 SAT TO 0100 SUN AT BLETCHLEY, 0830 SUN TO 1200 SUN AT WATFORD JN, FROM 1200 SUN TO 0300 TUE AT HEMEL HEMPSTEAD, FROM 0300 TUE TO 0500 WED AT NORTHAMPTON. 0300 SAT TO 0500 WED TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. 0300 SAT TO 1000 SAT AND 0300 TUE TO 0500 WED ACCESS NORTHAMPTON STATION, NORTHAMPTON UP YARD, KINGS HEATH TMD, DAVENTRY IRFT FROM THE SOUTH ONLY. 0300 SAT TO 0300 TUE NO ACCESS NORTHAMPTON STATION, NORTHAMPTON UP SIDE YARD, KINGS HEATH TMD AND DAVENTRY IRFT. 0300 SAT TO 0500 WED TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

Existing dispute around hours required. NG - Why not start at 0700.

TS - Northampton Car Park?

Chiltern cannot strengthen on Birmingham line until at least 1000 Tues.

DRS will object to 76 never mind 96hrs.

Clashing Possessions:

Section 4 midweek possessions be lifted between South Ruislip and Aynho Jn.

Section 5 midweek M/T, T/W Leamington to Bordesley Jn

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/xxxxxx

Week 22 to 24 Saturday 23rd August to Monday 8th September 2008

At/Between: Shilton and Colwich Jn

Lines: All BLOCKED

and

At/Between: Hawksbury Lane SB and Nuneaton South Jn

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Mon 8/9

and

At/Between: Croft Sidings and Abbey Jn

Lines: Down and Up Hinckley BLOCKED

and

At/Between: Nuneaton North Jn and Daw Mill

Lines: All BLOCKED

Times: 0030 Sat 23/8 to 0530 Tue 26/8

Work: Signalling Commissioning (Nuneaton Interlockings – North, South, East, West and Atherstone).

Traffic Remarks: 0030 SAT 23/8 TO 0530 MON 8/9

TRAINS TO BE DIVERTED VIA WEST MIDLANDS. RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN COVENTRY AND NUNEATON. ACCESS AVAILABLE BEDWORTH CALOR GAS SIDING FROM THE COVENTRY DIRECTION ONLY.

0030 SAT 23/8 TO 0530 TUE 26/8

TRAINS TO BE DIVERTED VIA TRENT, BURTON ON TRENT AND TAMWORTH. NO ACESS NUNEATON STATION. ACCESS DAW MILL COLLIERY FROM THE WHITACRE JN DIRECTION ONLY. BIRMINGHAM TO PETERBOROUGH SERVICES TO START/TERMINATE AT LEICESTER, RAIL REPLACEMENT ROAD SERVICE TO OPERATE BETWEEN BIRMINGHAM AND LEICESTER AND COVENTRY AND NUNEATON.

0530 TUE 26/8 TO 0530 MON 8/9

AT NUNEATON ACCESS AVAILABLE BETWEEN ARLEY AND HINCKLEY VIA PLATFORMS 6 & 7.

TS – not acceptable to VT. Or indeed to any other party.

Clashing Possessions:

Section 4 Possessions Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn..

P2008/870254 At Stafford - 18hrs (11hrs all BLOCKED)

P2008/915691 Stechford North Jn and Birmingham New Street – 52hrs

P2008/934508 Wolves North Jn and Penkridge – 18hrs

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/8636351

Week 23 Saturday 30th August to Monday 1st September 2008

At/Between: Hillmorton Jn and Shilton/Brandon

Lines Affected: All Blocked T3

Times: 0030 Saturday to 0500 Monday

Work: Preparation for Signalling Commissioning

Traffic remarks: Amended Train Working (Possession already agreed as 0300 Sat start).

GW – North Erewash Commissioning. Freight asking for 0700 start.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 25 Saturday 13th to Monday 15th September 2008

At/Between: Crewe North Jn and Preston Brook Tunnel

Lines: All BLOCKED

and

At/Between: Weaver Jn and Ditton East Jn

Lines: All BLOCKED

Times: 0020 Sat to 0215 Mon

Traffic Remarks: 0020 SAT TO 1200 SAT TRAINS TO BE DIVERTED VIA WILMSLOW, STOCKPORT, MANCHESTER AND CHAT MOSS. 1200 SAT TO 0215 MON TRAINS TIMETABLED VIA MANCHESTER.

Freight - NO. NG - suggests later start 0600 and later finish. Say 0600 acceptable for VT.

GW – Bradway tunnel.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 25 Sunday 14th to Monday 15th September 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION, LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

GW – Birmingham to Manchester capacity, only two lines.

KE – access Cockshute to Crewe.

TJ – is EMT service a no?

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 26 Saturday 20th to Monday 22nd September 2008

At/Between: Crewe North Jn and Preston Brook Tunnel

Lines: All BLOCKED

and

At/Between: Weaver Jn and Ditton East Jn

Lines: All BLOCKED

Times: 0020 Sat to 0215 Mon

Traffic Remarks: 0020 SAT TO 1200 SAT TRAINS TO BE DIVERTED VIA WILMSLOW, STOCKPORT, MANCHESTER AND CHAT MOSS. 1200 SAT TO 0215 MON TRAINS TIMETABLED VIA MANCHESTER.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 26 Sunday 21st to Monday 22nd September 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION,  LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 27 Sunday 28th to Monday 29th September 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION,  LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 28 Sunday 5th to Monday 6th October 2008

At/Between: Colwich Jn and Macclesfield

Lines: All BLOCKED

Times: 0005 Sun to 0530 Mon

Work: Line Speed Enhancements

Traffic Remarks: TRAINS TO BE DIVERTED VIA CREWE AND WILMSLOW. NORTHERN RAIL SERVICES TO SHUTTLE BETWEEN MACCLESFIELD AND MANCHESTER. EAST MIDLANDS TRAIN SERVICES TO START/TERMINATE AT UTTOXETER. NO ACCESS MARCROFT ENGINEERING SIDINGS, STOKE ON TRENT STATION,  LNW YARD AND LONGPORT FREIGHT DEPOT. RAIL REPLACEMENT ROAD SERVICES TO OPERATE BETWEEN STAFFORD, STOKE AND MACCLESFIELD AND UTTOXETER, STOKE AND CREWE.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 28 Saturday 4th to Tuesday 7th October 2008

At/Between: Hanslope Jn and Daventry North Jn

Lines: All BLOCKED

Times: 1000 Sat to 2305 Sat

and

At/Between: Hanslope Jn (inc) and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 2305 Sat to 0905 Sun

and

At/Between: Hanslope Jn and Hillmorton Jn (inc) (via Northampton)

Lines: All BLOCKED

Times: 0905 Sun to 1800 Sun

and

At/Between: Northampton North Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 1800 Sun to 0600 Mon

and

At/Between: Northampton North Jn and Hillmorton Jn

Lines: All BLOCKED

Times: 0600 Mon to 0500 Tue

Work: Signal commissioning and re-control

Traffic Remarks:

1000 SAT TO 2305 SAT AND 0905 SUN TO 0500 TUE

TRAINS TO BE DIVERTED VIA WEEDON. TRAINS TO START/TERMINATE AT MILTON KEYNES, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NORTHAMPTON TO BIRMINGHAM SERVICES TO OPERATE BETWEEN COVENTRY AND BIRMINGHAM ONLY, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

1000 SAT TO 1800 SUN

NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, KINGS HEATH DEPOT AND NORTHAMPTON YARD.

2305 SAT TO 0905 SUN

AMENDED TRAIN WORKING, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

2305 SAT TO 0500 TUE

NO ACCESS DAVENTRY IRFT.

1800 SUN TO 0600 TUE

ACCESS KINGS HEATH TMD AND NORTHAMPTON YARD FROM THE NORTHAMPTON DIRECTION ONLY.

VT wishes to run full service over the Old on Monday!

Freight access to Daventry, cannot agree.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 31 Saturday 25th to Tuesday 28th October 2008

At/Between: Rugby Trent Valley Jn and Atherstone, Hawkesbury Lane and Nuneaton South Jn, and Croft to Daw Mill

Lines: All BLOCKED

Times: 0030 Sat to 0530 Tue

Work: Nuneaton stage 2 commissioning Firewall possessions

Traffic Remarks: TRAINS TO BE DIVERTED VIA THE WEST MIDLANDS.

GW – not acceptable on ordinary weeks! Not enough capacity for Leicester bussing. Would be acceptable on weekends or to/from Nuneaton as a mid point. All resources on CC committed to Bradway tunnel – withdrawn later!!.

Clashing Possessions:

Section 5 Possessions W/Th Trent Valley Jn to Stechford, Stechford to Aston South Jn and Aston South Jn to Bescot Jn.

GW – Aynho possession.

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 34 Saturday 15th to Tuesday 18th November 2008

At/Between: Hanslope Jn and Daventry North Jn

Lines: All BLOCKED

Times: 1000 Sat to 2305 Sat

and

At/Between: Hanslope Jn (inc) and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 2305 Sat to 0905 Sun

and

At/Between: Hanslope Jn and Hillmorton Jn (inc) (via Northampton)

Lines: All BLOCKED

Times: 0905 Sun to 1800 Sun

and

At/Between: Northampton North Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

Times: 1800 Sun to 0600 Mon

and

At/Between: Northampton North Jn and Hillmorton Jn

Lines: All BLOCKED

Times: 0600 Mon to 0500 Tue

Work: Signal commissioning and re-control at Northampton, Firewall possession.

Traffic Remarks:

1000 SAT TO 2305 SAT AND 0905 SUN TO 0500 TUE

TRAINS TO BE DIVERTED VIA WEEDON. TRAINS TO START/TERMINATE AT MILTON KEYNES, RAIL REPLACEMENT ROAD SERVICE TO OPERATE. NORTHAMPTON TO BIRMINGHAM SERVICES TO OPERATE BETWEEN COVENTRY AND BIRMINGHAM ONLY, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

1000 SAT TO 1800 SUN

NO ACCESS NORTHAMPTON STATION, NORTHAMPTON RIVERSIDE SIDINGS, KINGS HEATH DEPOT AND NORTHAMPTON YARD.

2305 SAT TO 0905 SUN

AMENDED TRAIN WORKING, RAIL REPLACEMENT ROAD SERVICE TO OPERATE.

2305 SAT TO 0500 TUE

NO ACCESS DAVENTRY IRFT.

1800 SUN TO 0600 TUE

ACCESS KINGS HEATH TMD AND NORTHAMPTON YARD FROM THE NORTHAMPTON DIRECTION ONLY.

Existing LNW 2008 ROTR section 7 possession to be amended to read:

PPS Ref: P2008/1007054 and 1007055

Week 35/36 Friday 21st November to Monday 1st December 2008

At/Between: Kilsby North and Shilton

Lines: All BLOCKED

Was originally one possession right through. Disruption removed in the week. Both lines available each way in the week. 35 - 2315 Fri to 0015 Sat and 0700 Sat - 0530 Mon (with one line working 0015 – 0700 Sat) then 36 - 0700 Sat to 0530 Mon.

KE – What about Sunday night access.

RN – GEML??

LNW 2008 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 37 Saturday 6th to Sunday 7th December 2008

At/Between: Hillmorton Jn and Shilton

Lines: All BLOCKED

and

At/Between: Trent Valley Jn and Brandon

Lines: Down and Up Coventry BLOCKED

Times: 1030 Sat to 2100 Sun

Work: Contingency for stage J signal commissioning

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT NORTHAMPTON. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. RAIL REPLACEMENT ROAD SERVICE TO OPERATE. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

GBRF want 1800 Sat to 1400 Sun.

Clashing Possessions:

All lines BLOCKED at Claydon (S&C) on GEML does not permit XC diversion of liners.

GW – Chester line Jn clash.

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 39/40 Wednesday 24th to Monday 29th December 2008

At/Between: Hillmorton Jn and Shilton

Lines: All BLOCKED

and

At/Between: Trent Valley Jn and Brandon

Lines: Down and Up Coventry BLOCKED

Times: 2300 Wed 24/12 to 0300 Mon 29/12

Work: Signalling Stage J Commissioning Firewall

Traffic Remarks:

2300 WED 24/12 TO 0600 SAT 27/12

CHRISTMAS NO TRAIN PERIOD

0600 SAT 27/12 TO 0300 MON 29/12

TRAINS TO START/TERMINATE FROM THE SOUTH AT NORTHAMPTON. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT COVENTRY OR BIRMINGHAM INTERNATIONAL. RAIL REPLACEMENT ROAD SERVICE TO OPERATE. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

VT – EEA time – not acceptable!!

GW – WOULD AGREE

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2008/xxxxxx

Week 40/41 Thursday 1st to Monday 5th January 2009

At/Between: Denbigh South Jn and Hanslope Jn

Lines: All BLOCKED

Times: 0001 Thu 1/1 to 0300 Mon 5/1

Work: Signalling commissioning firewall possessions

Traffic Remarks: TRAINS TO START/TERMINATE FROM THE SOUTH AT BLETCHLEY. TRAINS TO/FROM THE NORTH TO START/TERMINATE AT NORTHAMPTON OR RUGBY. TRAINS TO BE DIVERTED VIA ACTON WELLS, ACTON MAIN LINE, EALING BROADWAY, GREENFORD, SOUTH RUISLIP, CHILTERNS, BANBURY AND LEAMINGTON OR NORTH LONDON LINE, KINGS CROSS INCLINE AND ECML.

VT – EEA time – not acceptable!!

GW – would NOT agree.

Clashing Possessions:

0215 Sat to 0500 Mon DCL BLOCKED

Northallerton and Darlington 0600 Sat to 0525 Mon

Section 4 midweek possessions be lifted between South Ruislip and Ayhno Jn.

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2009/xxxxxx

Week 3 Saturday 12th to Monday 14th April 2009

At/Between: Northampton South Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

and

At/Between: Kilsby and Hillmorton Jn (inc)

Lines: Down and Up Main BLOCKED

Times: 0730 Sat to 1200 Mon

Work: Signalling commissioning and re-control

Traffic Remarks: xxxxx

LNW 2009 ROTR additional possession request for section 7:

PPS Ref: P2009/xxxxxx

Week 6 Saturday 2nd to Monday 4th May 2009

At/Between: Northampton South Jn and Hillmorton Jn (inc)

Lines: All BLOCKED

and

At/Between: Kilsby and Hillmorton Jn (inc)

Lines: Down and Up Main BLOCKED

Times: 0730 Sat to 1200 Mon

Work: Signalling commissioning and re-control

Traffic Remarks: xxxxx