Ian Kapur.
Timetabling Manager.
First GB Railfreight.

Wednesday 2nd April 2008

#### LNW ROTR Changes for WCRM Enhancements

Dear Ian,

Thank you for your response of the 27th March 2008 to Network Rail’s proposed engineering access alterations to the 2008 ROTR to deliver WCRM enhancements. With colleagues from WCRM project I have reviewed your comments, and can confirm Network Rail’s point of view or agreed alterations to the proposals.

LNW 2008 ROTR section 4 possessions to be amended:

101.10 Hillmorton Jn and Trent Valley Jn, I can confirm that in the decision letter Network Rail has amended this proposal to read:

101.10 Hillmorton Jn and Trent Valley Jn, Weekend period ‘D’ amended to read 1015 Sat to 0935 Sun All BLOCKED and weekend period ‘E’ amended to read 2210 Sat to 0945 Sun (Network Rail Request).

NOTE: Between Hillmorton Jn and Long Lawford, the Down Fast (between Hillmorton Jn and Rugby) and Down Coventry (between Rugby and Long Lawford) is available until 1700 Sat for nominated freight services only.

101.11 Trent Valley Jn and Nuneaton South Jn, I can confirm that in the decision letter Network Rail has amended this proposal to start from 1015 Sat.

101.12 Nuneaton South Jn and Nuneaton North Jn, I can confirm that in the decision letter Network Rail has amended this proposal to start from 1015 Sat.

LNW 2008 ROTR section 7 possession to be amended to read:

Atherstone and Armitage Jn

Week 9

The timetable plan for services via the West Midlands on a normal ‘SX’ day during this blockade will be as per the agreed plan implemented on Tue 25th March. This possession does not prevent access at Nuneaton to/from the Whitacre Jn direction.

continued . . .

continued . . .

Hillmorton Jn and Shilton

Week 12

I can confirm sufficient information is available from the WCRM project to enable the withdrawal of this proposed firewall possession.

Denbigh Hall North Jn and Hanslope Jn

Week 21

I can confirm that the all lines BLOCKED time has been amended to start 0930 Sat.

Hillmorton Jn and Shilton/Coventry South Jn

Week 22

Network Rail is unable to support your proposed amendment to the times of this possession.

Shilton Jn and Colwich Jn

Weeks 22 to 24

The timetable plan for services via the West Midlands on a normal ‘SX’ day during this blockade will be as per the agreed plan implemented on Tue 25th March.

Hillmorton Jn and Shilton/Coventry South Jn

Week 23

I can confirm that this possession has been amended and that a route is now available until 1700 Sat for diesel traction only between Hillmorton Jn and Coventry.

Hanslope Jn and Hillmorton Jn (via Northampton)

Week 28

This possession has been amended and does not now affect Monday.

Trent Valley Jn and Atherstone

Week 31

The timetable plan for services via the West Midlands on a normal ‘SX’ day during this blockade will be as per the agreed plan implemented on Tue 25th March.

Hanslope Jn and Hillmorton Jn (via Northampton)

Week 34

This possession has been amended and does not now affect Monday.

continued . . .

continued . . .

Kilsby North Jn and Shilton Jn

Week 35/36

I can confirm that entry has been amended in the decision document and now reads:

PPS Ref: P2008/1007054

Week 35 Friday 21st to Monday 24th November 2008

At/Between: Kilsby North and Shilton

Lines: All BLOCKED

and

At/Between: Daventry South Jn and Hillmorton Jn

Lines: Down and Up Northampton BLOCKED

and

At/Between: Rugby Trent Valley Jn and Coventry South Jn

Lines: Down and Up Coventry BLOCKED

Times: 2315 Fri 21/11 to 0530 Mon 24/11

Hillmorton Jn and Shilton/Coventry South Jn

Week 36

Network Rail is unable to support your proposed amendment to the times of this possession.

Hillmorton Jn and Shilton/Coventry South Jn

Week 37

Network Rail is unable to support your proposed amendment to the times of this possession.

Denbigh Hall South Jn and Hanslope Jn

Week 40/41

I am unable to support your requirement to operate services on the WCML. If GBrf required to hire additional resources to enable services to be diverted, I can confirm that this possession is compensatable via the normal part ‘G’ conditions, using the normal process set up with the WCRM project.

Northampton South Jn and Hillmorton Jn (inc)

Week 3

I am unable to support your requirement to operate services on the WCML. If GBrf required to hire additional resources to enable services to be diverted, I can confirm that this possession is compensatable via the normal part ‘G’ conditions, using the normal process set up with the WCRM project.

continued . . .

continued . . .

Northampton South Jn and Hillmorton Jn (inc)

Week 6

I am unable to support your requirement to operate services on the WCML. If GBrf required to hire additional resources to enable services to be diverted, I can confirm that this possession is compensatable via the normal part ‘G’ conditions, using the normal process set up with the WCRM project.

If you require further information or if I can help further, please give me a call.

## Matt Allen

Yours sincerely,

Matt Allen, Network Access Unit Manager.