## Plan Linear
Week No | Hrs | Location | Discipline | Year | TDPU Ref | aiwp ref
37 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0605 | AA2
37 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0297 | I2
38 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0606 | AA3
38 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0511 | K3
38 | 29 | Millerhill Freddie 7 | Plain Line Worksite | 2007/08 | G0303 | I3
39 | 29 | Cowlairs East S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0309 | AC4
39 | 29 | Cowlairs West S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0307 | AC5
39 | 54 | Glasgow Central re-interlocking - All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0310 | AA4
39 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0305 | W4
39 | 20 | Monktonhall South | S&C Tamp Follow-up Tamp | 2007/08 | G0304 | U4
39 | 96 | Shields [Continues into week 40] | S&C Worksite | 2007/08 | G0308 | S4
40 | 54 | Glasgow Central re-interlocking- All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0316 | AA6
40 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0317 | W6
40 | 126 | Shields [Continued from week 39] | S&C Worksite | 2007/08 | G0315 | S6
40 | 29 | Newbridge Jn (A-B Project) | 3rd Party Schemes | 2007/08 | NEW | E6
41 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0608 | AA7
41 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0318 | W7
41 | 102 | Shields | S&C Worksite | 2007/08 | G0321 | S7
41 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0516 | M7
41 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0322 | K7
41 | 29 | Dundee Plat 1 (Up M) | Plain Line Worksite | 2007/08 | G0319 | I7
42 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0609 | AA8
42 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0327 | W8
42 | 78 | Shields | S&C Worksite | 2007/08 | G0325 | S8
42 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0517 | M8
42 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0326 | K8
42 | 29 | Dundee (Up L) | Plain Line Worksite | 2007/08 | G0328 | I8
43 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0611 | AA9
43 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0333 | W9
43 | 54 | Shields | S&C Worksite | 2007/08 | G0334 | S9
43 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | O9
43 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0610 | M9
43 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0330 | K9
43 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0331 | I9
44 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0612 | AA10
44 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0341 | W10
44 | 54 | Shields | S&C Worksite | 2007/08 | G0339 | S10
44 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | NEW | M10
44 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0338 | K10
44 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0340 | I10
45 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0345 | AA11
45 | 29 | Lagganstarroch | Structures Renewals 2 | 2007/08 | G0344 | Y11
45 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0342 | W11
45 | 51 | Slateford | S&C Worksite | 2007/08 | G0347 | S11
45 | 29 | Gorton (Rev) | Plain Line Worksite | 2007/08 | G0522 | O11
45 | 29 | Glenury (Dn) | Plain Line Worksite | 2007/08 | G0521 | M11
45 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0346 | K11
45 | 29 | Uddingston (Dn) | Plain Line Worksite | 2007/08 | G0388 | I11
46 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0352 | AA12
46 | 29 | Lagganstarroch | Structures Renewals 1 | 2007/08 | G0349 | W12
46 | 29 | Slateford | S&C Worksite | 2007/08 | G0351 | S12
46 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O12
46 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | M12
46 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | NEW | K12
46 | 29 | Dimsdale (Up) | Plain Line Worksite | 2007/08 | G0389 | I12
47 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0357 | AA13
47 | 54 | Kingskettle | Structures Renewals 1 | 2007/08 | G0355 | W13
47 | 54 | Shields Follow-up Tamp | S&C Tamp Follow-up Tamp | 2007/08 | G0358 | U13
47 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S13
47 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | M13
47 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0350 | K13
47 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0359 | I13
48 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0361 | AA14
48 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S14
48 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O14
48 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0513 | M14
48 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0354 | K14
48 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0360 | I14
49 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0366 | AA15
49 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S15
49 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0368 | M15
49 | 29 | Forthar (Up) | Plain Line Worksite | 2007/08 | G0363 | K15
49 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0367 | I15
50 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0371 | AA16
50 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S16
50 | 29 | Newton-on-Ayr (Dn) | Plain Line Worksite | 2007/08 | G0530 | M16
50 | 29 | Plean (Up) | Plain Line Worksite | 2007/08 | G0373 | K16
50 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0369 | I16
51 | 12 | Newton-on-Ayr S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0378 | AC17
51 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0372 | AA17
51 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S17
51 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | NEW | M17
51 | 43 | Auchencastle (Up) | Plain Line Worksite | 2007/08 | G0547 | K17
51 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0377 | I17
52 | 12 | Kilwinning Jn S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0381 | AC18
52 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0382 | AA18
52 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S18
52 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | G0383 | K18
52 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0380 | I18
1 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA20
1 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W20
1 | 54 | Stirling Middle | S&C Worksite | 2008/09 | new | S20
2 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA21
2 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W21
2 | 29 | Stirling Middle | S&C Worksite | 2008/09 | new | S21
3 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA22
3 | 54 | Larbert | S&C Worksite | 2008/09 | new | S22
4 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA23
4 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S23
5 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA24
5 | 78 | Falkland Yard | S&C Worksite | 2008/09 | new | S24
6 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA25
6 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S25
7 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA26
7 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S26
8 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA27
8 | 29 | Stirling Middle FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U27
9 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA28
10 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA29
11 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA30
12 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA31
12 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S31
13 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA32
13 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S32
14 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA33
14 | 78 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S33
15 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA34
15 | 54 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S34
16 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA35
16 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W35
16 | 78 | New Cumnock | S&C Worksite | 2008/09 | new | S35
16 | 168 | Ballochmyle (Up) | Plain Line Worksite | 2008/09 | new | I35
16 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G35
17 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA36
17 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W36
17 | 29 | New Cumnock | S&C Worksite | 2008/09 | new | S36
17 | 168 | Mauchline (Dn) | Plain Line Worksite | 2008/09 | new | I36
17 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G36
18 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA37
18 | 54 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W37
18 | 54 | Gartcosh | S&C Worksite | 2008/09 | new | S37
19 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA38
19 | 12 | Halbeath FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U38
19 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S38
20 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA39
20 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S39
21 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA40
21 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U40
22 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA41
22 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U41
23 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA42
23 | 12 | New Cumnock FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U42
24 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA43
24 | 51 | Monktonhall South (Up) | Plain Line Worksite | 2008/09 | new | I43
25 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA44
25 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I44
26 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA45
26 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W45
26 | 12 | Gartcosh FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U45
26 | 78 | Whifflet North | S&C Worksite | 2008/09 | new | S45
26 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I45
27 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA46
27 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W46
27 | 29 | Whifflet North | S&C Worksite | 2008/09 | new | S46
27 | 51 | Ninewar (Dn) | Plain Line Worksite | 2008/09 | new | K46
27 | 51 | Lemington (Up) | Plain Line Worksite | 2008/09 | new | I46
28 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA47
28 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W47
28 | 51 | Oxwellmains (Dn) | Plain Line Worksite | 2008/09 | new | I47
29 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA48
29 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W48
29 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S48
29 | 51 | Houndwood (Dn) | Plain Line Worksite | 2008/09 | new | I48
30 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA49
30 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W49
30 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S49
30 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I49
31 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA50
31 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W50
31 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S50
31 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I50
32 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA51
33 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA52
33 | 12 | Whifflet North FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U52
34 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA53
34 | 54 | Markinch | S&C Worksite | 2008/09 | new | S53
35 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA54
35 | 54 | Markinch | S&C Worksite | 2008/09 | new | S54
36 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA55
FY37 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA56
FY37 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S56
FY38 | 48 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA57
FY38 | 120 | Carmuirs East | S&C Worksite | 2008/09 | new | S57
FY39 | 77 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA58
FY39 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S58
FY40 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S59
FY41 | 12 | Markinch FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U60
FY41 | 54 | Cadder | S&C Worksite | 2008/09 | new | S60
FY44 | 54 | Beattock | S&C Worksite | 2008/09 | new | S63
FY44 | 43 | Ecclefechan (Dn) | Plain Line Worksite | 2008/09 | new | I63
FY45 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S64
FY45 | 43 | Fullwood (Dn) | Plain Line Worksite | 2008/09 | new | I64
FY46 | 12 | Carmuirs East FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U65
FY46 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S65
FY46 | 29 | Garriongill (Dn) | Plain Line Worksite | 2008/09 | new | I65
FY47 | 29 | Beattock Summit | S&C Worksite | 2008/09 | new | S66
FY47 | 29 | Garriongill (Up) | Plain Line Worksite | 2008/09 | new | I66
FY48 | 78 | Hilton Jn | S&C Worksite | 2008/09 | new | S67
FY48 | 29 | Rutherglen (Up Slow) | Plain Line Worksite | 2008/09 | new | I67
FY49 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W68
FY49 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S68
FY49 | 29 | Rutherglen Old Station (Up Slow) | Plain Line Worksite | 2008/09 | new | I68
FY50 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W69
FY50 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S69
FY50 | 29 | Shawfield (Up Slow) | Plain Line Worksite | 2008/09 | new | I69
FY51 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W70
FY51 | 54 | Hilton Jn - Ladybank Branch only | S&C Worksite | 2008/09 | new | S70

## Plan AIP
FISCAL YEAR | TT YEAR | Week No | Key Events/ Dates |  | Hrs | Enhancement Projects | Hrs | Enhancement Projects | Hrs | Enhancement / Estates Projects | Hrs | Enhancement Projects | Hrs | Estates | Hrs | Plain Line Worksite | Hrs | Plain Line Worksite | Hrs | Plain Line Worksite | Hrs | Plain Line Worksite | w/e Hrs | S&C Renewals | w/e Hrs | S&C Renewals | Hrs | Civils Renewals 1 | Hrs | Civils Renewals 2 | Hrs | Civils Renewals 3 | Hrs | OHL/Signalling Renewals | Hrs | S&C Tamping / OLE / Heavy Maintenance
2008/09 (2009 TTY) | PERIOD A
|  | 38 | [13 empty] | [All 28hrs Carstairs to Haymarket East times are 0650 Sat to 1050 Sun] |  | [All 43hrs Lockerbie to Carstairs times are 0530 Sat to 0020 Mon] | [16 empty] | 12 | Niddrie West/ South Jn S&C Tamp (Maint) [0001 Sun to 1201 Sun - ROTR + 2hrs]
|  | 39 |  | Christmas DayThur 25/12/08 | 48 | Edinburgh Tram (tie) - c/o Haymarket Cen Jn to Edin Park/ Saughton (All Lines) [Thur 25/12/08 & Fri 26/12/08] | 54 | A2B Project - Newbridge Jn [Thur 25/12/08 & Fri 26/12/08] | 54 | Newton Old Signal Box (Demolition) [Thur 25/12/08 & Fri 26/12/08] - Estates | 54 | GARL- Shields to Paisley [Thur 25/12/08 & Fri 26/12/08] [to be reviewed] | 54 | Paisley Gilmour St - Gourock Plats [Reroof/Reglaze] | 29 | Princes St Gdns (Line X - only Z available) [Thur 25/12/08] | 54 | Dock Street Tunnel (Up) [2300 Wed 24/12/08 to 0500 Sat 27/12/08] Ev1 |  |  |  |  | 100 (Mn) 184 (Bch) | Hilton Jn [Dunblane to Perth - Mainlines 0130 Thur 25/12/08 to 0510 Mon 29/12/08 then 0001 to 1800 Thur 1/1/09 ; Ladybank Branch 0130 Thur 25/12/08 to 1800 Thur 1/1/09] [DRS services 4A66 & 4N83 to be diverted via Stirling-Alloa & Tay Bridge] Ev2 |  |  | 54 | UB 160/001 Cook Street [Thur 25/12/08 & Fri 26/12/08] |  |  |  |  | 125 | Glasgow Central Interlocking - ALB [0001 Thur 25/12/08 to 0500 Tue 30/12/08] Ev1 | 17 | Dundee Cen Jn S&C Tamp (Maint) [Boxing Day - 0100 to 1800hr Fri 26/12/08]
|  | 40 |  | New Year's Day Thu 1/1/09 | 48 | Edinburgh Tram (tie) - c/o Haymarket Cen Jn to Edin Park/ Saughton (All Lines) [Thur 1/1/09 & Fri 2/1/09] | 54 | A2B Project - Newbridge Jn [Thur 1/1/09 & Fri 2/1/09] |  |  | 54 | GARL- Shields to Paisley [Thur 1/1/09 & Fri 2/1/09] [to be reviewed] |  |  | 9 | Law (Dn) [Lanark Jn - Law Sth Jn] [ROTR] | 54 | Jeanfield (Up) [0001 Thur 01/01/09 to 0510 Sat 3/1/09] Ev2 | [6 empty] | 78 | Dubbs Jn (Largs Branch) [0001 Thur 1/1/09 to 0600 Sun 4/1/09] [M] - Kilwinning Plat 2 not available electrically | [8 empty] | 10 | Inverkeithing Cen [2345 Sat - 0945 Sun - ROTR + 1hr 45 min] & North Jns [0945 - 1855 Sun] S&C Tamp (Maint)
|  | 41 | Medium Output Ballast Cleaner (MOBC) Allocation | [7 empty] | 54 | GARL- Shields to Paisley [to be reviewed] |  |  | 29 | Law (Dn) [Lanark Jn - Law Sth Jn] | 54 | Laurencekirk (Dn) [MOBC] |  |  |  |  | 54 | Halbeath [M]
|  | 42 | [8 empty] | 54 | GARL- Shields to Paisley [to be reviewed] |  |  | 29 | Fullwood (Dn) [Lanark Jn - Law Sth Jn] | 54 | Aberdeen (Dn Goods Lp - Clayhills) [NO access to Clayhills Depot] | 54 | Laurencekirk (Dn) [MOBC] |  |  | 54 | Halbeath [M]
|  | 43 | [8 empty] | 54 | GARL- Shields to Paisley [to be reviewed] |  |  | 29 | Fullwood (Dn) [Lanark Jn - Law Sth Jn] | 54 | Stannergate (Dn) [MOBC]
|  | 44 | [8 empty] | 54 | GARL- Shields to Paisley [to be reviewed] |  |  | 29 | Fullwood (Dn) [Lanark Jn - Law Sth Jn] | 54 | East Haven (Dn) [MOBC] | 54 | Marywell (Dn) [Drainage]
| PERIOD B | 45 |  | RBS Six Nations Rugby [dates and venues tbc] - Edinburgh to Aberdeen/ Inverness, E&G and Shotts routes to be open |  |  |  |  | 54 | Barrhead - Kilmarnock Route Enhancements | 54 | GARL- Paisley Gilmour St to Bishopton (Airport Branch Jn) [to be reviewed] |  |  | 43 | Ecclefechan (Dn) [Cove-Lockerbie] [0530 Sat to 0020 Mon] | 29 | Niddrie (Dn) | 54 | Coaltown of Balgonie (Dn) [Thornton Nth to Markinch] | [6 empty] | 54 | UB90/111 Slaughterhouse Rd, Markinch | 54 | Tay Bridge |  |  |  |  | 12 | Ladybank S&C Tamp (Maint) [0050 Sat to 1250 Sat]
|  | 46 | [6 empty] | 54 | Barrhead - Kilmarnock Route Enhancements | 54 | GARL- Paisley Gilmour St to Bishopton (Airport Branch Jn) [to be reviewed] | 54 | Paisley Gilmour St - Gourock Plats [Reroof/Reglaze] | 43 | Ecclefechan (Dn) [Cove-Lockerbie] [0530 Sat to 0020 Mon] | 29 | Niddrie (Dn) | 54 | Glenfoot (Ladybank Jn - Hilton Jn) | [6 empty] | 54 | UB90/131 Nabs Rd, Kingskettle | 54 | UB90/130 Station Rd, Kingskettle | 54 | Tay Bridge |  |  | 12 | Thornton North/ South S&C Tamp (Maint) [0035 Sat to 1235 Sat]
|  | 47 | [8 empty] | 54 | GARL- Paisley Gilmour St to Bishopton (Airport Branch Jn) [to be reviewed] |  |  | 29 | Lochwinnoch (Dn) [MOBC] | 29 | Ninewells (Dn)
|  | 48 | [8 empty] | 54 | GARL- Paisley Gilmour St to Bishopton (Airport Branch Jn) [to be reviewed] |  |  | 51 | Dolphinston (Rev/Fast) [Carstairs So. Jn/ Carstairs Station to Carstairs E. Jn] [no access towards Midcalder Jn and only Carstairs Plat 1 available] | 29 | Lochwinnoch (Dn) [MOBC] | 29 | Ninewells (Dn) |  |  | 51 | Curriehill (Hmkt East-Midcalder Jn) [removal of crossover] [0130 Sat to 0520 Mon]
|  | 49 | [12 empty] | 28 | Carstairs to Midcalder Jn (Mosshat - Dn) | 29 | Glengarnock (Dn) | 29 | Lochwinnoch (Dn) [MOBC] |  |  | 43 | Kirtlebridge - Up (Cove-Lockerbie) [xover out of use Mon wk 49 to Sun wk 51] [M] [0530 Sat to 0020 Mon] | [10 empty] | 12 | Kilwinning Jn S&C Tamp ( Maint) [0005 Sun to 1200 Sun]
|  | 50 | [12 empty] | 28 | Carstairs to Midcalder Jn (Mosshat - Dn) | 29 | Lochwinnoch (Dn) |  |  |  |  | 43 | Kirtlebridge - Dn (Cove-Lockerbie) [xover out of use Mon wk 49 to Sun wk 51] [M] [0530 Sat to 0020 Mon] |  |  | 393 | Strathcarron to Kyle [Earthworks] [2050 Fri 6/3/09 to 0615 Mon 23/3/09]- Ev1
|  | 51 | [12 empty] | 28 | Carstairs to Midcalder Jn (Mosshat - Dn) | 29 | Lochwinnoch (Dn) | 54 | Auchterarder (Up) [0030 Sat to 0100 Mon] | 54 | Jeanfield (Up) [MOBC] (0800 Mon to 1800 Tue) | 43 | Kirtlebridge (Cove-Lockerbie) [xover out of use Mon wk 49 to Sun wk 51] [M] [0530 Sat to 0020 Mon] | 173 | Stirling Middle 18, 20A/B, 22A/B, 32A/B, 35, 56, 72 (0030 Sat 14/03/09 to 0525 Sat 21/3/09) Ev2
|  | 52 | [12 empty] | 28 | Carstairs to Midcalder Jn (Mosshat - Dn) | 29 | Lochwinnoch (Dn)
2009/10 (2009 TTY) | PERIOD C | 1 | [6 empty] | 54 | Eglinton St Jn to Eglinton St Tunnel (M74 Extension) |  |  |  |  | 43 | Lockerbie - Carstairs So.Jn [Perchall Dn] (K) | 28 | Carstairs to Midcalder Jn (Harburn - Up) | 54 | Gushetfaulds (Up Slow) [ALB - access to Polmadie CSD only available from Shawfield end] |  |  | 54 | Rutherglen - Glasgow Cen (Larkfield Jn 927a/b) [ALB - access to Polmadie CSD only available from Shawfield end] [M] |  |  | 390 | Glenfinnan to Mallaig (E) incl UB313/065 Glenfinnan Viaduct (Repairs) [0001 Sat 28/3/09 to 0545 Mon 13/4/09] Ev1 | [6 empty] | 12 | Lesmahagow Jn S&C Maint Tamp (Law Jn - Uddingston) [0020 Sun to 1220 Sun - ROTR + 3hr 20 min]
|  | 2 |  |  |  |  | 389 | Gourock Interchange Project (0100 Sat 4/4/09 to 0530 Mon 20/4/09) Ev1 | 54 | Eglinton St Jn to Eglinton St Tunnel (M74 Extension) |  |  |  |  | 43 | Lockerbie - Carstairs So.Jn [Wamphray - Dn] (K) | 28 | Carstairs to Midcalder Jn (Harburn - Up) | 54 | Gushetfaulds (Dn Slow) [ALB - access to Polmadie CSD only available from Shawfield end] |  |  | 54 | Rutherglen - Glasgow Cen (Larkfield Jn 927a/b) [ALB - access to Polmadie CSD only available from Shawfield end] [M]
|  | 3 | Easter | [5 empty] | 54 | Dalmuir Station New Overbridge - ALB "Acess For All" Project |  |  |  |  | 43 | Lockerbie - Carstairs So.Jn [Wamphray - Dn] (K) | 78 | Carstairs - Midcalder Jn. [Cobbinshaw - Dn] (M) [1800 Sat to 2359 Tue] |  |  |  |  | 16 | Rutherglen - Glasgow Cen (Larkfield Jn 927a/b) [Fast Lines & Clydesdale Blocked] | 124 | Carstairs to Haymarket East Jn [Midcalder Jn] [0020 Fri 10/04 to 0440 Wed 15/04] Ev1 |  |  | 54 | UB 058/079 Whitely's Burn [Balloch Branch]
|  | 4 | [12 empty] | 43 | Lockerbie - Carstairs So.Jn [Dalmakether - Up] (K) | 28 | Carstairs to Midcalder Jn [Girwoodend - Up] | 29 | Crianlarich [Ardlui to Crianlarich] (Bus replacement Ardlui to Tyndrum Lower) |  |  | 16 | Rutherglen - Glasgow Cen (Larkfield Jn 927a/b) [Fast Lines & Clydesdale Blocked] |  |  | 105 | Crianlarich to Fort William (E) incl UB310/306 Tulloch Viaduct [2215 Fri 17/4/09 to 0715 Wed 22/4/09] Ev1 | [6 empty] | 12 | Blackford/ Auchterarder S&C Tamp (Maint) [0110 Sun to 1310 Sun - ROTR + 4hr 20 min]
|  | 5 | [10 empty] | 29 | Cambuslang (Platforms) | 43 | Lockerbie - Carstairs So.Jn [Abington - Up] (M) | 28 | Carstairs to Midcalder Jn [Girwoodend - Up] | 29 | Crianlarich [Ardlui to Crianlarich] (Bus replacement Ardlui to Tyndrum Lower) | [6 empty] | 105 | Crianlarich to Fort William (E) incl UB310/306 Tulloch Viaduct [2215 Fri 24/4/09 to 0715 Wed 29/4/09] Ev1 | [6 empty] | 12 | Polmont Jn S&C Tamp (Maint) [0015 Sun to 1215 Sun - ROTR + 4hr 10 min]
|  | 6 | May Day | [9 empty] | 29 | Cambuslang (Platforms) | 43 | Lockerbie - Carstairs So.Jn [Abington - Up] (M) | 28 | Carstairs to Midcalder Jn (Wilsontown - Up) (M) |  |  |  |  | 124 | Carmuirs East Jn 4A/B, 12A/B, 22A/B [0045 Sat 2/05/09 to 0440 Thur 7/05/09] Ev1 (Possession strategy under review) |  |  | 35 | UB076/008 Pilgrims Playing Fields, Falkirk [Polmont Jn to Grangemouth Jn] - must start 90hrs after S&C start
|  | 7 | [10 empty] | 29 | Cambuslang (Platforms) | 43 | Lockerbie - Carstairs So.Jn [Symington - Dn] (K) | 28 | Carstairs to Midcalder Jn (Wilsontown - Up) (M) |  |  |  |  | 43 | Lockerbie - Carstairs So.Jn [Whamphray - Dn S&C] [M] | 18 | Carmuirs East Jn [Welding & Stressing]
| PERIOD D1 | 8 | [10 empty] | 29 | Cambuslang (Platforms) | 28 | Midcalder Jn to Haymarket East Jn [Camps - Dn] | 28 | Carstairs to Midcalder Jn (Wilsontown - Up) (M) | 29 | Larbert Up Loop |  |  | 43 | Lockerbie - Carstairs So.Jn [Whamphray- Up S&C] [M] | 12 | Carstairs to Haymarket East Jn [Midcalder Jn - Follow-up Tamp]
|  | 9 | Spring BH | [11 empty] | 29 | Carmuirs East to West (Up) [Greenhill Lower and Carmuirs East Jn to Larbert Jn blocked] | 29 | Auchterarder (Dn) | 29 | West Kilbride (Up Freight) |  |  | 16 | Stirling Middle Jn [Follow-up Tamp] |  |  | 29 | UB132/021D Polmaise Jn [Plean to Stirling] | 29 | UB285/104 (Shotts to Addiewell)
|  | 10 | [12 empty] | 29 | Bonnymuir (Dn) | 29 | Dunfermline Town (Up) |  |  |  |  | 12 | Carmuirs East Jn [Follow-up Tamp] |  |  | 29 | UB113/024 Stream Thornton [Redford Jn to Thornton West Jn] | 29 | UB285/94 (Shotts to Addiewell)
|  | 11 | [12 empty] | 29 | Bonnymuir (Dn) | 29 | Dunfermline Town (Up) |  |  |  |  | 12 | Carmuirs East Jn [Follow-up Tamp] |  |  | 54 | UB105/003 River Leven [Thornton North Jn to Methil] | 54 | UB105/002 River Ore [Thornton North Jn to Methil] | 29 | UB285/94 (Shotts to Addiewell)
|  | 12 |  | Shotts Miners [Week 12 or 13 tbc] |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | [6 empty] | 29 | Cowlairs (Up) [Cowlairs W Jn-Bishopbriggs] | 29 | Kinghorn (Up) | [16 empty] | 12 | Hyndland East Jn S&C Tamp ( Maint) [0025 Sun to 1225 Sun - ROTR + 5hr 5 min]
|  | 13 |  |  |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | [6 empty] | 29 | Cowlairs (Up) [Cowlairs W Jn-Bishopbriggs] | 29 | Kinghorn (Up) | [16 empty] | 10 | Larbert Jn S&C Tamp (Maint) [0030 Sun to 1030 Sun - ROTR + 1hrs 40min]
|  | 14 |  |  |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | [6 empty] | 29 | Woodilee (Dn) [Cowlairs W Jn-Bishopbriggs] | 29 | Waverley Plat 7 (formerly Plat 10) |  |  |  |  | 78 | Mossend South Jn [0115 Sat 27/6/09 to 0500 Tue 30/6/09] Ev1 and [0015 to 0615hrs midweek - ROTR + 45min] [under review] |  |  | 29 | UB090/088 Den Footpath [Kirkcaldy to Thornton South Jn] | 29 | Aberdour YD235a (E) | 54 | UB072/009 Queensferry Road (Winchburgh to Dalmeny) |  |  | 9 | Cowlairs East Jn S&C Tamp (Maint) [0300 Sun to 1200 Sun]
|  | 15 | Edinburgh Trades |  |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | [6 empty] | 29 | Waverley South Loop (links to Plat 10) | [6 empty] | 6 | Mossend South Jn [0015 to 0615hrs midweek - ROTR + 45min] [under review] |  |  | 29 | UB090/088 Den Footpath [Kirkcaldy to Thornton South Jn] | 29 | Aberdour YD235a (E) |  |  |  |  | 10 | Carmuirs West Jn S&C Tamp (Maint) [0030 Sun to 1030 Sun - ROTR + 2hrs 45min]
|  | 16 |  | Open Golf Turnberry Mon 13/7 to Sun 19/07/09 |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 29 | Edinburgh Tram (tie) - Saughton to Dalmeny |  |  |  |  | 29 | Birdsmill (Dn) [Bathgate Branch] | 29 | Haymarket Plat 1 (Up) - North Lines |  |  |  |  | 6 | Mossend South Jn [0015 to 0615hrs midweek - ROTR + 45min] [under review] |  |  | 54 | UB090/032 Cemetery Road, Inverkeithing [North Queensferry Tunnel to Inverkeithing Tunnel] | 54 | North Queensferry YU & YD 253 (E) [North Queensferry Tunnel to Inverkeithing Tunnel] | 54 | Forth Bridge |  |  | 10 | Cowlairs West Jn S&C Tamp (Maint) [0055 Sun to 1055 Sun - ROTR + 3hr 10 min]
| PERIOD D2 | 17 | Glasgow Fair |  |  |  | 54 | A2B Project - Newbridge Jn to Bathgate | 78 | Edinburgh Tram (tie) - Saughton to Dalmeny |  |  |  |  | 29 | Sighthill East (Dn) | 29 | Haymarket Plat 1 (Up) - North Lines | 54 | Dalrymple Jn (Chalmerston Branch only) [midweek] |  |  | 78 | North Queensferry 301A/B, 302A/B [0030 Sat to 0440 Tue] [M] Ev1 (Possession strategy under review) | 54 | Annbank (midweek - between Tue and Fri) | 54 | UB207/029 Cattle Creep Tannoch Hill (Annbank to Mauchline) | 78 | Forth Bridge [must not constrain haulage trains] Ev1 |  |  |  |  | 9 | Gartcosh Jn S&C Tamp (Maint) [0045 Sun to 0945 Sun - ROTR + 1hr 30 min]
|  | 18 |  |  |  |  | 54 | A2B Project - Newbridge Jn to Bathgate | 29 | Edinburgh Tram (tie) - Saughton to Dalmeny |  |  |  |  | 29 | Dalmeny (Up) | 29 | Longannet [midweek] | 29 | Levenseat (Up) (Shotts to Addiewell) |  |  | 125 | Langloan Jn 75A/B, 76, 77A/B/C, 78 [0001 Mon 27/7 to 0455 Sat 1/8 ] [M] Ev1 | 29 | North Queensferry 301A/B, 302A/B [Sun] | 29 | North Queensferry YU & YD 253 (E) [North Queensferry Tunnel to Inverkeithing Tunnel] | 29 | Forth Bridge [must not constrain haulage trains] |  |  |  |  | 12 | Sighthill East & West Jns S&C Tamp (Maint) [0050 Sun to 1250 Sun - ROTR + 4hr 35 min]
|  | 19 |  |  |  |  | 54 | A2B Project - Newbridge Jn to Bathgate | [6 empty] | 54 | Cosshogle (Up) [Kirkconnel to Thornhill] | 29 | Turnhouse (Up) [Passenger services to use Dalmeny Plat 2 from N.Queensferry end] |  |  |  |  | 173 | Mossend East Jn 126, 127, 128A/B, 129, 131A/B, 132 [0001 Sat 1/8/09 to 0500 Sat 8/8/09] Ev2 |  |  | 54 | UB161/259 Mansefield (Thornhill)
|  | 20 |  |  |  |  | 54 | A2B Project - Newbridge Jn to Bathgate | [6 empty] | 54 | Carronbridge (Up) [Kirkconnel to Thornhill] | 29 | Turnhouse (Up) [Passenger services to use Dalmeny Plat 2 from N.Queensferry end] | [8 empty] | 54 | UB161/308 Wath Burn (Dumfries to Annan)
|  | 21 | Edinburgh Festival 14/08-6/09 | [9 empty] | 54 | Coatbridge Central (Platforms) | 29 | Carronbridge (Up) [Kirkconnel to Thornhill] | 29 | Dumfries South (Up) [linked to S&C] | 29 | Mossend East Curve (Up) [All Jcns Blocked - North, East , South , West] |  |  | 54 | Dumfries [KA. KB, F] |  |  | 29 | UB161/308 Wath Burn (Dumfries to Annan) | 54 | UB132/084 B804 Main St, Glenboig [Gartshewrrie So.Jn-Garnqueen Nth Jn - Cumbernauld route blocked] | 54 | Cardowan Rd, Stepps (Bridgeguard 3) [Sighthill to Gartcosh Jn]
|  | 22 | [10 empty] | 29 | Coatbridge Central (Platforms) | 29 | Burnhouse (Up) [no access to Mossend] | 29 | Dumfries South (Up) [linked to S&C] | 29 | Mossend East Curve (Up) [All Jcns Blocked - North, East , South , West] |  |  | 29 | Dumfries [KA. KB, F]
|  | 23 |  | August BH (England) | [10 empty] | 29 | Garnqueen North (Up) [Gartsherrie So.Jn-Garnqueen Nth] - Gartsherrie So.Jn to Gartcosh Jn available
|  | 24 | [12 empty] | 29 | Lenziemill (Dn) [Garnqueen Nth-Cumbernauld] | 29 | Allanfearn [Inverness-Nairn] | 29 | Nairn |  |  | 54 | Nairn No.103 pts |  |  | 54 | UB291/061 Findhorn Viaduct [Forres to Nairn]
| PERIOD E | 25 | First ScotRail services diverted via Shotts |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 29 | Stevenston Loop Extension [target completion Sept 09] |  |  | 29 | Kilmaurs | 29 | Wishaw Central (Dn) | 29 | Seafield [Inverness-Nairn] |  |  | 54 | Nairn No.101 pts | 12 | Mossend East Jn (Follow-up Tamp) | [8 empty] | 8 | Greenhill Lower Jn S&C Tamp (Maint) [0015 to 0815hrs - ROTR + 20 min]
|  | 26 |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 29 | Stevenston Loop Extension [target completion Sept 09] | 29 | Dyce (Platforms) | 29 | Kilmaurs | 29 | Wishaw Central (Dn) | 29 | Stoneywood [Aberdeen -Dyce] |  |  | 54 | Huntly No.7pts
|  | 27 |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 54 | Stranraer Station Redevelopment [target completion Sept 09] |  |  | 20 | Dundyvan (Dn) [Langloan Jn to Whifflet N. Jn] | 29 | Wishaw Central (Dn)
|  | 28 |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn |  |  |  |  | 168 | Strathcarron-Kyle Ev1 | [18 empty] | 8 | Craiglockhart Jn S&C Tamp (Maint) [2315 Sat to 0715 Sun - ROTR]
|  | 29 |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn |  |  |  |  | 48 | Monktonhall South (Up) | [6 empty] | 48 | Stenton 1A/B, 2A/B - Up [M] | [10 empty] | 8 | Winchburgh Jn Jn S&C Tamp (Maint) [0015 to 0815hrs - ROTR + 10min]
|  | 30 |  |  | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 54 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] |  |  | 48 | Markle (Up) | 29 | Johnny Baileys (Dn -RR) |  |  |  |  | 48 | Stenton 1A/B, 2A/B - Dn [M] |  |  | 390 | Glenfinnan to Mallaig (E) [0001 Sat 17/10/09 to 0545 Mon 2/11/09] Ev1 | 48 | UB001/086 Spott Road (Dunbar) |  |  |  |  | 8 | Newbridge Jn Jn S&C Tamp (Maint) [0025 to 0825hrs - ROTR + 25min]
|  | 31 | [8 empty] | 54 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] | 29 | Scotscalder & Forsinard (Platforms) | 48 | Reston (Dn) [c/o Drem Jn to LNE boundary only] | 48 | Lemington (Up) [c/o Drem Jn to LNE boundary only] | [10 empty] | 29 | UB302/333 Scotscalder Acc Rd [Scotscalder] | 29 | UB302/332 Dorrery Creep [Scotscalder] |  |  | 12 | Dalmeny S&C Tamp (Maint) [0045 Sun to 1245 Sun - ROTR + 4hr 45 min]
|  | 32 | [8 empty] | 54 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] |  |  | 48 | Lemington (Dn) [c/o Drem Jn to LNE boundary only] | 48 | Torness (Dn) [c/o Drem Jn to LNE boundary only] | 54 | Clunes [ Inverness-Muir of Ord] |  |  | 54 | Muir of Ord No.4 pts | [10 empty] | 8 | Portobello Jn S&C Tamp (Maint) (0035hrs to 0835hrs Sun - ROTR)
|  | 33 | [8 empty] | 54 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] | 29 | Dunkeld & Birnam (Platforms) | 29 | Perth North (Up) | 29 | Cradelehall (Up) [Carrbridge-Inverness] |  |  |  |  | 54 | Kingussie No.11 pts [no access to station] |  |  | 29 | UB290/006 B9099 Caputh Rd, Murthly | 54 | Slochd to Culloden (Earthworks)
|  | 34 | [8 empty] | 54 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] | 29 | Dunkeld & Birnam (Platforms) | 29 | Perth North (Up) | 29 | Cradelehall (Up) [Carrbridge-Inverness] | 29 | Crookston Station |  |  | 78 | Stanley No.24 pts [ services between Dunkeld and Inverness on Mon 16/11] Ev1 | 54 | Aviemore No.24 pts [no access to station] | 389 | Crianlarich to Oban (E) [0001 Sat 14/11/09 to 0530 Mon 30/11/09] Ev1 [access to Crianlarich Lower required] | 54 | Slochd to Culloden (Earthworks)
|  | 35 |  | SPT Christmas Shopper Services | [8 empty] | 29 | Dunkeld & Birnam (Platforms) | 29 | Perth North (Up) | [6 empty] | 29 | Stanley No.24 pts
|  | 36 | [32 empty] | 9 | Ladybank Jn S&C Tamp (Maint) [0040 Sun to 0940 Sun - ROTR + 2hrs 15min]
|  | 37 | [12 empty] | 29 | Carpetwise (Edin Sub) | [18 empty] | 10 | Inverkeithing Cen S&C Tamp (Maint) [2350 Sat - 0950 Sun - ROTR + 1hr 50 min ]
2009/10 (2010 TTY) | '09 PERIOD A | 38 | [12 empty] | 29 | Carpetwise (Edin Sub) | [18 empty] | 10 | Inverkeithing East S&C Tamp (Maint) [2350 Sat - 0950 Sun - ROTR + 2hrs]
|  | 39 |  | Christmas Day Fri 25/12/09 | [10 empty] | 78 | Winchburgh (Up) [0050 Fri 25/12 to 0600 Mon 28/12 incl] | 54 | North Queensferry Tunnel (Up) [Fri 25/12/09 & Sat 26/12/09]
|  | FY40 |  | New Year's Day Fri 1/1/10
|  | 41 | [10 empty] | 29 | Dundee Station (Platforms) | 29 | Dundee Station (Up Loop) | 29 | Kinnaber (Dn) - south of Laurencekirk |  |  |  |  | 54 | Laurencekirk 33A/B, 36B |  |  | 54 | UB133/306 Balfieth (Laurencekirk to Stonehaven) | 54 | Carmont YD51 & YU51 (E) (Laurencekirk to Stonehaven)
|  | 42 | [8 empty] | 29 | GARL- c/o Shields Jn to Paisley [Cardonald to Arkleston Jn] | 29 | Dundee Station (Platforms) | 29 | Dundee Plat 4 (Dn) | 29 | Monifeith (Up) [MOBC] | 29 | Carfin (Up) |  |  | 54 | Laurencekirk 33A/B, 36B |  |  | 54 | Glenury Viaduct (Stonehaven to Newtonhill) | 54 | Carmont YD51 & YU51 (E) (Laurencekirk to Stonehaven) |  |  |  |  | 9 | Greenhill Upper Jn S&C Tamp (Maint) [0030 to 0930hrs - ROTR + 1hr 40 min]
|  | 43 | [8 empty] | 29 | GARL- c/o Shields Jn to Paisley [Cardonald to Arkleston Jn] | 29 | Dundee Station (Platforms) | 29 | Dundee Station (Dn Loop) | 29 | Carmont (Up) - south of Stonehaven [MOBC] | 29 | Carfin (Up) |  |  | 54 | Stonehaven 37, 39A/B |  |  | 54 | Den of Cowie (Stonehaven to Newtonhill) | 54 | Carmont YD51 & YU51 (E) (Laurencekirk to Stonehaven)
|  | 44 | [8 empty] | 29 | GARL- c/o Shields Jn to Paisley [Cardonald to Arkleston Jn] |  |  | 54 | Broughty Ferry (Dn) | 54 | South Barns (Up) - south of Laurencekirk [MOBC] |  |  |  |  | 54 | Stonehaven 37, 39A/B |  |  | 43 | Cove to Lockerbie [UB030/105 Netherplace] [not EEA compliant] | [6 empty] | 8 | Thornton North Jn S&C Tamp (Maint) [0035 to 0835 - ROTR + 55min]
|  | 45 | [8 empty] | 29 | GARL- c/o Shields Jn to Paisley [Cardonald to Arkleston Jn] |  |  | 29 | Cupar Platform (Up) | 29 | Carfin (Dn) |  |  |  |  | 54 | Leuchars 13A/B, 36 |  |  | 43 | Cove to Lockerbie [UB030/106 Netherplace] [not EEA compliant] | 54 | Tay Bridge |  |  |  |  | 12 | Niddrie West/ South Jn S&C Tamp (Maint) [0001 Sun to 1201 Sun - ROTR + 2hrs]
| '09 PERIOD B | 46 |  | RBS Six Nations Rugby [dates and venues tbc] - Edinburgh to Aberdeen/ Inverness, E&G and Shotts routes to be open | [6 empty] | 29 | GARL- c/o Shields Jn to Paisley [Cardonald to Arkleston Jn] |  |  | 29 | Water of Luce (Rev) [Girvan-Stranraer] | 29 | Carfin (Dn) |  |  |  |  | 54 | Leuchars 13A/B, 36 |  |  | 54 | Girvan to Stranraer (E) YD005, YU223, YU219, YD206 | 54 | Tay Bridge
|  | 47 | [8 empty] | 29 | GARL- c/o Shields Jn to Paisley [Cardonald to Arkleston Jn] |  |  | 29 | Girvan (Rev) | 29 | Thornton North (Dn) | 29 | Bridge of Earn (Ladybank Jn - Hilton Jn) | [6 empty] | 54 | Girvan to Stranraer (E) YD005, YU223, YU219, YD206 | 96 | Law Jn to Wishaw Cen Jn [UB036/001B Garriongill Intersection Bdge]
|  | 48 | [8 empty] | 29 | GARL- c/o Shields Jn to Paisley [Cardonald to Arkleston Jn] |  |  | 29 | Girvan (Rev) | 29 | Thornton North (Dn) | [8 empty] | 54 | Girvan to Stranraer (E) YD005, YU223, YU219, YD206
|  | 49 | [12 empty] | 29 | Beith (Dn) | 29 | Barassie (Rev) | 29 | Thornton North (Dn) |  |  | 54 | Brownhill 56A/B, 57, 58
|  | 50 | [12 empty] | 29 | Beith (Dn) | 29 | Thornton South (Up) [route available from West to North Jns] |  |  |  |  | 54 | Brownhill 56A/B, 57, 58 |  |  | 29 | Slochd to Culloden (E) | 100 | Craigendoran to Crianlarich (E) incl UB310/104 Allt Fionn Ghlinne (Oss Burn) [Ardlui to Crianlarich] [2345 Fri 5/03/10 to 0415 Wed 10/03/10]
|  | 51 | [12 empty] | 29 | Glengarnock (Dn) | 29 | Lochwinnoch (Up) | 29 | Thornton South (Up) [route available from West to North Jns] | [6 empty] | 29 | Slochd to Culloden (E) | 100 | Craigendoran to Crianlarich (E) [2345 Fri 12/03/10 to 0415 Wed 17/03/10] |  |  |  |  | 12 | Kilwinning Jn S&C Tamp ( Maint) [0005 Sun to 1200 Sun - ROTR + 4hrs]
|  | 52 | [12 empty] | 29 | Lochwinnoch (Up) | 44 | Keppoch [Roy Bridge-Spean Bridge] | [8 empty] | 29 | Slochd to Culloden (E) | 105 | Crianlarich to Fort William (E) [2215 Fri 19/031/10 to 0715 Wed 24/03/10] |  |  |  |  | 8 | Thornton West Jn S&C Tamp (Maint) [0010 to 0810 - ROTR]
|  | 53 | [12 empty] | 44 | Keppoch [Roy Bridge-Spean Bridge] | [10 empty] | 29 | Slochd to Culloden (E) | 105 | Crianlarich to Fort William (E) [2215 Fri 26/03/10 to 0715 Wed 31/03/10] | 29 | UB162/025 Cattle Creep Western Gailes [Kilwinning-Barassie] |  |  | 8 | Thornton South Jn S&C Tamp (Maint) [0010 to 0750 - ROTR]
[11 empty] | KEY | POWERPOINT SLIDE | KEY | POWERPOINT SLIDE
| Bank Hol (West) |  |  | Prepared by David H Kerr, Integrated Planning Manager, TDPU Scotland, Network Rail. email : david.kerr@networkrail.co.uk tel: 0141 555 4859 | [7 empty] | 1 - GSW work |  | 1 - GSW work |  | 5 - South Electrics |  | 10 - Forth Bridge & Fife |  |  | All 54hr possessions are planned for Sat/ Sun unless otherwise shown
| Bank Hol (East) | [10 empty] | 1 & 2 - WCML work |  | 1 & 2 - WCML work |  | 6 - North Electrics |  | 11 - Central Scotland
| Bank Hol (All) | [10 empty] | 1 & 2 - other WCML-related routes |  | 1 & 2 - other WCML-related routes |  | 7 - West Highland Line |  | 12 - Dundee to Aberdeen
| Bank Hol (England) | [10 empty] | 3 - East Coast Main Line |  | 3 - East Coast Main Line |  | 8 - E&G West & Cumbernauld |  | 13 - Highland Line & Abdn/Inv
Note on G6: new
Note on G43: new
Note on G44: new
Note on G45: new
Note on G46: new
Note on G47: new
Note on G48: new
Note on I4: new
Note on I6: new
Note on I30: new
Note on I31: new
Note on I32: new
Note on I34: new
Note on I35: new
Note on I37: new
Note on I38: new
Note on I43: new
Note on I44: new
Note on I45: new
Note on I46: new
Note on I47: new
Note on I48: new
Note on K11: new
Note on K12: new
Note on K34: new
Note on K35: new
Note on K36: new
Note on K43: new
Note on K44: new
Note on K45: new
Note on K46: new
Note on K47: new
Note on K48: new
Note on M6: new
Note on M7: new
Note on M8: new
Note on M9: new
Note on M10: new
Note on M11: new
Note on M12: new
Note on M13: new
Note on M14: new
Note on M48: new
Note on M49: new
Note on M50: new
Note on M51: new
Note on M52: new
Note on M57: new
Note on M60: new
Note on M62: new
Note on M63: new
Note on M64: new
Note on M65: new
Note on M66: new
Note on O4: new
Note on O12: new
Note on O59: new
Note on O60: new
Note on O61: new
Note on Q6: new
Note on Q7: new
Note on Q8: new
Note on Q9: new
Note on Q10: new
Note on Q11: new
Note on Q12: new
Note on Q13: new
Note on Q14: new
Note on Q36: new
Note on Q59: new
Note on Q60: new
Note on Q61: new
Note on Q62: new
Note on Q63: new
Note on Q71: new
Note on S7: new
Note on S8: new
Note on S9: new
Note on S10: new
Note on S11: new
Note on S12: new
Note on S13: new
Note on S14: new
Note on S15: new
Note on S16: new
Note on S17: new
Note on S18: new
Note on S28: new
Note on S29: new
Note on S30: new
Note on S31: new
Note on S36: new
Note on S57: new
Note on S59: new
Note on S60: new
Note on S61: new
Note on S62: new
Note on S65: new
Note on S66: new
Note on S68: new
Note on S70: new
Note on U8: new
Note on U10: new
Note on U11: new
Note on U12: new
Note on U14: new
Note on U15: new
Note on U22: new
Note on U23: new
Note on U52: new
Note on U65: new
Note on U67: new
Note on U69: new
Note on Y4: new
Note on Y7: new
Note on Y8: new
Note on Y14: new
Note on Y15: new
Note on Y16: new
Note on Y17: new
Note on Y18: new
Note on Y35: new
Note on Y59: new
Note on Y60: new
Note on Y61: new
Note on Y62: new
Note on Y63: new
Note on Y64: new
Note on AA36: new
Note on AC11: new
Note on AC12: new
Note on AC16: new
Note on AC19: new
Note on AC22: new
Note on AC23: new
Note on AC28: new
Note on AC29: new
Note on AC32: new
Note on AC33: new
Note on AC48: new
Note on AC52: new
Note on AC59: new
Note on AC60: new
Note on AC61: new
Note on AE12: new
Note on AE29: new
Note on AE59: new
Note on AE60: new
Note on AE61: new
Note on AE63: new
Note on AE64: new
Note on AE68: new
Note on AE69: new
Note on AE70: new
Note on AE71: new
Note on AK3: new
Note on AK4: NEW
Note on AK6: new
Note on AK11: new
Note on AK12: new
Note on AK15: new
Note on AK30: new
Note on AK54: new
Note on AK55: new
Note on AK56: new
Note on AK62: new
Note on AK63: new
Note on AK69: new
Note on AK70: new
Note on AK71: new

## data
Set reference | Discipline title | Hours | Locations | Set Range references | Set Label reference | Start Row | End Row | Seperator
Plan range | [5 empty] | 2 | 70 | :
1 | #REF! | D | E | D2:E70 | E1
2 | #REF! | F | G | F2:G70 | G1
3 | #REF! | H | I | H2:I70 | I1
4 | #REF! | J | K | J2:K70 | K1
5 | #REF! | L | M | L2:M70 | M1
6 | #REF! | N | O | N2:O70 | O1
7 | #REF! | P | Q | P2:Q70 | Q1
8 | #REF! | R | S | R2:S70 | S1
9 | #REF! | T | U | T2:U70 | U1
10 | #REF! | V | W | V2:W70 | W1
11 | #REF! | X | Y | X2:Y70 | Y1
12 | #REF! | Z | AA | Z2:AA70 | AA1
13 | #REF! | AB | AC | AB2:AC70 | AC1

## template
Week No | Hrs | Location | Discipline | Row Cnt | Set Ref | Year | TDPU Ref | aiwp ref
37 | #REF! | #REF! | #REF! | 2 | 1 | 2007/08 |  | E2
38 | #REF! | #REF! | #REF! | 3 |  | 2007/08 |  | E3
39 | #REF! | #REF! | #REF! | 4 |  | 2007/08 |  | E4
39 | #REF! | #REF! | #REF! | 5 |  | 2007/08 |  | E5
40 | #REF! | #REF! | #REF! | 6 |  | 2007/08 |  | E6
41 | #REF! | #REF! | #REF! | 7 |  | 2007/08 |  | E7
42 | #REF! | #REF! | #REF! | 8 |  | 2007/08 |  | E8
43 | #REF! | #REF! | #REF! | 9 |  | 2007/08 |  | E9
44 | #REF! | #REF! | #REF! | 10 |  | 2007/08 |  | E10
45 | #REF! | #REF! | #REF! | 11 |  | 2007/08 |  | E11
46 | #REF! | #REF! | #REF! | 12 |  | 2007/08 |  | E12
47 | #REF! | #REF! | #REF! | 13 |  | 2007/08 |  | E13
48 | #REF! | #REF! | #REF! | 14 |  | 2007/08 |  | E14
49 | #REF! | #REF! | #REF! | 15 |  | 2007/08 |  | E15
50 | #REF! | #REF! | #REF! | 16 |  | 2007/08 |  | E16
51 | #REF! | #REF! | #REF! | 17 |  | 2007/08 |  | E17
52 | #REF! | #REF! | #REF! | 18 |  | 2007/08 |  | E18
1 | #REF! | #REF! | #REF! | 20 |  | 2008/09 |  | E20
2 | #REF! | #REF! | #REF! | 21 |  | 2008/09 |  | E21
3 | #REF! | #REF! | #REF! | 22 |  | 2008/09 |  | E22
4 | #REF! | #REF! | #REF! | 23 |  | 2008/09 |  | E23
5 | #REF! | #REF! | #REF! | 24 |  | 2008/09 |  | E24
6 | #REF! | #REF! | #REF! | 25 |  | 2008/09 |  | E25
7 | #REF! | #REF! | #REF! | 26 |  | 2008/09 |  | E26
8 | #REF! | #REF! | #REF! | 27 |  | 2008/09 |  | E27
9 | #REF! | #REF! | #REF! | 28 |  | 2008/09 |  | E28
10 | #REF! | #REF! | #REF! | 29 |  | 2008/09 |  | E29
11 | #REF! | #REF! | #REF! | 30 |  | 2008/09 |  | E30
12 | #REF! | #REF! | #REF! | 31 |  | 2008/09 |  | E31
13 | #REF! | #REF! | #REF! | 32 |  | 2008/09 |  | E32
14 | #REF! | #REF! | #REF! | 33 |  | 2008/09 |  | E33
15 | #REF! | #REF! | #REF! | 34 |  | 2008/09 |  | E34
16 | #REF! | #REF! | #REF! | 35 |  | 2008/09 |  | E35
17 | #REF! | #REF! | #REF! | 36 |  | 2008/09 |  | E36
18 | #REF! | #REF! | #REF! | 37 |  | 2008/09 |  | E37
19 | #REF! | #REF! | #REF! | 38 |  | 2008/09 |  | E38
20 | #REF! | #REF! | #REF! | 39 |  | 2008/09 |  | E39
21 | #REF! | #REF! | #REF! | 40 |  | 2008/09 |  | E40
22 | #REF! | #REF! | #REF! | 41 |  | 2008/09 |  | E41
23 | #REF! | #REF! | #REF! | 42 |  | 2008/09 |  | E42
24 | #REF! | #REF! | #REF! | 43 |  | 2008/09 |  | E43
25 | #REF! | #REF! | #REF! | 44 |  | 2008/09 |  | E44
26 | #REF! | #REF! | #REF! | 45 |  | 2008/09 |  | E45
27 | #REF! | #REF! | #REF! | 46 |  | 2008/09 |  | E46
28 | #REF! | #REF! | #REF! | 47 |  | 2008/09 |  | E47
29 | #REF! | #REF! | #REF! | 48 |  | 2008/09 |  | E48
30 | #REF! | #REF! | #REF! | 49 |  | 2008/09 |  | E49
31 | #REF! | #REF! | #REF! | 50 |  | 2008/09 |  | E50
32 | #REF! | #REF! | #REF! | 51 |  | 2008/09 |  | E51
33 | #REF! | #REF! | #REF! | 52 |  | 2008/09 |  | E52
34 | #REF! | #REF! | #REF! | 53 |  | 2008/09 |  | E53
35 | #REF! | #REF! | #REF! | 54 |  | 2008/09 |  | E54
36 | #REF! | #REF! | #REF! | 55 |  | 2008/09 |  | E55
FY37 | #REF! | #REF! | #REF! | 56 |  | 2008/09 |  | E56
FY38 | #REF! | #REF! | #REF! | 57 |  | 2008/09 |  | E57
FY39 | #REF! | #REF! | #REF! | 58 |  | 2008/09 |  | E58
FY40 | #REF! | #REF! | #REF! | 59 |  | 2008/09 |  | E59
FY41 | #REF! | #REF! | #REF! | 60 |  | 2008/09 |  | E60
FY42 | #REF! | #REF! | #REF! | 61 |  | 2008/09 |  | E61
FY43 | #REF! | #REF! | #REF! | 62 |  | 2008/09 |  | E62
FY44 | #REF! | #REF! | #REF! | 63 |  | 2008/09 |  | E63
FY45 | #REF! | #REF! | #REF! | 64 |  | 2008/09 |  | E64
FY46 | #REF! | #REF! | #REF! | 65 |  | 2008/09 |  | E65
FY47 | #REF! | #REF! | #REF! | 66 |  | 2008/09 |  | E66
FY48 | #REF! | #REF! | #REF! | 67 |  | 2008/09 |  | E67
FY49 | #REF! | #REF! | #REF! | 68 |  | 2008/09 |  | E68
FY50 | #REF! | #REF! | #REF! | 69 |  | 2008/09 |  | E69
FY51 | #REF! | #REF! | #REF! | 70 |  | 2008/09 |  | E70
FY52 | #REF! | #REF! | #REF! | 71 |  | 2008/09 |  | E71

## References
Week No | Hrs | Location | Discipline | Year | TDPU Ref | aiwp ref
37 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0605 | AA2
37 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0297 | I2
38 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0606 | AA3
38 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0511 | K3
38 | 29 | Millerhill Freddie 7 | Plain Line Worksite | 2007/08 | G0303 | I3
39 | 29 | Cowlairs East S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0309 | AC4
39 | 29 | Cowlairs West S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0307 | AC5
39 | 54 | Glasgow Central re-interlocking - All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0310 | AA4
39 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0305 | W4
39 | 20 | Monktonhall South | S&C Tamp Follow-up Tamp | 2007/08 | G0304 | U4
39 | 96 | Shields [Continues into week 40] | S&C Worksite | 2007/08 | G0308 | S4
40 | 54 | Glasgow Central re-interlocking- All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0316 | AA6
40 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0317 | W6
40 | 126 | Shields [Continued from week 39] | S&C Worksite | 2007/08 | G0315 | S6
40 | 29 | Newbridge Jn (A-B Project) | 3rd Party Schemes | 2007/08 | NEW | E6
41 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0608 | AA7
41 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0318 | W7
41 | 102 | Shields | S&C Worksite | 2007/08 | G0321 | S7
41 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0516 | M7
41 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0322 | K7
41 | 29 | Dundee Plat 1 (Up M) | Plain Line Worksite | 2007/08 | G0319 | I7
42 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0609 | AA8
42 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0327 | W8
42 | 78 | Shields | S&C Worksite | 2007/08 | G0325 | S8
42 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0517 | M8
42 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0326 | K8
42 | 29 | Dundee (Up L) | Plain Line Worksite | 2007/08 | G0328 | I8
43 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0611 | AA9
43 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0333 | W9
43 | 54 | Shields | S&C Worksite | 2007/08 | G0334 | S9
43 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | O9
43 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0610 | M9
43 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0330 | K9
43 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0331 | I9
44 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0612 | AA10
44 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0341 | W10
44 | 54 | Shields | S&C Worksite | 2007/08 | G0339 | S10
44 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | NEW | M10
44 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0338 | K10
44 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0340 | I10
45 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0345 | AA11
45 | 29 | Lagganstarroch | Structures Renewals 2 | 2007/08 | G0344 | Y11
45 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0342 | W11
45 | 51 | Slateford | S&C Worksite | 2007/08 | G0347 | S11
45 | 29 | Gorton (Rev) | Plain Line Worksite | 2007/08 | G0522 | O11
45 | 29 | Glenury (Dn) | Plain Line Worksite | 2007/08 | G0521 | M11
45 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0346 | K11
45 | 29 | Uddingston (Dn) | Plain Line Worksite | 2007/08 | G0388 | I11
46 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0352 | AA12
46 | 29 | Lagganstarroch | Structures Renewals 1 | 2007/08 | G0349 | W12
46 | 29 | Slateford | S&C Worksite | 2007/08 | G0351 | S12
46 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O12
46 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | M12
46 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | NEW | K12
46 | 29 | Dimsdale (Up) | Plain Line Worksite | 2007/08 | G0389 | I12
47 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0357 | AA13
47 | 54 | Kingskettle | Structures Renewals 1 | 2007/08 | G0355 | W13
47 | 54 | Shields Follow-up Tamp | S&C Tamp Follow-up Tamp | 2007/08 | G0358 | U13
47 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S13
47 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | M13
47 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0350 | K13
47 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0359 | I13
48 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0361 | AA14
48 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S14
48 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O14
48 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0513 | M14
48 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0354 | K14
48 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0360 | I14
49 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0366 | AA15
49 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S15
49 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0368 | M15
49 | 29 | Forthar (Up) | Plain Line Worksite | 2007/08 | G0363 | K15
49 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0367 | I15
50 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0371 | AA16
50 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S16
50 | 29 | Newton-on-Ayr (Dn) | Plain Line Worksite | 2007/08 | G0530 | M16
50 | 29 | Plean (Up) | Plain Line Worksite | 2007/08 | G0373 | K16
50 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0369 | I16
51 | 12 | Newton-on-Ayr S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0378 | AC17
51 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0372 | AA17
51 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S17
51 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | NEW | M17
51 | 43 | Auchencastle (Up) | Plain Line Worksite | 2007/08 | G0547 | K17
51 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0377 | I17
52 | 12 | Kilwinning Jn S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0381 | AC18
52 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0382 | AA18
52 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S18
52 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | G0383 | K18
52 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0380 | I18
1 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA20
1 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W20
1 | 54 | Stirling Middle | S&C Worksite | 2008/09 | new | S20
2 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA21
2 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W21
2 | 29 | Stirling Middle | S&C Worksite | 2008/09 | new | S21
3 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA22
3 | 54 | Larbert | S&C Worksite | 2008/09 | new | S22
4 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA23
4 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S23
5 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA24
5 | 78 | Falkland Yard | S&C Worksite | 2008/09 | new | S24
6 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA25
6 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S25
7 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA26
7 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S26
8 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA27
8 | 29 | Stirling Middle FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U27
9 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA28
10 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA29
11 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA30
12 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA31
12 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S31
13 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA32
13 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S32
14 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA33
14 | 78 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S33
15 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA34
15 | 54 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S34
16 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA35
16 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W35
16 | 78 | New Cumnock | S&C Worksite | 2008/09 | new | S35
16 | 168 | Ballochmyle (Up) | Plain Line Worksite | 2008/09 | new | I35
16 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G35
17 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA36
17 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W36
17 | 29 | New Cumnock | S&C Worksite | 2008/09 | new | S36
17 | 168 | Mauchline (Dn) | Plain Line Worksite | 2008/09 | new | I36
17 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G36
18 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA37
18 | 54 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W37
18 | 54 | Gartcosh | S&C Worksite | 2008/09 | new | S37
19 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA38
19 | 12 | Halbeath FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U38
19 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S38
20 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA39
20 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S39
21 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA40
21 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U40
22 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA41
22 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U41
23 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA42
23 | 12 | New Cumnock FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U42
24 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA43
24 | 51 | Monktonhall South (Up) | Plain Line Worksite | 2008/09 | new | I43
25 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA44
25 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I44
26 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA45
26 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W45
26 | 12 | Gartcosh FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U45
26 | 78 | Whifflet North | S&C Worksite | 2008/09 | new | S45
26 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I45
27 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA46
27 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W46
27 | 29 | Whifflet North | S&C Worksite | 2008/09 | new | S46
27 | 51 | Ninewar (Dn) | Plain Line Worksite | 2008/09 | new | K46
27 | 51 | Lemington (Up) | Plain Line Worksite | 2008/09 | new | I46
28 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA47
28 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W47
28 | 51 | Oxwellmains (Dn) | Plain Line Worksite | 2008/09 | new | I47
29 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA48
29 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W48
29 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S48
29 | 51 | Houndwood (Dn) | Plain Line Worksite | 2008/09 | new | I48
30 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA49
30 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W49
30 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S49
30 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I49
31 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA50
31 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W50
31 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S50
31 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I50
32 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA51
33 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA52
33 | 12 | Whifflet North FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U52
34 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA53
34 | 54 | Markinch | S&C Worksite | 2008/09 | new | S53
35 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA54
35 | 54 | Markinch | S&C Worksite | 2008/09 | new | S54
36 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA55
FY37 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA56
FY37 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S56
FY38 | 48 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA57
FY38 | 120 | Carmuirs East | S&C Worksite | 2008/09 | new | S57
FY39 | 77 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA58
FY39 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S58
FY40 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S59
FY41 | 12 | Markinch FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U60
FY41 | 54 | Cadder | S&C Worksite | 2008/09 | new | S60
FY44 | 54 | Beattock | S&C Worksite | 2008/09 | new | S63
FY44 | 43 | Ecclefechan (Dn) | Plain Line Worksite | 2008/09 | new | I63
FY45 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S64
FY45 | 43 | Fullwood (Dn) | Plain Line Worksite | 2008/09 | new | I64
FY46 | 12 | Carmuirs East FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U65
FY46 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S65
FY46 | 29 | Garriongill (Dn) | Plain Line Worksite | 2008/09 | new | I65
FY47 | 29 | Beattock Summit | S&C Worksite | 2008/09 | new | S66
FY47 | 29 | Garriongill (Up) | Plain Line Worksite | 2008/09 | new | I66
FY48 | 78 | Hilton Jn | S&C Worksite | 2008/09 | new | S67
FY48 | 29 | Rutherglen (Up Slow) | Plain Line Worksite | 2008/09 | new | I67
FY49 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W68
FY49 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S68
FY49 | 29 | Rutherglen Old Station (Up Slow) | Plain Line Worksite | 2008/09 | new | I68
FY50 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W69
FY50 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S69
FY50 | 29 | Shawfield (Up Slow) | Plain Line Worksite | 2008/09 | new | I69
FY51 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W70
FY51 | 54 | Hilton Jn - Ladybank Branch only | S&C Worksite | 2008/09 | new | S70