Scotland Engineering Access Consultation

DRS / Network Rail Scotland Meeting

Thursday 24th January, 2008

Old Meeting Room 3, Kingmoor

Minutes

Attendees

| Name | Representing |
| --- | --- |
| David Kerr (DK) | Network Rail Scotland |
| Gayle Robertson (GR) | Network Rail Scotland |
| Anne MacKenzie (AMacK) | Network Rail Scotland |
| Pauline McFarlane (PMcF) | Network Rail Scotland |
| David Stubbs (DS) | DRS |
| Sabrina Brannan (SB) | DRS |

Apologies

|  | Name |  | Representing |  |
| --- | --- | --- | --- | --- |
|  | Chris Connelly |  | DRS |  |
|  |  | Overview DK provided the meeting with copies of the 2008TTY and 2009TTY Scotland Territory Access Summary. The minutes from the previous meeting held on 22nd November 2007 have been used and updated to ensure consistency of information 2008TTY Access Summary Version 8.5 2009TTY Access Summary – ROTR Version 9.5 (ROTR V2) Engineering Plan Update - Version 9.5 (ROTR V2) GARL Project Update |  |  |
|  |  | Note Any alterations or Customer comments from the meeting are recorded in blue. Any actions from the meeting are recorded in red. |  |  |
|  |  | DRS Traffic Update CC commented existing traffic will continue into the 2009 timetable period. Inverness Inverness is to become a key area for DRS – new service for Tesco to commence Feb ‘08 with 6 days a week operation using 8’ 6 boxes. Dep Grangemouth approx 0500hrs arr Inverness approx 1100hrs. Return service dep Inverness approx 1400hrs. 1st train Tesco will be for non-perishable traffic. 2nd train is anticipated to commence within 6 months of 1st train and will convey perishable goods DRS Traffic Update – (continued) Still due to commence in Feb 2008, however there are still discussions being held with the Scottish Executive regarding the Freight Facilities Grant (FFG). SB to inform all of any further updates. Only diversionary route is via Aberdeen Aberdeen Craiginches facility to be commissioned in 1st week in Dec. Existing paths will be transferred to new terminal. Potential 2nd train for Aberdeen with Tesco traffic (Coatbridge – Aberdeen). On hold. SB to inform NR of any further updates. Anglo-Scottish More services planned in Scotland -Tesco primary service, commencement in May 2008. Dagenham to Coatbridge 3 round trips a week for that service. Ongoing. Ely to Central Scotland via the ECML full north bound half full south bound service (Eddie Stobart) 6 day operations. Other Internal Scotland No recent developments for Asda traffic to Stranraer. AMacK informed DRS that RA5 containers can operate to Stranraer. Subject to gauge clearance, possible extension of service from Inverness to Elgin. |  |  |
|  |  | Outstanding Compensation Issues DK asked what the status was re potential compensation claims by DRS for renewals undertaken in 2006/07 i.e Larbert Jn, Montrose South & North and Grangemouth Junction. DK highlighted the funding stream to cover such claims were drawing to a close as these Projects have now been concluded. DK apologised for the delay in responding to the claim received from DRS which was due to problems with the email system. DK stated more time would be required by NR to review the detail. DK highlighted that previous discussions during 2007 between Sarka Oldham and Angus Robertson had focussed on making a settlement for Montrose rather than Larbert and Grangemouth. SB agreed to discuss further with SO. DRS are reviewing their internal process by which possible compensation claims are identified, in order to update customers in advance so they can collate their costs sooner. Outstanding Compensation Issues (contd) SB to discuss with Sarka Oldham and clarify DRS’s position in relation to the previous discussions with Angus Robertson. DK to respond to DRS re compensation claims for Grangemouth and Larbert within the next 4 weeks. |  |  |
|  |  | Montrose North Signal Box DK advised that transfer of signalling control to Montrose North was due to be undertaken in Week 44 (2008TTY) under to cover of the 54hr possession for Glenury (PLTR). However, as a consequence of the overrun at Shields Junction at Christmas 2007, all renewal works involving complex signalling design are currently being reviewed which has resulted in this work being cancelled. DK advised the work cannot now be undertaken within its original 29hr possession and this incremental enhancement will now require a 40hr disruptive possession in Week 10, 2008TTY at the earliest. The feasibility of permitting the passage of the DRS services would be investigated. (For noting, to comply with the Informed Traveller Process and taking into account other works requiring diversionary routes, the earliest opportunity First ScotRail would consider further access opportunities would be Week 18) AMacK advised that DRS are planning to increase the length of the trains (10 megafrets) on their Aberdeen services but this cannot happen until Montrose North is commissioned (extension of Montrose Up Loop). DS stated that DRS would prefer the work at Montrose to be undertaken in another week when it can piggyback onto other works in that area to minimise disruption to their services. DS suggested Week 14 or 24 when works at Plean are already planned. DK to update Project Team and consider alternative options. |  |  |
|  |  | Plean Signal Box Abolition Stage 1 – Recovery Plan The work at Plean has been divided into 3 phases, Stage 1 (Week 40, 2008TTY), Stage 2 (Week 51, 2008TTY) and Stage 3a & 3b (Week 14 & 24 2008TTY respectively). Unfortunately, due to an overrun of pre-testing activities in Stage 1 there is a requirement for an additional 16hr possession prior to Stage 2 (Week 51) for signal testing. DK proposed Week 46 2008TTY, 2000 Sat – 1200 Sun. Network Rail understand that this is extremely short notice. However, the work must be undertaken prior to the commissioning of Stage 2. DRS responded positively and advised they can accommodate this additional possession by retiming 4A11 1038 Grangemouth to Aberdeen slightly later. PMcF to confirm with DRS proposed alternative dates. |  |  |
|  |  | Review of Scotland 2008 TTY Plan DK provided the meeting with the 2008 TTY Access Summary and the disruption to DRS traffic was reviewed week by week. Period A Weeks 37 & 38 No issues. Week 39 Laurieston Rd Overbridge SB to confirm diversion of 4A66, 4N83 & 4M30 to/from Mossend Down Yard (P D Stirling) Week 40 Plean – Stage 1 New intermediate signal section works phased over 3 stages, supporting future works at Stirling Middle. DRS advised no services running on 1st and 2nd January 2008 AMacK to inform DS and SB if Plean is Network Change. Action Complete. AMacK advised that Plean stage 1 was Network Change as it involved enhancement works whereas, Plean Stages 2 & 3 are not regarded as Network Change as these are renewals. Dundee – Aberdeen (54hr blocks) Combination of Plain line track renewals and Civils works. Route Blocked. DRS advised no services running on 1st and 2nd January 2008 Week 41 Dundee – Aberdeen (54hr blocks) Combination of Plain Line track renewals and Civils works. Route blocked with no suitable diversionary route ( except potentially via Inverness). CC to inform W H Malcolm of weekend blocks during Weeks 41 – 44 Week 42 as week 41 Week 43 as week 41 Week 44 as week 41 |  |  |
|  |  | Period B Week 45 - 50 No issues Week 51 Stirling – Alloa – Kincardine and Plean Stage 2 (29hrs) DRS to investigate possibility of obtaining smaller containers and investigate diversion of Aberdeen services via Forth Bridge and Fife (W7 Gauge) Action Complete. DRS unable to obtain smaller containers and have informed WH Malcolm that the Aberdeen service on the Monday is cancelled. Week 52 Stirling – Alloa – Kincardine (78hrs) Commissioning of the Stirling – Alloa route. DRS to investigate possibility of obtaining smaller containers and to investigate diversion of Inverness and Aberdeen services via Forth Bridge and Fife (W7 Gauge) Action Complete. DRS unable to obtain smaller containers and have informed WH Malcolm that the Aberdeen services on Sat/Sun/Mon are cancelled. |  |  |
|  |  | Period C Week 1 No issues. Week 2&3 Stirling Plats 6 & 9 (29hrs) Does not affect main lines or DRS traffic. Weeks 4 to 7 No issues. Period C Weeks 8 to 10 No issues. Weeks 11 & 12 Grahamston track renewal (29hr) DRS to investigate diversion of 4A66, 4N83 & 4M30 to/from Mossend Down Yard (P D Stirling). Action Complete. DRS to divert to/from Mossend Down Yard (P D Stirling). There may be capacity issues, as the maximum length allowed at Mossend Yard for the 4M30 service is 80 SLUs. Week 13 No issues. Week 14 Plean – Stage 3a (29hrs) DRS to investigate possibility of obtaining smaller containers and to investigate diversion of Aberdeen services via Forth Bridge and Fife (W7 Gauge) Action Complete. DRS unable to obtain smaller containers; informed WH Malcolm that Aberdeen service on the Sunday is cancelled. Weeks 15 to 21 No issues. Week 22 & 23 Whifflet S&C renewal (78hrs & 29hrs) Allows access to Mossend but no access to Coatbridge from the south. Originally c/o Coatbridge Jn but no longer feasible due to scope of work and methodology. DRS potential dispute - no access to Grangemouth. If Coatbridge Jn was available there would be no issues for DRS. DK asked if Mossend or Elderslie terminals could be considered. CC advised there will not be sufficient capacity at these terminals to accommodate all the services. DRS to investigate potential of using Euro terminal with EWS. The option of diverting Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML also to be investigated ( NB: this is a diversion which has previously been planned for 4M30) Action Ongoing: SB suggested that there is still a possibility of using the Euro terminal however, options still require to be discussed. DK to further investigate if there is any scope to reduce the possession limits to be c/o Coatbridge Jn. Action Complete. DK advised services can now be permitted through Coatbridge Jcn to/from Langloan Jcn start of possession (Week 22) on Saturday 23 August until 1000 Monday. Thereafter, the possession limits will need to be extended to include Coatbridge Jn for S&T testing until 0500hrs on Tuesday 26th August 2008. AMacK suggested an alternative route for Week 22 of running services via R&C line as possession limits have been marginally improved allowing trains to run from Grangemouth on to the R&C line to Polmadie and back again. In order to balance resources, it was suggested 4S49 arrival at Grangemouth on Monday morning would form 4M44 Grangemouth to Daventry on Tuesday and 4S45 arrival Friday morning at Mossend would form 4M30 Mossend to Daventry on Monday night. DRS to confirm review operational issues and confirm terminal alterations for the affected services. DK advised that Network Rail had reduced from 6 to 4 contractors nationally. As a consequence, the S&C renewals within Scotland were being transferred from Jarvis to First Engineering and Whifflet Jn was one of the sites which would be reviewed as part of the transition plan. Week 24 Plean – Stage 3b (33hrs) DRS to investigate possibility of obtaining smaller containers and to investigate diversion of Aberdeen services via Forth Bridge and Fife (W7 Gauge). Action Complete. DRS unable to obtain smaller containers; informed WH Malcolm that Aberdeen service is cancelled. |  |  |
|  |  | Period E Week 25 – 32 GARL - c/o Shields to c/o Arkleston Jn (29hr blocks) Refer to embedded GARL Project Update. 2008 disruptive access does not affect DRS traffic. The more significant disruptive access will not be required until 2010/11. Weeks 28 & 29 Paisley Gilmour St Re-roofing Project Ayr Platforms Plats 1 & 2 (2no. 54hrs) DK provided an overview on the scope of the Project which was principally to re- roof Paisley Gilmour Street. DK stated that this programme of work had only recently been advised to him. The proposed access strategy was constructed around the need to erect and dismantle the crash decks on both the Ayr and Gourock Platforms on a progressive basis. CC expressed his concern that the level of disruption to services seemed excessive given the work was only for re-roofing. DK explained the Project were currently in the design phase and the methodology could not be confirmed until a single option had been decided. DK agreed the possession requirements would be reviewed at the end of January 2008 when surveys had been completed and a more definitive access strategy should be known. Revisions to the possession strategy have now been proposed as a consequence of Version 1 responses and these will be discussed at the separate discussion when the outcome from the surveys are known. Timescales for completion of surveys have slipped slighty from January to February. (refer embedded Engineering Access Update for details) DK to provide update once a more definitive proposal is available. |  |  |
| 1 |  | Review of Scotland 2009 TTY Plan DK provided the meeting with the 2009 TTY Access Summary and the disruption to DRS traffic was reviewed week by week Additional items included the Section 4 & 7 items raised from the DRS response to RotR version 1. DK advised there are major S&C renewals at Hilton Jn and Stirling Middle planned for 2009 which would impact on DRS services. DK stated that Network Rail will be installing “modular” S&C at several locations during 2009 and this would support the implementation of the “7-day railway” Reduction in possession durations will be progressively introduced over the next few years (e.g possessions traditionally 54hrs reduced to 37 hrs with further time reductions in the long term to 8hrs). However, the modular concept is still at early phase but Network Rail will continue to seek opportunities to reduce access durations where possible. Review of Scotland 2009 TTY Plan (contd) DK provided an update of changes for the 2009TTY plan since the last DRS consultation meeting on 22nd November 2007. As a consequence of a review of target volumes to be delivered in 2009/10, the delivery teams had been given a revised track & S&C renewals programme resulting in various sites being deferred/cancelled into a future year. (Refer to embedded Engineering Plan Update) DRS RotR v.1 Response Section 4 1.4 Wamphray GF to Beattock South - Down Blocked 0530 Sat – 0530 Mon. All Year. PMcF resolved the issue by advising that this was a data error and the above block applied in Period C only. Period A Week 38 No issues. Week 39 & 40 Stirling to Perth Hilton Jn S&C and Jeanfield Track Renewals [Mainlines - 0130hrs Thurs 25/12/08 to 0510hrs Mon 29/12/08] DRS to investigate possibility of diverting Aberdeen and Inverness services via Stirling-Alloa route. SB advised that this year very few services are running 25, 26, 31 Dec (day services). No services 1 & 2 January. AMacK to confirm gauge for the Stirling to Alloa route. Action Complete. AMacK confirmed the gauge of the Stirling to Alloa route is W9 (and the Tay Bridge is W7) DRS confirmed dates of operation would be 27th & 28th December 2008. DRS to confirm requirements for Inverness and Aberdeen services. Week 40 Edinburgh Tram (tie) 54hrs reduced to 29hrs. (Refer to embedded Engineering Plan Update) A2B Project 54hrs reduced to 29hrs. (Refer to embedded Engineering Plan Update) Week 41 Dundee to Aberdeen (54hrs) Plain line track renewals – Route blocked with no suitable diversionary route (except potentially via Inverness). CC to inform W H Malcolm of weekend blocks during Weeks 41 – 44. Ongoing. Week 41 Dundee to Aberdeen (54hrs) (contd) DS advised that DRS had disputed these blocks in their RotR v.1 response although they accept there is no practical diversionary route available. WCML Law (Dn) track renewal 29hrs – reduced to 28hrs. Now 0010 Sun to 0430hrs Mon in order to accommodate the 0430 Glasgow - Euston Virgin West Coast service. Slight improvement for arrival time for 4S49 ex Daventry on Sun nights. (Refer to embedded Engineering Plan Update) Week 42 Dundee to Aberdeen (54hrs) As week 41 WCML Fullwood (Dn) track renewal 29hrs – reduced to 28hrs. Now 0010 Sun to 0430hrs Mon in order to accommodate the 0430 Glasgow - Euston Virgin West Coast service. Slight improvement for arrival time for 4S49 ex Daventry on Sun nights. (Refer to embedded Engineering Plan Update) Ayrshire Paisley Gilmour Street (Gourock Platforms 1 & 2 – Re-roofing/Re-glazing) 54hrs - Previously in Week 39 changed to Week 42. Does not affect DRS traffic. (Refer to embedded Engineering Plan Update) Week 43 Dundee to Aberdeen (54hrs) As week 41 YD093 Kirkton of Craig - Civils Additional site in Weeks 43 & 44 (54hrs) piggybacking existing 54hr access. (Refer to embedded Engineering Plan Update) WCML Fullwood (Dn) track renewal 29hrs – reduced to 28hrs. Now 0010 Sun to 0430hrs Mon in order to accommodate the 0430 Glasgow - Euston Virgin West Coast service. Slight improvement for arrival time for 4S49 ex Daventry on Sun nights. (Refer to embedded Engineering Plan Update) GARL (Paisley Gilmour St – Bishopton) Previously in Weeks 47 & 48 changed to Weeks 43 & 44 (54hrs). Does not affect DRS traffic. Week 44 Dundee to Aberdeen (54hrs) As week 41 - including Dock Street Tunnel (Up) track renewal which is now deferred until 2010/11 . Still disruptive access required for East Haven (Dn). (Refer to embedded Engineering Plan Update) YD093 Kirkton of Craig - Civils As Week 43 Week 44 WCML Fullwood (Dn) track renewal As Week 43 GARL (Paisley Gilmour St – Bishopton) As Week 43 |  |  |
| 2 |  | Period B Week 45 No issues. Week 46 No issues. Week 47 Stirling to Dundee Auchterarder & Ninewells track renewals (29hrs) DRS to investigate possibility of diverting Aberdeen service via Stirling-Alloa route AMacK to establish gauge (W7 or W8). Gauge confirmed as W7. DRS to confirm requirements for Aberdeen services. Week 48 Perth to Dundee Ninewells track renewals (29hrs) DRS to investigate possibility of diverting Aberdeen service via Stirling-Alloa route AMacK to establish gauge (W7 or W8). Gauge confirmed as W7. DRS to confirm requirements for Aberdeen services. Week 49 No issues. Week 50 No issues. Week 51 Paisley Gilmour St Re-roofing Project – Previously Week 3 Re-roofing Ayr Platforms 3 & 4 – includes crash deck installation – 54hrs DS highlighted that work on the Ayr platforms affect the Grangemouth to Elderslie service (to Kirby Thore). DK advised additional access proposed in 2008 may slip into 2009. (Refer to embedded Engineering Plan Update) DK to provide update once a more definitive proposal is available. Week 52 Paisley Gilmour St Re-roofing Project - Previously Week 4 Re-roofing Ayr Platforms 3 & 4 – includes crash deck installation – 54hrs As Week 51 (Refer to embedded Engineering Plan Update) Revisions to the possession strategy have now been proposed as a consequence of Version 1 responses and these will be discussed at the separate discussion when the outcome from the surveys are known. Timescales for completion of surveys have slipped slighty from January to February. (refer embedded Engineering Access Update for details) DK to provide update once a more definitive proposal is available. Annbank S&C (54hrs) Now cancelled – deferred to 2012/13 (Refer to embedded Engineering Plan Update) |  |  |
| 3 |  | Period C Week 01 Paisley Gilmour Street (Gourock Platforms 1 & 2 – Re-roofing/Re-glazing) Additonal 54hrs required in Weeks 1 & 2. Does not affect DRS services. Week 2 Paisley Gilmour Street (Gourock Platforms 1 & 2 – Re-roofing/Re-glazing) As Week 1. Week 02 – 04 (incl Easter 2009) Stirling Middle S&C Renewal incl Carmuirs West to East track renewals – 29hrs on Sunday 12/4/09 incl Larbert Up Goods Loop track renewals incl Auchterarder track renewals Greenhill Lower Jn to Dunblane (0035hrs Fri 10/4/09 to 0510hrs Mon 20/4/09) Combination of Plain line track renewals and Civils works. DK explained Stirling Middle will be the biggest S&C renewal in Scotland in 2009. DK shared the proposed layout plan and advised that the blockade required to be increased from 7 to 10 days following completion of the final design for the new layout. Week 02 – 04 (incl Easter 2009) (contd) Greenhill Lower Jn to Dunblane (0035hrs Fri 10/4/09 to 0510hrs Mon 20/4/09) – (contd) DRS to investigate if 4M30 can depart Elderslie or Mossend Down Yard (P D Stirling) instead of Grangemouth on Sunday of Week 3 when the Carmuirs track renewal is planned. (Grangemouth Terminal can be accessed for the rest of the 10 day blockade). DRS advised they would likely divert 4M30 to start from Mossend Down Yard (P D Stirling’s facility). DK indicated the new down line would be installed early in the programme and it may be possible of getting limited traffic through during the later stages of the work. However, this could not be determined for some time and the planning assumption should continue to be that the route is blocked for the full 10 days. DK confirmed other track renewals undertaken during the 10 day blockade which would result in very restricted access to Larbert ( if this location was required for reversing the Aberdeen and Inverness services to be re-routed via Fife) DRS to investigate alternative loading / unloading facilities for the Aberdeen and Inverness services for the period of the blockade. Ongoing DRS also to confirm status of Network Change. Ongoing DK advised that as a consequence of the overrun at Shields Junction at Christmas 2007, all renewal / remodelling works involving complex signalling design are currently being reviewed and Stirling Middle falls within this category. The renewal remains in the programme but there is still a risk of deferral. There are a few PLTR sites which are currently working under the cover of Stirling Middle S&C which will need to be revised if Stirling Middle is deferred. DK informed that the full 10 day possession will still be required as there are critical signalling works to be completed. AMcK suggested alternative options for DRS to consider - services to run at W7 over the Forth and Tay Bridges using megafrets ? AMacK highlighted that Stobart may provide smaller containers as it is for a more sustained period of 10days rather than a usual weekend block. SB to investigate if Stobart’s smaller containers are W7 or W8. Week 03 Paisley Gilmour St Re-roofing Project Ayr Platforms Plats 1 & 2 (54hrs) DK agreed the possession requirements would be reviewed at the end of January 2008 when surveys had been completed and a more definitive access strategy should be known. Ongoing. Week 03 Paisley Gilmour St Re-roofing Project (contd) Revisions to the possession strategy have now been proposed as a consequence of Version 1 responses and these will be discussed at the separate discussion when the outcome from the surveys are known. Timescales for completion of surveys have slipped slighty from January to February. (refer embedded Engineering Access Update for details) DRS to consider if the Kirby Thore to Elderslie traffic could be held at Kingmoor until Mon morn to facilitate this possession – as per the agreement for GARL Shields to Paisley Blocks. Agreed. DRS traffic to be held at Kingmoor. Week 04 Paisley Gilmour St Re-roofing Project Ayr Platforms Plats 1 & 2 (54hrs) as Week 3 Elderslie Up Loop (29hrs) No impact on DRS services Week 05 Carmuirs East Jn S&C (54hrs) DRS to investigate alternative loading / unloading facilities at Mossend or Coatbridge terminals. Action Complete. DRS will use alternative loading/unloading facilities at Mossend for 4S49 on Fri & 4M30 on Sun. DS requested clarification on published times in Section 7. PMcF agreed some anomalies had been printed and would rectify in Version 2 – 0645hrs finish published incorrectly. Week 06 Carmuirs East Jn S&C (78hrs) as week 05 DRS to investigate the option of running WH Malcolm services to Mossend and Eddie Stobart service to Coatbridge. DS requested clarification on published times in Section 7. PMcF agreed some anomalies had been printed and would rectify in Version 2 – 0645hr finish published incorrectly. (4S49 service on Tues passes 0515 at Carmuirs). DRS request for PMcF to amend possession time to finish at 0500 Tues in Week 6 only. Agreed. Week 07 Pilgrims Playing Field structure renewal (29hrs) DK confirmed possession limits Polmont Jn to c/o Grangemouth Jn and therefore no longer affects DRS traffic. Week 07 UB 132/021D Polmaise Jn structure renewal It will not now be possible to undertake structure works at same time as Stirling Middle S&C due to close proximity of sites. Previously in Week 3 (29hrs). Carmuirs East Jn S&C Follow-up Welding & Stressing (18hrs) DRS to investigate alternative loading terminal (at Mossend or Elderslie ?) for 4A11 1038hrs Grangemouth to Aberdeen service. Action Complete. DRS to use Mossend terminal. Week 08 Stirling Middle Jn S&C Follow-up Welding & Stressing (12hrs – 0030 to 1230) DRS to investigate alternative loading terminal (at Mossend or Elderslie ?) for 4A11 1038hrs Grangemouth to Aberdeen service. Week 08 Stirling Middle Jn S&C Follow-up Welding & Stressing (12hrs – 0030 to 1230) (contd) DRS agreed in principal to retime 4A11 service to depart Grangemouth later (for possession finishing at 1230hrs) and would no longer need to divert to Mossend. DS to confirm retiming will be acceptable |  |  |
| 4 |  | Period D1 Week 09 Stirling Middle Jn S&C Follow-up Welding & Stressing (12hrs – 0030 to 1230) DRS to investigate alternative loading terminal (at Mossend or Elderslie ?) for 4A66 0843hrs Grangemouth to Aberdeen service As Week 8. Carmuirs West Jn to Greenhill Lower Jn (Bonnymuir track renewal) 4M30 to be passed through possession over Up Line Week 10 Carmuirs West Jn to Greenhill Lower Jn (Bonnymuir track renewal) 4M30 to be passed through possession over Up Line Week 11 Carmuirs West Jn to Greenhill Lower Jn (Bonnymuir track renewal) 4M30 to be passed through possession over Up Line Week 12 No issues. Week 13 No issues. Week 14 No issues. Week 15 No issues. Week 16 No issues. |  |  |
| 5 |  | Period D2 Week 17 Mossend East S&C renewal (173hrs) Due to a reduction in the volumes of S&C units to be undertaken in 2009TTY – work has been deferred to 2010/11. (Refer to embedded Engineering Plan Update) Week 18 Mossend East S&C renewal (173hrs) As week 17 – Deferred to 2010/11. Week 19 Burnhouse track renewals (29hrs) DRS to investigate option of diverting 4M30 Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML ( NB: this is a diversion which has previously been planned for 4M30) or use Elderslie. Action Complete. DRS confirmed diversion of 4M30 Daventry traffic via Larbert / Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML. Week 20 Burnhouse track renewals (29hrs) As Week 19 Week 21 Mossend East Curve track renewal (29hrs) No route through Mossend. DRS to investigate option of diverting 4M30 Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML ( NB: this is a diversion which has previously been planned for 4M30) or use Elderslie. Action Complete. DRS confirmed diversion of 4M30 Daventry traffic via Larbert / Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML. UB132/084 B804 Main St Glenboig structure renewal (54hrs) Garnqueen – Cumbernauld blocked. Sighthill – Gartcosh blocked. DRS to investigate option of diverting 4S49 and 4M30 Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML ( NB: this is a diversion which has previously been planned for 4M30) or use Elderslie. Action Complete. DRS confirmed diversion of 4M30 Daventry traffic via Larbert / Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML. Week 22 Mossend East Curve track renewal (29hrs) No route through Mossend. DRS to investigate option of diverting 4M30 Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML ( NB: this is a diversion which has previously been planned for 4M30) or use Elderslie. Action Complete. DRS confirmed diversion of 4M30 Daventry traffic via Larbert / Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML. Lenziemill track renewal (Cumbernauld route) 29hrs DRS to investigate option of diverting 4M30 Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML ( NB: this is a diversion which has previously been planned for 4M30) or use Elderslie. Route via Stepps and Cowlairs blocked due to Cardowan Road structure renewal. Action Complete. DRS confirmed diversion of 4M30 Daventry traffic via Larbert / Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML. Cardowan Road, Stepps structure renewal (54hrs) Sighthill to Gartcosh Jn blocked. See above. Dumfries PLTR & S&C 29hrs requires to be increased to 54hrs due to methodologies. Does not affect DRS traffic. (Refer to embedded Engineering Plan Update) Week 23 Lenziemill track renewal (Cumbernauld route) 29hrs DRS to investigate option of diverting 4M30 Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route or via Stepps and Cowlairs DRS to confirm preferred route. Week 24 Cumbernauld route (Garnqueen North track renewal) 29hrs DRS to investigate option of diverting 4M30 Daventry traffic via Larbert/ Dalmeny/ Waverley/ Edinburgh Suburban route or via Stepps and Cowlairs DRS to confirm preferred route. Inverness to Elgin Allanfearn track renewal Deferred to 2010/11. 54hr access remains for Nairn S&C (Refer to embedded Engineering Plan Update) DK confirmed Grangemouth to Invernesss traffic via Highland Line will NOT be affected. |  |  |
| 6 |  | Period E Week 25 Inverness to Elgin Seafield track renewal Deferred to 2010/11. 54hrs access remains for Nairn S&C (Refer to embedded Engineering Plan Update). Does not currently affect DRS services. DK confirmed Grangemouth to Invernesss traffic via Highland Line will NOT be affected. Week 26 to 29 No issues Week 30 GARL - Shields Jn to Paisley (54hrs) Refer to embedded GARL Project Update. SB advised the Kirby Thore to Elderslie traffic could be held at Kingmoor until Mon morn to facilitate this possession. Agreed. DRS traffic to be held at Kingmoor. Week 31 GARL as Week 30 Week 32 GARL as Week 30 Week 33 GARL as Week 30 Perth – Inverness (54hrs) (Track, S&C, Civils and Platform renewals) Inverness service(s) affected on Saturday. Divert via Aberdeen. No impact on Aberdeen services. DRS to confirm diversion of Grangemouth/Inverness traffic via Elgin. Various sites have been deferred/cancelled: - Cradlehall (Up) track renewal Deferred to 2012/13. - Perth North (Up) track renewal 3no. 29hrs in weeks 33-35 now cancelled. - Kingussie No. 24 pts S&C 54hrs – Deferred to 2011/12. Stanley S&C No.24 points - Due to the replanning of work, this renewal has moved to Weeks 33 & 34 (2no. 54hrs). (Refer to embedded Engineering Plan Update) Week 34 GARL as Week 30 Perth – Inverness (54hrs) (Track, S&C, Civils and Platform renewals) Inverness service(s) affected on Saturday. Divert via Aberdeen. No impact on Aberdeen services. DRS to confirm diversion of Grangemouth/Inverness traffic via Elgin. Week 35 No issues Week 36 No issues. Week 37 No issues |  |  |

| 7 | AOB Glasgow Airport Rail Link (GARL) DK provided DRS with the project update for GARL (this was the same update provided at a recent meeting with First ScotRail). No further developments. Grangemouth Branch - Fouldubs loop extension Possessions expected in 2009. No further details at present. Disruptive Possession Briefing to W H Malcolm SB has a meeting with WH Malcolm w/c 28/01/08. SB to provide update on WH Malcom response/ concerns regarding continuing high levels of disruption to their important supermarket traffic for the foreseeable future. Next Meeting: Time: 1200-1500hrs Date: Tuesday, 18 March 2008 Room: Room 10 Venue: Buchanan House, Glasgow |
| --- | --- |