## Plan Linear
Week No | Hrs | Location | Discipline | Year | TDPU Ref | aiwp ref
37 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0605 | AA2
37 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0297 | I2
38 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0606 | AA3
38 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0511 | K3
38 | 29 | Millerhill Freddie 7 | Plain Line Worksite | 2007/08 | G0303 | I3
39 | 29 | Cowlairs East S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0309 | AC4
39 | 29 | Cowlairs West S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0307 | AC5
39 | 54 | Glasgow Central re-interlocking - All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0310 | AA4
39 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0305 | W4
39 | 20 | Monktonhall South | S&C Tamp Follow-up Tamp | 2007/08 | G0304 | U4
39 | 96 | Shields [Continues into week 40] | S&C Worksite | 2007/08 | G0308 | S4
40 | 54 | Glasgow Central re-interlocking- All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0316 | AA6
40 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0317 | W6
40 | 126 | Shields [Continued from week 39] | S&C Worksite | 2007/08 | G0315 | S6
40 | 29 | Newbridge Jn (A-B Project) | 3rd Party Schemes | 2007/08 | NEW | E6
41 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0608 | AA7
41 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0318 | W7
41 | 102 | Shields | S&C Worksite | 2007/08 | G0321 | S7
41 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0516 | M7
41 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0322 | K7
41 | 29 | Dundee Plat 1 (Up M) | Plain Line Worksite | 2007/08 | G0319 | I7
42 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0609 | AA8
42 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0327 | W8
42 | 78 | Shields | S&C Worksite | 2007/08 | G0325 | S8
42 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0517 | M8
42 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0326 | K8
42 | 29 | Dundee (Up L) | Plain Line Worksite | 2007/08 | G0328 | I8
43 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0611 | AA9
43 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0333 | W9
43 | 54 | Shields | S&C Worksite | 2007/08 | G0334 | S9
43 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | O9
43 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0610 | M9
43 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0330 | K9
43 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0331 | I9
44 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0612 | AA10
44 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0341 | W10
44 | 54 | Shields | S&C Worksite | 2007/08 | G0339 | S10
44 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | NEW | M10
44 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0338 | K10
44 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0340 | I10
45 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0345 | AA11
45 | 29 | Lagganstarroch | Structures Renewals 2 | 2007/08 | G0344 | Y11
45 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0342 | W11
45 | 51 | Slateford | S&C Worksite | 2007/08 | G0347 | S11
45 | 29 | Gorton (Rev) | Plain Line Worksite | 2007/08 | G0522 | O11
45 | 29 | Glenury (Dn) | Plain Line Worksite | 2007/08 | G0521 | M11
45 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0346 | K11
45 | 29 | Uddingston (Dn) | Plain Line Worksite | 2007/08 | G0388 | I11
46 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0352 | AA12
46 | 29 | Lagganstarroch | Structures Renewals 1 | 2007/08 | G0349 | W12
46 | 29 | Slateford | S&C Worksite | 2007/08 | G0351 | S12
46 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O12
46 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | M12
46 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | NEW | K12
46 | 29 | Dimsdale (Up) | Plain Line Worksite | 2007/08 | G0389 | I12
47 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0357 | AA13
47 | 54 | Kingskettle | Structures Renewals 1 | 2007/08 | G0355 | W13
47 | 54 | Shields Follow-up Tamp | S&C Tamp Follow-up Tamp | 2007/08 | G0358 | U13
47 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S13
47 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | M13
47 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0350 | K13
47 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0359 | I13
48 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0361 | AA14
48 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S14
48 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O14
48 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0513 | M14
48 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0354 | K14
48 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0360 | I14
49 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0366 | AA15
49 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S15
49 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0368 | M15
49 | 29 | Forthar (Up) | Plain Line Worksite | 2007/08 | G0363 | K15
49 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0367 | I15
50 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0371 | AA16
50 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S16
50 | 29 | Newton-on-Ayr (Dn) | Plain Line Worksite | 2007/08 | G0530 | M16
50 | 29 | Plean (Up) | Plain Line Worksite | 2007/08 | G0373 | K16
50 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0369 | I16
51 | 12 | Newton-on-Ayr S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0378 | AC17
51 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0372 | AA17
51 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S17
51 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | NEW | M17
51 | 43 | Auchencastle (Up) | Plain Line Worksite | 2007/08 | G0547 | K17
51 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0377 | I17
52 | 12 | Kilwinning Jn S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0381 | AC18
52 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0382 | AA18
52 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S18
52 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | G0383 | K18
52 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0380 | I18
1 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA20
1 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W20
1 | 54 | Stirling Middle | S&C Worksite | 2008/09 | new | S20
2 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA21
2 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W21
2 | 29 | Stirling Middle | S&C Worksite | 2008/09 | new | S21
3 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA22
3 | 54 | Larbert | S&C Worksite | 2008/09 | new | S22
4 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA23
4 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S23
5 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA24
5 | 78 | Falkland Yard | S&C Worksite | 2008/09 | new | S24
6 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA25
6 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S25
7 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA26
7 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S26
8 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA27
8 | 29 | Stirling Middle FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U27
9 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA28
10 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA29
11 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA30
12 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA31
12 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S31
13 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA32
13 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S32
14 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA33
14 | 78 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S33
15 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA34
15 | 54 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S34
16 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA35
16 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W35
16 | 78 | New Cumnock | S&C Worksite | 2008/09 | new | S35
16 | 168 | Ballochmyle (Up) | Plain Line Worksite | 2008/09 | new | I35
16 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G35
17 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA36
17 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W36
17 | 29 | New Cumnock | S&C Worksite | 2008/09 | new | S36
17 | 168 | Mauchline (Dn) | Plain Line Worksite | 2008/09 | new | I36
17 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G36
18 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA37
18 | 54 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W37
18 | 54 | Gartcosh | S&C Worksite | 2008/09 | new | S37
19 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA38
19 | 12 | Halbeath FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U38
19 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S38
20 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA39
20 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S39
21 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA40
21 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U40
22 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA41
22 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U41
23 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA42
23 | 12 | New Cumnock FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U42
24 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA43
24 | 51 | Monktonhall South (Up) | Plain Line Worksite | 2008/09 | new | I43
25 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA44
25 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I44
26 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA45
26 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W45
26 | 12 | Gartcosh FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U45
26 | 78 | Whifflet North | S&C Worksite | 2008/09 | new | S45
26 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I45
27 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA46
27 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W46
27 | 29 | Whifflet North | S&C Worksite | 2008/09 | new | S46
27 | 51 | Ninewar (Dn) | Plain Line Worksite | 2008/09 | new | K46
27 | 51 | Lemington (Up) | Plain Line Worksite | 2008/09 | new | I46
28 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA47
28 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W47
28 | 51 | Oxwellmains (Dn) | Plain Line Worksite | 2008/09 | new | I47
29 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA48
29 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W48
29 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S48
29 | 51 | Houndwood (Dn) | Plain Line Worksite | 2008/09 | new | I48
30 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA49
30 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W49
30 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S49
30 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I49
31 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA50
31 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W50
31 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S50
31 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I50
32 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA51
33 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA52
33 | 12 | Whifflet North FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U52
34 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA53
34 | 54 | Markinch | S&C Worksite | 2008/09 | new | S53
35 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA54
35 | 54 | Markinch | S&C Worksite | 2008/09 | new | S54
36 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA55
FY37 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA56
FY37 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S56
FY38 | 48 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA57
FY38 | 120 | Carmuirs East | S&C Worksite | 2008/09 | new | S57
FY39 | 77 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA58
FY39 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S58
FY40 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S59
FY41 | 12 | Markinch FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U60
FY41 | 54 | Cadder | S&C Worksite | 2008/09 | new | S60
FY44 | 54 | Beattock | S&C Worksite | 2008/09 | new | S63
FY44 | 43 | Ecclefechan (Dn) | Plain Line Worksite | 2008/09 | new | I63
FY45 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S64
FY45 | 43 | Fullwood (Dn) | Plain Line Worksite | 2008/09 | new | I64
FY46 | 12 | Carmuirs East FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U65
FY46 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S65
FY46 | 29 | Garriongill (Dn) | Plain Line Worksite | 2008/09 | new | I65
FY47 | 29 | Beattock Summit | S&C Worksite | 2008/09 | new | S66
FY47 | 29 | Garriongill (Up) | Plain Line Worksite | 2008/09 | new | I66
FY48 | 78 | Hilton Jn | S&C Worksite | 2008/09 | new | S67
FY48 | 29 | Rutherglen (Up Slow) | Plain Line Worksite | 2008/09 | new | I67
FY49 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W68
FY49 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S68
FY49 | 29 | Rutherglen Old Station (Up Slow) | Plain Line Worksite | 2008/09 | new | I68
FY50 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W69
FY50 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S69
FY50 | 29 | Shawfield (Up Slow) | Plain Line Worksite | 2008/09 | new | I69
FY51 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W70
FY51 | 54 | Hilton Jn - Ladybank Branch only | S&C Worksite | 2008/09 | new | S70

## Plan AIP
FISCAL YEAR | TT YEAR | Week No | Key Events/ Dates |  | Sleeper Services ECML / Internal Diversions | DRS internal services - network availability | Hrs | Enhancement Projects | Hrs | Enhancement Projects | Hrs | Enhancement / Estates Projects | Hrs | Enhancement / Estates Projects |  | Hrs | Enhancement / Estates Projects |  | Hrs | Plain Line Renewal |  | Hrs | Plain Line Renewal | Hrs | Plain Line Renewal | Hrs | Plain Line Renewal/ Drainage | Hrs | Slab Track Renewal |  | Hrs | S&C Renewals | Hrs | S&C Renewals | Hrs | Civils Renewals 1 | Hrs | Civils Renewals 2 | Hrs | Civils Renewals 3 | Hrs | OHL/Signalling Renewals / Civils Renewals 4 | Hrs | S&C Tamping / OLE / Heavy Maintenance
2008/09 (2009 TTY) | PERIOD A
|  | 38 |  |  |  | All routes available | [13 empty] | [All 28hrs Carstairs to Haymarket East times are 0650 Sat to 1050 Sun] | [20 empty] | 7 | Glas Cen Interlocking - extended midwk [2210-0500 : Zone 3] | 12 | Niddrie West/ South Jn S&C Tamp (Maint) [0001 Sun to 1201 Sun - ROTR + 2hrs]
|  | 39 |  | Christmas DayThur 25/12/08 |  | Diverted via Sirling to Alloa & Fife ? | 48 | Edinburgh Tram (tie) - c/o Haymarket Cen Jn to Edin Park/ Saughton (All Lines) [Thur 25/12/08 & Fri 26/12/08] | 54 | A2B Project - Newbridge Jn [Thur 25/12/08 & Fri 26/12/08] | [8 empty] | 29 | Princes St Gdns (Line X - only Z available) [Thur 25/12/08] | [10 empty] | 100 (Mn) 184 (Bch) | Hilton Jn [Dunblane to Perth - Mainlines 0130 Thur 25/12/08 to 0510 Mon 29/12/08 then 0001 to 1800 Thur 1/1/09 ; Ladybank Branch 0130 Thur 25/12/08 to 1800 Thur 1/1/09] [DRS services 4A66 & 4N83 to be diverted via Stirling-Alloa & Tay Bridge] | [8 empty] | 125 | Glasgow Central Interlocking - ALB [0030 Thur 25/12/08 to 0500 Tue 30/12/08] (Extent of signalling restrictions within Control Area under discussion)
|  | 40 |  | New Year's Day Thu 1/1/09 | I'ness via A'deen, Glasgow via Falkirk G'ston & All via ECML Sun night [28/12/08] | Diverted via Sirling to Alloa & Fife ? | 29 | Edinburgh Tram (tie) - c/o Haymarket Cen Jn to Edin Park/ Saughton (All Lines) [Thur 1/1/09] | 29 | A2B Project - Newbridge Jn [Thur 1/1/09] | 54 | Newton Old Signal Box (Demolition) [Thur 1/01/09 & Fri 2/01/09] - Estates | [6 empty] | 9.5 | Law (Dn) [Lanark Jn - Law Sth Jn] [extended ROTR] [2345 Sat 27/12/08 to 0915 Sun 28/12/08] |  | 54 | Jeanfield (Up) [0001 Sat 27/12/08 to 0510 Mon 29/12/08] |  |  | 78 | Dubbs Jn (Largs Branch) - linked with S&C renewal [0001 Thur 1/01/09 to 0600 Sun 4/1/09] | [5 empty] | 78 | Dubbs Jn (Largs Branch) [0001 Thur 1/01/09 to 0600 Sun 4/1/09] [M] - Kilwinning Plat 2 not available electrically
|  | 41 |  |  |  | Dundee to Aberdeen Blocked | [12 empty] | 28 | Law (Dn) [Lanark Jn - Law Sth Jn] (2345 Sat to 0430 Mon) | Dundee to Aberdeen Blocked | 54 | Laurencekirk (Dn) [MOBC] | 54 | Aberdeen (Dn Goods Lp - Clayhills) [NO access to Clayhills Depot & Plats 4 & 5 to be clear]
|  | 42 |  |  |  | Dundee to Aberdeen Blocked | [9 empty] | 54 | Paisley Gil St : Re-roofing (Gourock Plats 1 & 2) [subject to further consultation] |  | 28 | Fullwood (Dn) [Lanark Jn - Law Sth Jn] (2345 Sat to 0430 Mon) |  | 54 | Laurencekirk (Dn)
|  | 43 |  |  |  | Dundee to Aberdeen Blocked | [12 empty] | 28 | Fullwood (Dn) [Lanark Jn - Law Sth Jn] (2345 Sat to 0430 Mon) |  | 54 | Marywell (Dn) [Drainage] | 54 | Stannergate (Dn) | [5 empty] | 54 | Halbeath [M] (under review) |  |  | 54 | Kirkton of Craig YD093 [Devegetation] (Dn)
|  | 44 |  |  |  | Dundee to Aberdeen Blocked | [12 empty] | 28 | Fullwood (Dn) [Lanark Jn - Law Sth Jn] (2345 Sat to 0430 Mon) |  | 54 | East Haven (Dn) [MOBC] | [7 empty] | 54 | Halbeath [M] (under review) |  |  | 54 | Kirkton of Craig YD093 [Devegetation] (Dn)
| PERIOD B | 45 |  |  | Aberdeen Sleeper via Perth & Stirling | All routes available |  |  |  |  | 54 | Barrhead - Kilmarnock Route Enhancements | [5 empty] | Period B Block - Cove to Lockerbie (Weeks 48 & 52 to be STP'd to 1130hrs Sat ) - Cannot STP to 1130hrs in Week 47 due to LNW 43hr possession | 43 | Ecclefechan (Dn) [Cove-Lockerbie] [0530 Sat to 0020 Mon] |  | 29 | Niddrie (Dn) | 54 | Coaltown of Balgonie (Dn) [Thornton Nth to Markinch] - Rerail | [9 empty] | 54 | UB90/111 Slaughterhouse Rd, Markinch | 54 | Tay Bridge |  |  |  |  | 12 | Ladybank S&C Tamp (Maint) [0050 Sat to 1250 Sat]
|  | 46 |  |  |  | All routes available |  |  |  |  | 54 | Barrhead - Kilmarnock Route Enhancements |  |  |  | 54 | Paisley Gil St : Re-roofing (Gourock Plats 1 & 2) [subject to further consultation] |  | 43 | Ecclefechan (Dn) [Cove-Lockerbie] [0530 Sat to 0020 Mon] |  | 29 | Niddrie (Dn) | 54 | Glenfoot (Ladybank Jn - Hilton Jn) | [9 empty] | 54 | UB90/131 Nabs Rd, Kingskettle | 54 | UB90/130 Station Rd, Kingskettle | 54 | Tay Bridge |  |  | 12 | Thornton North/ South S&C Tamp (Maint) [0035 to 1235 Sun - to be c/o South Jn by 1030 Sun]
|  | 47 |  |  |  | Diverted via Sirling to Alloa & Fife ? | [12 empty] | 29 | Lochwinnoch (Dn) [MOBC] |  | 29 | Ninewells (Dn) [Perth to Dundee] | 29 | Auchterarder (Up)
|  | 48 |  |  | Edinburgh Sleeper via Falkirk Grahamston | Diverted via Sirling to Alloa & Fife ? | [12 empty] | 51 | Dolphinston (Rev/Fast) [Carstairs So. Jn/ Carstairs Station to Carstairs E. Jn] [no access towards Midcalder Jn and only Carstairs Plat 1 available] |  | 29 | Lochwinnoch (Dn) [MOBC] | 29 | Ninewells (Dn) [Perth to Dundee] | [5 empty] | 51 | Curriehill (Hmkt East-Midcalder Jn) [removal of crossover] [0130 Sat to 0520 Mon]
|  | 49 |  |  |  | All routes available | [12 empty] | 28 | Carstairs to Midcalder Jn (Mosshat - Dn) |  | 29 | Glengarnock (Dn) | 29 | Lochwinnoch (Dn) [MOBC] | [5 empty] | 43 | Kirtlebridge - Up (Cove-Lockerbie) [xover out of use Mon wk 49 to Sun wk 51] [M] [0530 Sat to 0020 Mon] |  |  | 396 | Strathcarron to Kyle [Earthworks] [1745 Fri 6/3/09 to 0615 Mon 23/3/09] | [6 empty] | 12 | Kilwinning Jn S&C Tamp ( Maint) [0005 Sun to 1200 Sun]
|  | 50 |  |  |  | All routes available | [12 empty] | 28 | Carstairs to Midcalder Jn (Mosshat - Dn) |  | 29 | Lochwinnoch (Dn) | [7 empty] | 43 | Kirtlebridge - Dn (Cove-Lockerbie) [xover out of use Mon wk 49 to Sun wk 51] [M] [0530 Sat to 0020 Mon]
|  | 51 |  |  |  | All routes available | 16 | A2B Project - Winchburgh Jn to Newbridge Jn [OB070/12 Bridge Demolition] | [7 empty] | 54 | Paisley Gil St : Re-roofing (Ayr Plats 3 & 4) [subject to further consultation] |  | 28 | Carstairs to Midcalder Jn (Mosshat - Dn: drainage) |  | 29 | Lochwinnoch (Dn) | [7 empty] | 43 | Kirtlebridge - Dn (Cove-Lockerbie) [xover out of use Mon wk 49 to Sun wk 51] [M] [0530 Sat to 0020 Mon]
|  | 52 |  |  |  | All routes available | 16 | A2B Project - Newbridge Jn to Haymarket West Jn [OB070/07 Bridge Demolition] | [7 empty] | 54 | Paisley Gil St : Re-roofing (Ayr Plats 3 & 4) [subject to further consultation] |  | 28 | Carstairs to Midcalder Jn (Mosshat - Dn : drainage) |  | 29 | Lochwinnoch (Dn)
2009/10 (2009 TTY) | PERIOD C | 1 |  |  | Glasgow Sleeper via Cathcart Circle (Sun) | All routes available |  |  | 54 | Eglinton St Jn to Eglinton St Tunnel (M74 Extension) | [5 empty] | 54 | Paisley Gil St : Re-roofing (Gourock Plats 1 & 2) [subject to further consultation] | Period C Block - Lockerbie to Carstairs [0530hrs Sat to 0020hrs Mon] | 54 | Gushetfaulds (Up Slow) [ALB - access to Polmadie CSD only available from Shawfield end] (12 trains) | Period C Block - Carstairs to Midcalder Jn [0650hrs Sat to 1050hrs Sun] | 28 | Carstairs - Midcalder Jn [Cobbinshaw - Dn] (10 trains) | [7 empty] | 54 | Rutherglen - Glasgow Cen (Larkfield Jn 927a/b) [ALB - access to Polmadie CSD only available from Shawfield end] [M] |  |  | 174 | Glenfinnan to Mallaig (E) [0001 Sat 28/3/09 to 0630 Sat 4/4/09] | [6 empty] | 12 | Lesmahagow Jn S&C Maint Tamp (Law Jn - Uddingston) [0020 Sun to 1220 Sun - ROTR + 3hr 20 min]
|  | 2 |  |  | Inverness Sleeper via Ladybank (Fri night) and Glasgow Sleeper via Cathcart Circle (Sun) | Temporary transfer to Mossend/ Elderslie ? and diverted via Forth Bridge ? | 389 | Gourock Interchange Project (0100 Sat 4/4/09 to 0530 Mon 20/4/09) Ev1 | 54 | Eglinton St Jn to Eglinton St Tunnel (M74 Extension) | [5 empty] | 54 | Paisley Gil St : Re-roofing (Gourock Plats 1 & 2) [subject to further consultation] |  | 54 | Gushetfaulds (Dn Slow) [ALB - access to Polmadie CSD only available from Shawfield end] (8 trains) |  | 28 | Carstairs - Midcalder Jn [Cobbinshaw - Dn] (8 trains) | [7 empty] | 54 | Rutherglen - Glasgow Cen (Larkfield Jn 927a/b) [ALB - access to Polmadie CSD only available from Shawfield end] [Follow-up] | 244 | Stirling Middle 18, 20A/B, 22A/B, 32A/B, 35, 56, 72 (0035 Fri 10/04/09 to 0510 Mon 20/04/09) (24 trains between Fri/ Sat/ Sun)
|  | 3 | Easter |  | Inverness Sleeper via Ladybank then All via ECML Sun night | Temporary transfer to Mossend/ Elderslie ? and diverted via Forth Bridge ? Also hold Kirby Thore service at Kingmoor until Mon morn |  |  | 22 | Dalmuir Station New Overbridge - ALB "Acess For All" Project [0040hrs to 2240hrs Sun] | [11 empty] | 28 | Carstairs to Midcalder Jn (Harburn - Up) (7 trains) | 29 | Carmuirs West to East (Up) [Greenhill Lower and Carmuirs East Jn to Larbert Jn blocked] [0001 Sun to 0600 Mon] (3 trains) | [11 empty] | 54 | UB 058/079 Whitely's Burn [Balloch Branch]
|  | 4 |  |  | Ft William Sleeper diverted to Oban (Mon & Tues) | Temporary transfer to Mossend/ Elderslie ? and diverted via Forth Bridge ? Also hold Kirby Thore service at Kingmoor until Mon morn | [9 empty] | 29 | Cambuslang (Platforms renewal) [0005hrs Sun to 0425hrs Mon] (access requirements still under review) |  | 43 | Lockerbie - Carstairs So.Jn [Wamphray - Dn] (7 trains) |  | 28 | Carstairs to Midcalder Jn (Harburn - Up) (7 trains) | 29 | Carmuirs West to East (Up) [Greenhill Lower and Carmuirs East Jn to Larbert Jn blocked] [0001 Sun to xxxx Mon] (4 trains) | [9 empty] | 105 | Crianlarich to Fort William (S) incl UB310/306 Tulloch Viaduct [2210hrs Fri 17/4/09 until 0730hrs Wed 22/04/09]
|  | 5 |  |  | Ft William Sleeper diverted to Oban (Sun to Tues) | Temporary transfer to Mossend/ Coatbridge ? | [9 empty] | 29 | Cambuslang (Platforms renewal) [0005hrs Sun to 0425hrs Mon] (access requirements still under review) |  | 43 | Lockerbie - Carstairs So.Jn [Wamphray - Dn] (9 trains) |  | 28 | Carstairs to Midcalder Jn (Wilsontown - Up) (5 trains) | [7 empty] | 54 | Carmuirs East Jn 4A/B, 12A/B, 22A/B [Carmuirs West Jn to Larbert Jn available] (0045 Sat to 0445 Mon) (7 trains) |  |  | 105 | Crianlarich to Fort William (S) incl UB310/306 Tulloch Viaduct [2210hrs Fri 24/4/09 until 0730hrs Wed 29/04/09]
|  | 6 | May Day |  | Inverness via Ladybank then All via ECML Sun night | Temporary transfer to Mossend/ Coatbridge ? | [9 empty] | 29 | Cambuslang (Platforms renewal) [0005hrs Sun to 0425hrs Mon] (access requirements still under review) |  | 43 | Lockerbie - Carstairs So.Jn [Dalmakether - Up] (17 trains) |  | 28 | Carstairs to Midcalder Jn (Girwoodend - Up) (7 trains) | [7 empty] | 78 | Carmuirs East Jn 4A/B, 12A/B, 22A/B [Carmuirs West Jn to Larbert Jn available] (0045 Sat to 0530 Tue) (7 trains)
|  | 7 |  |  |  | Diverted 4A11 to/ from Elderslie/Coatbridge ? | [9 empty] | 29 | Cambuslang (Platforms renewal) [0005hrs Sun to 0425hrs Mon] (access requirements still under review) |  | 43 | Lockerbie - Carstairs So.Jn [Perchall Dn] (15 trains) |  | 28 | Midcalder Jn to Haymarket East Jn [Camps - Dn] (8 trains) |  |  | 28 | Carstairs to Midcalder Jn (Harburn - Up) | [5 empty] | 18 | Carmuirs East Jn [Welding & Stressing] | 29 | UB076/008 Pilgrims Playing Fields, Falkirk [Polmont Jn to c/o Grangemouth Jn] | 29 | UB132/021D Polmaise Jn [Plean to Stirling]
| PERIOD D1 | 8 |  |  |  | All routes available | [12 empty] | 29 | Auchterarder (Dn) |  | 29 | Larbert Up Goods Loop | [9 empty] | 29 | Stirling Middle [Welding & Stressing] (Mainlines 0030 to 1230hrs. S&D Lines, Plats 6 & 9 and Up Loop extended to 1630hrs) | 29 | UB113/024 Stream Thornton [Redford Jn to Thornton West Jn]
|  | 9 | Spring BH |  | All via ECML Sun night | Route available (4M30 to be passed site) | [12 empty] | 29 | Bonnymuir (Dn) [4M30 2224 G'mouth to Daventry to be passed over the Up Line @ 2300hrs] |  | 29 | Dunfermline Town (Up) | [11 empty] | 29 | UB285/104 Blackhill (Shotts to Addiewell) |  | No other civils works on west side of Fife Circle compatible with Dunfermline track renewal
|  | 10 |  |  | Aberdeen via Stirling & All via ECML Sun night | Route available (4M30 to be passed site) | [12 empty] | 29 | Bonnymuir (Dn) [4M30 2224 G'mouth to Daventry to be passed over the Up Line @ 2300hrs] |  | 29 | Turnhouse (Up) [Passenger services to use Dalmeny Plat 2 from N.Queensferry end] | [7 empty] | 8 | Carmuirs East Jn [Follow-up Tamp] [ROTR] |  |  | 29 | UB285/94 Handaxwood (Shotts to Addiewell) (under review) | 54 | UB105/002 River Ore [Thornton North Jn to Cameron Bridge - Methil Branch] | 54 | UB105/003 River Leven [Thornton North Jn to Cameron Bridge - Methil Branch]
|  | 11 |  |  | Aberdeen via Stirling & All via ECML Sun night | Route available (4M30 to be passed site) | [12 empty] | 29 | Bonnymuir (Dn) [4M30 2224 G'mouth to Daventry to be passed over the Up Line @ 2300hrs] |  | 29 | Turnhouse (Up) [Passenger services to use Dalmeny Plat 2 from N.Queensferry end] | [7 empty] | 8 | Carmuirs East Jn [Follow-up Tamp] [ROTR] |  |  | 29 | UB285/94 Handaxwood (Shotts to Addiewell) (under review) | [6 empty] | 12 | Hyndland East Jn S&C Tamp ( Maint) [0025 Sun to 1225 Sun - ROTR + 5hr 5 min]
|  | 12 |  | Shotts Miners [Week 12 or 13 tbc] | Aberdeen via Dunfermline & All via ECML Sun night | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | [10 empty] | 29 | Cowlairs (Up) [c/o Cowlairs So. Jn-Bishopbriggs] - No access to Eastfield Depot |  | 29 | Kinghorn (Up) | [11 empty] | 29 | UB090/088 Den Footpath [Kirkcaldy to Thornton South Jn] | 29 | UB090/087A Dunnikier Subway [Kirkcaldy to Thornton South Jn]
|  | 13 |  |  | Aberdeen via Dunfermline & All via ECML Sun night | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | [10 empty] | 29 | Cowlairs (Up) [c/o Cowlairs So. Jn-Bishopbriggs] - No access to Eastfield Depot |  | 29 | Kinghorn (Up) | [11 empty] | 29 | UB090/088 Den Footpath [Kirkcaldy to Thornton South Jn] | 29 | UB090/087A Dunnikier Subway [Kirkcaldy to Thornton South Jn] |  |  |  |  | 8.5 | Larbert Jn S&C Tamp (Maint) [0030 to 0900 Sun - ROTR reduced by 45min]
|  | 14 |  |  | Aberdeen via Dunfermline & All via ECML Sun night | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] |  |  | 29 | Barrhead - Kilmarnock Route Enhancement | [6 empty] | 29 | Waverley Plat 7 (formerly Plat 10) | [14 empty] | 29 | Aberdour YD235a (E) | 54 | UB072/009 Queensferry Road (Winchburgh to Dalmeny) | 54 | UB072/001 Beatlie (Winchburgh to Dalmeny) |  |  | 9 | Cowlairs East Jn S&C Tamp (Maint) [0300 Sun to 1200 Sun]
|  | 15 | Edinburgh Trades |  | Aberdeen Sleeper via Stirling (Sat morn & Sun night) | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | Edinburgh Tram (tie) - Saughton to Dalmeny [not permitted to restrict engineering train movements] | 29 | Barrhead - Kilmarnock Route Enhancement | [6 empty] | 29 | Waverley South Loop (links to Plat 10) |  | 29 | Levenseat (Up) (Shotts to Addiewell) | 54 | Birdsmill (Dn) [Bathgate Branch] |  |  |  |  | School Holiday Period - Weeks 15 to 21 incl | 54 | North Queensferry 301A/B, 302A/B [0030 Sat to 0440 Mon] [M] [Crossovers o/o/u until Mon 13/7/09] |  |  | 54 | Forth Bridge [not permitted to restrict engineering train movements] | 29 | UB072/009 Queensferry Road (Winchburgh to Dalmeny) | 29 | UB072/001 Beatlie (Winchburgh to Dalmeny) |  |  | 10 | Carmuirs West Jn S&C Tamp (Maint) [0030 Sun to 1030 Sun - ROTR + 2hrs 45min]
|  | 16 |  | Open Golf Turnberry Mon 13/7 to Sun 19/07/09 | Aberdeen Sleeper via Stirling (Sat morn & Sun night) | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | Edinburgh Tram (tie) - Saughton to Dalmeny [not permitted to restrict engineering train movements] | 29 | Barrhead - Kilmarnock Route Enhancement | [6 empty] | 29 | Sighthill East (Dn) |  | 29 | Haymarket Plat 1 (Up) - North Lines | [7 empty] | 54 | North Queensferry 301A/B, 302A/B [0030 Sat to 0440 Mon] [M] [Crossovers o/o/u until Mon 13/7/09] |  |  | 54 | Forth Bridge [not permitted to restrict engineering train movements]
| PERIOD D2 | 17 | Glasgow Fair |  | Aberdeen Sleeper via Stirling (Sat morn & Sun night) | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate | 54 | Edinburgh Tram (tie) - Saughton to Dalmeny [not permitted to restrict engineering train movements] | 29 | Barrhead - Kilmarnock Route Enhancement | [6 empty] | 29 | Sighthill East (Dn) |  | 29 | Haymarket Plat 1 (Up) - North Lines | 54 | Dalrymple Jn (Chalmerston Branch only) [midweek] | [5 empty] | 125 | Langloan Jn 75A/B, 76, 77A/B/C, 78 [0001 Sat 18/07/09 to 0455 Thur 23/7/09 ] [M] |  |  | 54 | UB090/032 Cemetery Road, Inverkeithing [North Queensferry Tunnel to Inverkeithing Tunnel] | 54 | North Queensferry YU & YD 253 (E) [North Queensferry Tunnel to Inverkeithing Tunnel] | 54 | Forth Bridge [not permitted to restrict engineering train movements] |  |  | 9 | Gartcosh Jn S&C Tamp (Maint) [0045 Sun to 0945 Sun - ROTR + 1hr 30 min]
|  | 18 |  |  | Aberdeen via Stirling & All via ECML Sun night | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate | 29 | Edinburgh Tram (tie) - Saughton to Dalmeny [not permitted to restrict engineering train movements] | 29 | Barrhead - Kilmarnock Route Enhancement | [6 empty] | 29 | Dalmeny (Up) |  | 29 | Longannet [midweek] | [11 empty] | 54 | UB207/029 Cattle Creep Tannoch Hill (Annbank to Mauchline) | 29 | North Queensferry YU & YD 253 (E) [North Queensferry Tunnel to Inverkeithing Tunnel] | 29 | Forth Bridge [not permitted to restrict engineering train movements] |  |  | 12 | Sighthill East & West Jns S&C Tamp (Maint) [0050 Sun to 1250 Sun - ROTR + 4hr 35 min]
|  | 19 | Edinburgh Festival 1/08/08 to 6/09/09 |  | All via ECML Sun night | Divert 4M30 via Dalmeny & Edin Sub then WCML ? | 54 | A2B Project - Newbridge Jn to Bathgate | [10 empty] | 54 | Cosshogle (Up) [Kirkconnel to Thornhill] |  | 29 | Burnhouse (Up) [no access to Mossend] | [11 empty] | 54 | UB161/191 Carsencan Cattle Creep (Thornhill) | [6 empty] | 10 | Cowlairs West Jn S&C Tamp (Maint) [0055 Sun to 1055 Sun - ROTR + 3hr 10 min]
|  | 20 |  |  | All via ECML Sun night | Divert 4M30 via Dalmeny & Edin Sub then WCML ? | 54 | A2B Project - Newbridge Jn to Bathgate | [10 empty] | 54 | Carronbridge (Up) [Kirkconnel to Thornhill] |  | 29 | Burnhouse (Up) [no access to Mossend] | [11 empty] | 54 | UB161/308 Wath Burn (Dumfries to Annan)
|  | 21 |  |  | All via ECML Sun night | Divert 4M30 via Dalmeny & Edin Sub then WCML ? | [12 empty] | 29 | Carronbridge (Up) [Kirkconnel to Thornhill] |  | 29 | Dumfries South (Up) [linked to S&C] | 29 | Mossend East Curve (Up) [All Jcns Blocked - North, East , South , West] | [5 empty] | 54 | Dumfries [KA. KB, F] |  |  | 29 | UB161/308 Wath Burn (Dumfries to Annan) | 54 | UB132/084 B804 Main St, Glenboig [Gartsherrie So.Jn-Garnqueen Nth Jn - Cumbernauld route blocked]
|  | 22 |  |  | All via ECML Sun night | Divert 4M30 via Dalmeny & Edin Sub then WCML ? | [12 empty] | 29 | Lenziemill (Dn) [Garnqueen Nth-Cumbernauld] |  | 29 | Dumfries South (Up) [linked to S&C] | 29 | Mossend East Curve (Up) [All Jcns Blocked - North, East , South , West] | [5 empty] | 54 | Dumfries [KA. KB, F] |  |  |  |  | 54 | Cardowan Rd, Stepps (Bridgeguard 3) [Sighthill to Gartcosh Jn]
|  | 23 |  | August BH (England) |  | Divert 4M30 via Stepps & Cowlairs ? | [12 empty] | 29 | Lenziemill (Dn) [Garnqueen Nth-Cumbernauld]
|  | 24 |  |  |  | Divert 4M30 via Stepps & Cowlairs ? | [12 empty] | 54 | Nairn |  | 29 | Garnqueen North (Up) [Gartsherrie So.Jn-Garnqueen Nth] - Route via Gartsherrie So.Jn to Gartcosh Jn will be available |  |  |  |  | 29 | Finnieston Tunnel and High Street Tunnel 1 & 2 | [5 empty] | 54 | UB291/061 Findhorn Viaduct [Forres to Nairn]
| PERIOD E | 25 | First ScotRail services diverted via Shotts |  | Ft William Sleeper via Shotts | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 54 | Paisley Gil St : Re-roofing (Gourock Plats 1 & 2) [subject to further consultation] |  |  |  |  | 29 | Kilmaurs |  | 29 | Wishaw Central (Dn) |  |  |  |  | 29 | High Street |  | 54 | Nairn No.101 & 103 pts |  |  | 54 | UB291/061 Findhorn Viaduct [Forres to Nairn] | 54 | YU034 Huntly (Devegetation) [Huntly to Keith] ?? |  |  |  |  | 8 | Greenhill Lower Jn S&C Tamp (Maint) [0015 to 0815hrs - ROTR + 20 min]
|  | 26 |  |  | Ft William Sleeper via Shotts | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 54 | Paisley Gil St : Re-roofing (Gourock Plats 1 & 2) [subject to further consultation] |  | 29 | Dyce (Platforms) |  | 29 | Stoneywood [Aberdeen -Dyce] |  | 29 | Kilmaurs | 29 | Wishaw Central (Dn) |  |  | 29 | Charing Cross |  | 54 | Huntly No.7pts |  |  | 54 | OB294/ 070 Tarmore Rd, Keith [Elgin-Huntly]
|  | 27 |  |  | Ft William Sleeper via Shotts | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 54 | Stranraer Station Redevelopment [target completion Sept 09] |  | 29 | Barrhead - Kilmarnock Route Enhancement (Commissioning) |  | 29 | Stoneywood [Aberdeen -Dyce] |  |  |  | 180 | Strathcarron-Kyle [1745hrs Fri 2/10/09 until 0615hrs Sat 10/10/09] |  |  | 29 | Finnieston Tunnel | [5 empty] | 180 | Strathcarron-Kyle - Earthworks [1745hrs Fri 2/10/09 until 0615hrs Sat 10/10/09]
|  | 28 |  |  | Ft William Sleeper via Shotts | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 29 | GARL- Elderslie Loop ( 2 no. S&C on mainline & within W H Malcom Terminal) |  | 54 | Paisley Gil St : Re-roofing (Ayr Plats 3 & 4) [subject to further consultation] |  | 48 | Monktonhall South (Up) [Portobello Jn to Drem Jn] (0520 Sat to 0520 Mon) |  | 48 | Markle (Up) [Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) |  |  |  |  | 29 | Finnieston Tunnel | [13 empty] | 8 | Craiglockhart Jn S&C Tamp (Maint) [2315 Sat to 0715 Sun - ROTR]
|  | 29 |  |  | Ft William Sleeper via Shotts | All routes available | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 29 | GARL- Elderslie Loop ( 2 no. S&C on mainline & within W H Malcom Terminal) |  | 54 | Paisley Gil St : Re-roofing (Ayr Plats 3 & 4) [subject to further consultation] |  | 20 | Dundyvan (Dn) [Langloan Jn to Whifflet N. Jn] [0020 Sun to 2020 Sun] Blocks SC093 Burnhouse to Coatbridge Jn | [5 empty] | 225 | Altnabreac and Kinbrace [2130 Fri 16/10/09 to 0645 Mon 26/10/09] | 29 | Finnieston Tunnel |  | 48 | Stenton 1A/B, 2A/B incl PLTR - Up [M] [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) | [10 empty] | 8 | Winchburgh Jn Jn S&C Tamp (Maint) [0015 to 0815hrs - ROTR + 10min]
|  | 30 |  |  | Ft William Sleeper via Shotts | Hold Kirby Thore service at Kingmoor until Mon morn | 54 | A2B Project - Newbridge Jn to Bathgate [OLE & Civils] | 54 | A2B Project - Haymarket West Jn to Newbridge Jn [OLE & Civils] | 54 | Edinburgh Tram (tie) - Haymarket West Jn to Newbridge Jn | 54 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] incl relocation of GSMR mast @ Paisley Sigal Centre and UB 160/013 Hillington Road |  | 29 | Scotscalder (Platforms) |  | 29 | Johnny Baileys (Dn -RR) [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) | [10 empty] | 48 | Stenton 1A/B, 2A/B incl PLTR - Dn [M] [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) |  |  | 174 | Glenfinnan to Mallaig (E) [0001 Sat 17/10/09 to 0630 Sat 24/10/09] | 29 | UB302/333 Scotscalder Acc Rd and UB302/332 Dorrery Creep [Scotscalder] |  |  |  |  | 8 | Newbridge Jn Jn S&C Tamp (Maint) [0025 to 0825hrs - ROTR + 25min]
|  | 31 |  |  |  | Hold Kirby Thore service at Kingmoor until Mon morn | [6 empty] | 29 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] incl UB 160/013 Hillington Road |  |  |  |  | 48 | Reston (Dn) [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) |  | 48 | Lemington (Up) [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) | 48 | Stenton PLTR linked with S&C [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) | [17 empty] | 12 | Dalmeny S&C Tamp (Maint) [0045 Sun to 1245 Sun - ROTR + 4hr 45 min]
|  | 32 |  |  |  | Hold Kirby Thore service at Kingmoor until Mon morn | [6 empty] | 29 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] incl UB 160/013 Hillington Road |  |  |  |  | 48 | Lemington (Dn) [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) |  | 48 | Torness (Dn) [c/o Drem Jn to LNE boundary only] (0520 Sat to 0520 Mon) | [19 empty] | 8 | Portobello Jn S&C Tamp (Maint) (0035hrs to 0835hrs Sun - ROTR)
|  | 33 |  |  | Inverness Sleeper via Aberdeen | Hold Kirby Thore service at Kingmoor until Mon morn. Divert Inverness service via Aberdeen ? | [6 empty] | 29 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] | Perth to Inverness Blocked | 29 | Dunkeld & Birnam (Platforms) | [6 empty] | 29 | West Kilbride (Up Freight) | [5 empty] | 54 | Stanley No.24 pts |  |  | 29 | UB290/006 B9099 Caputh Rd, Murthly | 54 | ZD294 Dalcapone [Ballinluig to Pitlochry] , YU029 Drummore of Clava [Moy to Culloden], YD021 Culloden Wood (Dn) [Culloden to Millburn Jn] (Earthworks) | 54 | OB133/105 Perth Station (north end Plat 4)
|  | 34 |  |  | Inverness Sleeper via Aberdeen | Divert Inverness service via Aberdeen ? | [6 empty] | 29 | GARL- Shields Jn to Paisley [Gower St to Cardonald/ Arkleston Jn] |  | 29 | Dunkeld & Birnam (Platforms) |  |  |  |  | 56 | Crianlarich [south of station] [2235hrs Fri 13/11/09 until 0715 Mon 16/11/09] (Bus replacement Ardlui to Fort William) | 29 | West Kilbride (Up Freight) | 29 | Crookston Station [Drainage] |  |  |  | 54 | Stanley No.24 pts |  |  | 174 | Crianlarich to Oban (E) [0001 Sat 14/11/09 to 0630 Sat 21/11/09] [access to Crianlarich Lower required] | 54 | ZD294 Dalcapone [Ballinluig to Pitlochry] , YU029 Drummore of Clava [Moy to Culloden], YD021 Culloden Wood (Dn) [Culloden to Millburn Jn] (Earthworks) | 54 | OB133/105 Perth Station (north end Plat 4) |  |  | 12 | Polmont Jn S&C Tamp (Maint) [0015 Sun to 1215 Sun - ROTR + 4hr 10 min]
|  | 35 |  | SPT Christmas Shopper Services | Inverness Sleeper via Aberdeen | All routes available
|  | 36 |  |  | Inverness Sleeper via Aberdeen | All routes available | [36 empty] | 9 | Ladybank Jn S&C Tamp (Maint) [0040 Sun to 0940 Sun - ROTR + 2hrs 15min]
|  | 37 |  |  |  | All routes available | [12 empty] | 29 | Carpetwise (Edin Suburban) | [22 empty] | 10 | Inverkeithing Cen S&C Tamp (Maint) [2350 Sat - 0950 Sun - ROTR + 1hr 50 min ]
[16 empty] | KEY | POWERPOINT MAPS
| Bank Hol (West) | [7 empty] | Prepared by David H Kerr, Integrated Planning Manager, TDPU Scotland, Network Rail. email : david.kerr@networkrail.co.uk tel: 0141 555 4859 | [7 empty] | 1 - GSW, Carstairs to Haymkt & WCML South |  |  | 5 - South Electrics & Barrhead |  |  | 10 - Forth Bridge & Fife |  |  |  |  | All 54hr possessions are planned for Sat/ Sun unless otherwise shown
| Bank Hol (East) | [18 empty] | 6 - North Electrics |  |  | 11 - Central Scotland & Perth
| Bank Hol (All) | [15 empty] | 2- WCML North, Mossend & Shotts |  |  | 7 - West Highland Line |  |  | 12 - Dundee to Aberdeen
| Bank Hol (England) | [15 empty] | 3 - East Coast Main Line |  |  | 8 - E&G West & Cumbernauld |  |  | 13 - Highland Line & Aberdeen to Inverness
[17 empty] | 4 - Ayrshire, South Bank, Largs |  |  | 9- E&G East, Haymarket & Bathgate
Note on I6: new
Note on I17: new
Note on I18: new
Note on I30: new
Note on I31: new
Note on I32: new
Note on I33: new
Note on I34: new
Note on I35: new
Note on I36: new
Note on I37: new
Note on I38: new
Note on I43: new
Note on I44: new
Note on I45: new
Note on I46: new
Note on I47: new
Note on I48: new
Note on K4: new
Note on K6: new
Note on K33: new
Note on K34: new
Note on K35: new
Note on K36: new
Note on K43: new
Note on K44: new
Note on K45: new
Note on K46: new
Note on K47: new
Note on K48: new
Note on M11: new
Note on M12: new
Note on M32: new
Note on M33: new
Note on M34: new
Note on M35: new
Note on M36: new
Note on M43: new
Note on M44: new
Note on M45: new
Note on M46: new
Note on M47: new
Note on M48: new
Note on O43: new
Note on O44: new
Note on O46: new
Note on O47: new
Note on O48: new
Note on O49: new
Note on O50: new
Note on O51: new
Note on O52: new
Note on R8: new
Note on R12: new
Note on R17: new
Note on R18: new
Note on R19: new
Note on R20: new
Note on R45: new
Note on R46: new
Note on R47: new
Note on U6: new
Note on U7: new
Note on U8: new
Note on U9: new
Note on U10: new
Note on U11: new
Note on U12: new
Note on U13: new
Note on U14: new
Note on U36: new
Note on X7: new
Note on X8: new
Note on X9: new
Note on X10: new
Note on X11: new
Note on X12: new
Note on X13: new
Note on X14: new
Note on X15: new
Note on X16: new
Note on X17: new
Note on X18: new
Note on X27: new
Note on X30: new
Note on X31: new
Note on X36: new
Note on X52: new
Note on Z7: new
Note on Z9: new
Note on Z11: new
Note on Z12: new
Note on Z14: new
Note on Z15: new
Note on AB13: NEW
Note on AB52: new
Note on AD13: NEW
Note on AG4: new
Note on AG9: new
Note on AG10: new
Note on AG14: new
Note on AG15: new
Note on AG16: new
Note on AG17: new
Note on AG33: new
Note on AG34: new
Note on AK9: new
Note on AK10: new
Note on AK11: new
Note on AK12: new
Note on AK19: new
Note on AK22: new
Note on AK23: new
Note on AK26: new
Note on AK30: new
Note on AK31: new
Note on AK48: new
Note on AK52: new
Note on AM12: new
Note on AM28: new
Note on AM30: new
Note on AM31: new
Note on AO28: new
Note on AO51: new
Note on AO52: new
Note on AQ49: new
Note on AQ51: new
Note on AS3: new
Note on AS11: new
Note on AS12: new
Note on AS15: new
Note on AS29: new
Note on AS54: new
Note on AS55: new

## data
Set reference | Discipline title | Hours | Locations | Set Range references | Set Label reference | Start Row | End Row | Seperator
Plan range | [5 empty] | 2 | 70 | :
1 | #REF! | D | E | D2:E70 | E1
2 | #REF! | F | G | F2:G70 | G1
3 | #REF! | H | I | H2:I70 | I1
4 | #REF! | J | K | J2:K70 | K1
5 | #REF! | L | M | L2:M70 | M1
6 | #REF! | N | O | N2:O70 | O1
7 | #REF! | P | Q | P2:Q70 | Q1
8 | #REF! | R | S | R2:S70 | S1
9 | #REF! | T | U | T2:U70 | U1
10 | #REF! | V | W | V2:W70 | W1
11 | #REF! | X | Y | X2:Y70 | Y1
12 | #REF! | Z | AA | Z2:AA70 | AA1
13 | #REF! | AB | AC | AB2:AC70 | AC1

## template
Week No | Hrs | Location | Discipline | Row Cnt | Set Ref | Year | TDPU Ref | aiwp ref
37 | #REF! | #REF! | #REF! | 2 | 1 | 2007/08 |  | E2
38 | #REF! | #REF! | #REF! | 3 |  | 2007/08 |  | E3
39 | #REF! | #REF! | #REF! | 4 |  | 2007/08 |  | E4
39 | #REF! | #REF! | #REF! | 5 |  | 2007/08 |  | E5
40 | #REF! | #REF! | #REF! | 6 |  | 2007/08 |  | E6
41 | #REF! | #REF! | #REF! | 7 |  | 2007/08 |  | E7
42 | #REF! | #REF! | #REF! | 8 |  | 2007/08 |  | E8
43 | #REF! | #REF! | #REF! | 9 |  | 2007/08 |  | E9
44 | #REF! | #REF! | #REF! | 10 |  | 2007/08 |  | E10
45 | #REF! | #REF! | #REF! | 11 |  | 2007/08 |  | E11
46 | #REF! | #REF! | #REF! | 12 |  | 2007/08 |  | E12
47 | #REF! | #REF! | #REF! | 13 |  | 2007/08 |  | E13
48 | #REF! | #REF! | #REF! | 14 |  | 2007/08 |  | E14
49 | #REF! | #REF! | #REF! | 15 |  | 2007/08 |  | E15
50 | #REF! | #REF! | #REF! | 16 |  | 2007/08 |  | E16
51 | #REF! | #REF! | #REF! | 17 |  | 2007/08 |  | E17
52 | #REF! | #REF! | #REF! | 18 |  | 2007/08 |  | E18
1 | #REF! | #REF! | #REF! | 20 |  | 2008/09 |  | E20
2 | #REF! | #REF! | #REF! | 21 |  | 2008/09 |  | E21
3 | #REF! | #REF! | #REF! | 22 |  | 2008/09 |  | E22
4 | #REF! | #REF! | #REF! | 23 |  | 2008/09 |  | E23
5 | #REF! | #REF! | #REF! | 24 |  | 2008/09 |  | E24
6 | #REF! | #REF! | #REF! | 25 |  | 2008/09 |  | E25
7 | #REF! | #REF! | #REF! | 26 |  | 2008/09 |  | E26
8 | #REF! | #REF! | #REF! | 27 |  | 2008/09 |  | E27
9 | #REF! | #REF! | #REF! | 28 |  | 2008/09 |  | E28
10 | #REF! | #REF! | #REF! | 29 |  | 2008/09 |  | E29
11 | #REF! | #REF! | #REF! | 30 |  | 2008/09 |  | E30
12 | #REF! | #REF! | #REF! | 31 |  | 2008/09 |  | E31
13 | #REF! | #REF! | #REF! | 32 |  | 2008/09 |  | E32
14 | #REF! | #REF! | #REF! | 33 |  | 2008/09 |  | E33
15 | #REF! | #REF! | #REF! | 34 |  | 2008/09 |  | E34
16 | #REF! | #REF! | #REF! | 35 |  | 2008/09 |  | E35
17 | #REF! | #REF! | #REF! | 36 |  | 2008/09 |  | E36
18 | #REF! | #REF! | #REF! | 37 |  | 2008/09 |  | E37
19 | #REF! | #REF! | #REF! | 38 |  | 2008/09 |  | E38
20 | #REF! | #REF! | #REF! | 39 |  | 2008/09 |  | E39
21 | #REF! | #REF! | #REF! | 40 |  | 2008/09 |  | E40
22 | #REF! | #REF! | #REF! | 41 |  | 2008/09 |  | E41
23 | #REF! | #REF! | #REF! | 42 |  | 2008/09 |  | E42
24 | #REF! | #REF! | #REF! | 43 |  | 2008/09 |  | E43
25 | #REF! | #REF! | #REF! | 44 |  | 2008/09 |  | E44
26 | #REF! | #REF! | #REF! | 45 |  | 2008/09 |  | E45
27 | #REF! | #REF! | #REF! | 46 |  | 2008/09 |  | E46
28 | #REF! | #REF! | #REF! | 47 |  | 2008/09 |  | E47
29 | #REF! | #REF! | #REF! | 48 |  | 2008/09 |  | E48
30 | #REF! | #REF! | #REF! | 49 |  | 2008/09 |  | E49
31 | #REF! | #REF! | #REF! | 50 |  | 2008/09 |  | E50
32 | #REF! | #REF! | #REF! | 51 |  | 2008/09 |  | E51
33 | #REF! | #REF! | #REF! | 52 |  | 2008/09 |  | E52
34 | #REF! | #REF! | #REF! | 53 |  | 2008/09 |  | E53
35 | #REF! | #REF! | #REF! | 54 |  | 2008/09 |  | E54
36 | #REF! | #REF! | #REF! | 55 |  | 2008/09 |  | E55
FY37 | #REF! | #REF! | #REF! | 56 |  | 2008/09 |  | E56
FY38 | #REF! | #REF! | #REF! | 57 |  | 2008/09 |  | E57
FY39 | #REF! | #REF! | #REF! | 58 |  | 2008/09 |  | E58
FY40 | #REF! | #REF! | #REF! | 59 |  | 2008/09 |  | E59
FY41 | #REF! | #REF! | #REF! | 60 |  | 2008/09 |  | E60
FY42 | #REF! | #REF! | #REF! | 61 |  | 2008/09 |  | E61
FY43 | #REF! | #REF! | #REF! | 62 |  | 2008/09 |  | E62
FY44 | #REF! | #REF! | #REF! | 63 |  | 2008/09 |  | E63
FY45 | #REF! | #REF! | #REF! | 64 |  | 2008/09 |  | E64
FY46 | #REF! | #REF! | #REF! | 65 |  | 2008/09 |  | E65
FY47 | #REF! | #REF! | #REF! | 66 |  | 2008/09 |  | E66
FY48 | #REF! | #REF! | #REF! | 67 |  | 2008/09 |  | E67
FY49 | #REF! | #REF! | #REF! | 68 |  | 2008/09 |  | E68
FY50 | #REF! | #REF! | #REF! | 69 |  | 2008/09 |  | E69
FY51 | #REF! | #REF! | #REF! | 70 |  | 2008/09 |  | E70
FY52 | #REF! | #REF! | #REF! | 71 |  | 2008/09 |  | E71

## References
Week No | Hrs | Location | Discipline | Year | TDPU Ref | aiwp ref
37 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0605 | AA2
37 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0297 | I2
38 | 29 | Glasgow Central re-interlocking - Zone 3 | OHL/Signalling Renewals | 2007/08 | G0606 | AA3
38 | 29 | Huntly (ANI1 - Rev) | Plain Line Worksite | 2007/08 | G0511 | K3
38 | 29 | Millerhill Freddie 7 | Plain Line Worksite | 2007/08 | G0303 | I3
39 | 29 | Cowlairs East S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0309 | AC4
39 | 29 | Cowlairs West S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0307 | AC5
39 | 54 | Glasgow Central re-interlocking - All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0310 | AA4
39 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0305 | W4
39 | 20 | Monktonhall South | S&C Tamp Follow-up Tamp | 2007/08 | G0304 | U4
39 | 96 | Shields [Continues into week 40] | S&C Worksite | 2007/08 | G0308 | S4
40 | 54 | Glasgow Central re-interlocking- All Lines Blocked | OHL/Signalling Renewals | 2007/08 | G0316 | AA6
40 | 54 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0317 | W6
40 | 126 | Shields [Continued from week 39] | S&C Worksite | 2007/08 | G0315 | S6
40 | 29 | Newbridge Jn (A-B Project) | 3rd Party Schemes | 2007/08 | NEW | E6
41 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0608 | AA7
41 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0318 | W7
41 | 102 | Shields | S&C Worksite | 2007/08 | G0321 | S7
41 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0516 | M7
41 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0322 | K7
41 | 29 | Dundee Plat 1 (Up M) | Plain Line Worksite | 2007/08 | G0319 | I7
42 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0609 | AA8
42 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0327 | W8
42 | 78 | Shields | S&C Worksite | 2007/08 | G0325 | S8
42 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0517 | M8
42 | 29 | Cauldcotts (Dn) | Plain Line Worksite | 2007/08 | G0326 | K8
42 | 29 | Dundee (Up L) | Plain Line Worksite | 2007/08 | G0328 | I8
43 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0611 | AA9
43 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0333 | W9
43 | 54 | Shields | S&C Worksite | 2007/08 | G0334 | S9
43 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | O9
43 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | G0610 | M9
43 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0330 | K9
43 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0331 | I9
44 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0612 | AA10
44 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0341 | W10
44 | 54 | Shields | S&C Worksite | 2007/08 | G0339 | S10
44 | 29 | Craigendoran (Rev) | Plain Line Worksite | 2007/08 | NEW | M10
44 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0338 | K10
44 | 29 | Dundee (Thru Rd) | Plain Line Worksite | 2007/08 | G0340 | I10
45 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0345 | AA11
45 | 29 | Lagganstarroch | Structures Renewals 2 | 2007/08 | G0344 | Y11
45 | 29 | Kirkton Hill, Montrose, Stonehaven | Structures Renewals 1 | 2007/08 | G0342 | W11
45 | 51 | Slateford | S&C Worksite | 2007/08 | G0347 | S11
45 | 29 | Gorton (Rev) | Plain Line Worksite | 2007/08 | G0522 | O11
45 | 29 | Glenury (Dn) | Plain Line Worksite | 2007/08 | G0521 | M11
45 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | G0346 | K11
45 | 29 | Uddingston (Dn) | Plain Line Worksite | 2007/08 | G0388 | I11
46 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0352 | AA12
46 | 29 | Lagganstarroch | Structures Renewals 1 | 2007/08 | G0349 | W12
46 | 29 | Slateford | S&C Worksite | 2007/08 | G0351 | S12
46 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O12
46 | 29 | Muchalls (RR) | Plain Line Worksite | 2007/08 | NEW | M12
46 | 29 | Kinnaber (Up) | Plain Line Worksite | 2007/08 | NEW | K12
46 | 29 | Dimsdale (Up) | Plain Line Worksite | 2007/08 | G0389 | I12
47 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0357 | AA13
47 | 54 | Kingskettle | Structures Renewals 1 | 2007/08 | G0355 | W13
47 | 54 | Shields Follow-up Tamp | S&C Tamp Follow-up Tamp | 2007/08 | G0358 | U13
47 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S13
47 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | M13
47 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0350 | K13
47 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0359 | I13
48 | 29 | Glasgow Central re-interlocking - Zone 1 | OHL/Signalling Renewals | 2007/08 | G0361 | AA14
48 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S14
48 | 29 | Soldiers Trenches (Rev) | Plain Line Worksite | 2007/08 | NEW | O14
48 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0513 | M14
48 | 29 | Falkland (Up) | Plain Line Worksite | 2007/08 | G0354 | K14
48 | 29 | Wamphray (Dn) | Plain Line Worksite | 2007/08 | G0360 | I14
49 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0366 | AA15
49 | 43 | Carstairs Nth Jn | S&C Worksite | 2007/08 | new | S15
49 | 29 | Beith (Dn) | Plain Line Worksite | 2007/08 | G0368 | M15
49 | 29 | Forthar (Up) | Plain Line Worksite | 2007/08 | G0363 | K15
49 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0367 | I15
50 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0371 | AA16
50 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S16
50 | 29 | Newton-on-Ayr (Dn) | Plain Line Worksite | 2007/08 | G0530 | M16
50 | 29 | Plean (Up) | Plain Line Worksite | 2007/08 | G0373 | K16
50 | 29 | Elvanfoot (Up) | Plain Line Worksite | 2007/08 | G0369 | I16
51 | 12 | Newton-on-Ayr S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0378 | AC17
51 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0372 | AA17
51 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S17
51 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | NEW | M17
51 | 43 | Auchencastle (Up) | Plain Line Worksite | 2007/08 | G0547 | K17
51 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0377 | I17
52 | 12 | Kilwinning Jn S&C Tamp (Maint) | S&C Tamping / OLE / Heavy Maintenance | 2007/08 | G0381 | AC18
52 | 29 | Glasgow Central re-interlocking - Zone 4 | OHL/Signalling Renewals | 2007/08 | G0382 | AA18
52 | 43 | Beattock | S&C Worksite | 2007/08 | NEW | S18
52 | 29 | Larbert (Dn) | Plain Line Worksite | 2007/08 | G0383 | K18
52 | 43 | Dalmakether (Up) | Plain Line Worksite | 2007/08 | G0380 | I18
1 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA20
1 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W20
1 | 54 | Stirling Middle | S&C Worksite | 2008/09 | new | S20
2 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA21
2 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W21
2 | 29 | Stirling Middle | S&C Worksite | 2008/09 | new | S21
3 | 29 | Glasgow Central Interlocking - Zone 4 | OHL/Signalling Renewals | 2008/09 | new | AA22
3 | 54 | Larbert | S&C Worksite | 2008/09 | new | S22
4 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA23
4 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S23
5 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA24
5 | 78 | Falkland Yard | S&C Worksite | 2008/09 | new | S24
6 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA25
6 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S25
7 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA26
7 | 54 | Falkland Yard | S&C Worksite | 2008/09 | new | S26
8 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA27
8 | 29 | Stirling Middle FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U27
9 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA28
10 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA29
11 | 29 | Glasgow Central Interlocking - Zone 2 | OHL/Signalling Renewals | 2008/09 | new | AA30
12 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA31
12 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S31
13 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA32
13 | 54 | Halbeath | S&C Worksite | 2008/09 | new | S32
14 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA33
14 | 78 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S33
15 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA34
15 | 54 | Craiglockhart Jn | S&C Worksite | 2008/09 | new | S34
16 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA35
16 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W35
16 | 78 | New Cumnock | S&C Worksite | 2008/09 | new | S35
16 | 168 | Ballochmyle (Up) | Plain Line Worksite | 2008/09 | new | I35
16 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G35
17 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA36
17 | 168 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W36
17 | 29 | New Cumnock | S&C Worksite | 2008/09 | new | S36
17 | 168 | Mauchline (Dn) | Plain Line Worksite | 2008/09 | new | I36
17 | 168 | GARL- Shields to Paisley | Glasgow Airport Link Enhancement Scheme | 2008/09 | new | G36
18 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA37
18 | 54 | G&SW-Kilmarnock to Dumfries | Structures Renewals 1 | 2008/09 | new | W37
18 | 54 | Gartcosh | S&C Worksite | 2008/09 | new | S37
19 | 29 | Glasgow Central Interlocking - Zone 3 | OHL/Signalling Renewals | 2008/09 | new | AA38
19 | 12 | Halbeath FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U38
19 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S38
20 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA39
20 | 29 | Gartcosh | S&C Worksite | 2008/09 | new | S39
21 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA40
21 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U40
22 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA41
22 | 12 | Craiglockhart Jn FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U41
23 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA42
23 | 12 | New Cumnock FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U42
24 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA43
24 | 51 | Monktonhall South (Up) | Plain Line Worksite | 2008/09 | new | I43
25 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA44
25 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I44
26 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA45
26 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W45
26 | 12 | Gartcosh FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U45
26 | 78 | Whifflet North | S&C Worksite | 2008/09 | new | S45
26 | 51 | Lamberton (Dn) | Plain Line Worksite | 2008/09 | new | I45
27 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA46
27 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W46
27 | 29 | Whifflet North | S&C Worksite | 2008/09 | new | S46
27 | 51 | Ninewar (Dn) | Plain Line Worksite | 2008/09 | new | K46
27 | 51 | Lemington (Up) | Plain Line Worksite | 2008/09 | new | I46
28 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA47
28 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W47
28 | 51 | Oxwellmains (Dn) | Plain Line Worksite | 2008/09 | new | I47
29 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA48
29 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W48
29 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S48
29 | 51 | Houndwood (Dn) | Plain Line Worksite | 2008/09 | new | I48
30 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA49
30 | 168 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W49
30 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S49
30 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I49
31 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA50
31 | 54 | Mallaig Branch - Rock Cuttings | Structures Renewals 1 | 2008/09 | new | W50
31 | 51 | Oxwellmains Jn | S&C Worksite | 2008/09 | new | S50
31 | 51 | Pinkerton (Up) | Plain Line Worksite | 2008/09 | new | I50
32 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA51
33 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA52
33 | 12 | Whifflet North FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U52
34 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA53
34 | 54 | Markinch | S&C Worksite | 2008/09 | new | S53
35 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA54
35 | 54 | Markinch | S&C Worksite | 2008/09 | new | S54
36 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA55
FY37 | 7 | Glas Cen Interlocking - extended midwk | OHL/Signalling Renewals | 2008/09 | new | AA56
FY37 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S56
FY38 | 48 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA57
FY38 | 120 | Carmuirs East | S&C Worksite | 2008/09 | new | S57
FY39 | 77 | Glasgow Central Interlocking - ALB | OHL/Signalling Renewals | 2008/09 | new | AA58
FY39 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S58
FY40 | 29 | Carmuirs East | S&C Worksite | 2008/09 | new | S59
FY41 | 12 | Markinch FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U60
FY41 | 54 | Cadder | S&C Worksite | 2008/09 | new | S60
FY44 | 54 | Beattock | S&C Worksite | 2008/09 | new | S63
FY44 | 43 | Ecclefechan (Dn) | Plain Line Worksite | 2008/09 | new | I63
FY45 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S64
FY45 | 43 | Fullwood (Dn) | Plain Line Worksite | 2008/09 | new | I64
FY46 | 12 | Carmuirs East FUT | S&C Tamp Follow-up Tamp | 2008/09 | new | U65
FY46 | 54 | Beattock Summit | S&C Worksite | 2008/09 | new | S65
FY46 | 29 | Garriongill (Dn) | Plain Line Worksite | 2008/09 | new | I65
FY47 | 29 | Beattock Summit | S&C Worksite | 2008/09 | new | S66
FY47 | 29 | Garriongill (Up) | Plain Line Worksite | 2008/09 | new | I66
FY48 | 78 | Hilton Jn | S&C Worksite | 2008/09 | new | S67
FY48 | 29 | Rutherglen (Up Slow) | Plain Line Worksite | 2008/09 | new | I67
FY49 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W68
FY49 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S68
FY49 | 29 | Rutherglen Old Station (Up Slow) | Plain Line Worksite | 2008/09 | new | I68
FY50 | 168 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W69
FY50 | 54 | Hilton Jn | S&C Worksite | 2008/09 | new | S69
FY50 | 29 | Shawfield (Up Slow) | Plain Line Worksite | 2008/09 | new | I69
FY51 | 54 | Kyle Line - Earthworks | Structures Renewals 1 | 2008/09 | new | W70
FY51 | 54 | Hilton Jn - Ladybank Branch only | S&C Worksite | 2008/09 | new | S70