DRS & Network Rail Scotland Liaison Meeting

Scotland Engineering Access Consultation

Thursday, 19th June 2008

Room 3, DRS Offices, Kingmoor

Minutes

Attendees

| Name | Representing |
| --- | --- |
| David Kerr (DK) | Network Rail Scotland (TDPU) |
| Pauline McFarlane (PMcF) | Network Rail Scotland (NAU) |
| Anne MacKenzie (AMacK) | Network Rail Scotland (Commercial) |
| Tom Curry (TC) | DRS |
| Dave Stubbs (DS) | DRS |
| Sarka Oldham (SO) | DRS |
| Sabrina Brannan (SB) | DRS |
| Kenny Martin (KM) | Asda |
| Jerry Dawson (JD) | Asda |
| Graeme Undy (GU) | Eddie Stobart |
| Gayle Robertson (GR) | Network Rail Scotland (Note Taker) |

|  | 2009TTY Access Summary – ROTR Version 9.7 (16.06.08) |
| --- | --- |
|  | Purpose of Meeting The purpose of this meeting is to discuss the 2009TTY plan and review DRS’s response to RotR V.4 addressing any outstanding issues prior to the publication of RotR V.5. SO stated that DRS wanted to bring their customers together with Network Rail to give them a better understanding of Network Rail’s planning processes and timescales by which decisions are made. This will also give Network Rail a better understanding of DRS’s customers’ needs. |
|  | Engineering Access Plan Development Process DK provided an overview of Network Rail’s Engineering Access Plan Development Process in order to provide representatives from Asda & Eddie Stobart with an understanding of the planning processes undertaken by Network Rail when co-ordinating disruptive access for the work bank contained in 2010/11 plan. The process commences 90 weeks prior to the beginning of the timetable planning year, ie in March 2008 Network Rail began planning the access for the work bank to be implemented from Dec 2010 to March 2011. During the subsequent months the TDPU (Territory Delivery Planning Unit) are involved in meetings with contractors, engineers and project managers to discuss the access required for these works to ultimately create a co-ordinated possession strategy with the objective of mitigating overall disruption to the T/FOCs. The TDPUs in all five territories across the UK also hold a series of Inter-Territory workshops to gain an overall perspective of works that will be implemented across the country. This allows the territories to gain an understanding of works which will affect T/FOC services nationally and co-ordinate the disruptive access to ensure reasonable diversionary routes are available. The access plan is then consulted with the T/FOCs in order to refine the plan further. These discussions provide the foundations for the RotR Version 1 which will be published in November 2009, after which the NAU assumes responsibility for the possession strategy until the works have been implemented. There has been progress in a number of engineering efficiencies which will be implemented in 2010 which will ultimately reduce the level of disruption required for particular engineering works supporting Network Rail’s vision of the “7-day railway”. S&C modular installation (switches & crossings) which involves constructing switches and crossings off site that can then be installed as a fabricated unit and thus reducing the possession time taken. Reduction in possession durations will be progressively introduced over the next few years (e.g possessions traditionally 54hrs reduced to 37 then 27 hrs with further time reductions in the longer term). The modular concept cannot be applied to all switches & crossings due to complexities in engineering requirements, eg the length of a turnout etc. However, Network Rail will continue to seek opportunities to reduce access durations where possible. Engineering Access Plan Development Process (contd) Another initiative to reduce disruptive access is Bottom Up Relays for plain line track renewals, using a “production line” methodology. Whereas in a traditional 29hr possession approximately 450yrds of track can be renewed, in a bottom up relay 29hr possession 800yrds of track can be achieved. However,while this method reduces the net no. of disruptive weekends it requires the adjacent line to be available for engineering trains /plant and therefore is not suitable for Single Line Working. The EEA (Efficient Engineering Access) possession strategy will also be implemented in Scotland at the beginning of the 2010 timetable year (from Dec 2009), which requires disruptive possessions not to exceed 27hrs on the WCML between Carlisle and Carstairs (via Beattock). Exceptions to this can be considered for Bank Holidays. Overall, customers should expect to see a phased reduction in the level of disruption over the next few years. |
|  | DRS Traffic Update KM also advised the profile has been raised for the Asda service running from Crick which has just increased to running services 7 days a week. This traffic (28 boxes) would be difficult and expensive to transport by road. TC highlighted that the gauge across the Trans Pennine routes are important. The need to have the appropriate routes available at the right time is critical as diversions can take up to 14hrs, making it quicker to transport by road instead. GU stated diverting via London is a significant issue for Stobart traffic as it impacts greatly on the increase of journey times. Also access to and from Daventry is causing problems for not only Stobart and Asda traffic but also Tesco, JD Wetherspoon and JG Russell which needs to be reviewed further. ACTION: DK to arrange meeting between DRS and Network Rail to discuss possessions/ strategy for access to/ from the Daventry Distribution Terminal. Inverness DRS hope to run 2 services for Stobart/Tesco and 1 service for JG Russell per day, 6 days a week (Mon-Sat). The first train will commence as soon as the terminal is available, with the second (within 6/8 months thereafter) and third services having chilled products on them running overnight. The construction of the terminal at Inverness is expected to take 20 weeks from date of authorisation (approx early Dec 08) Only diversionary route is via Aberdeen Aberdeen ASDA expect to run 3 services a day 6 days a week to Aberdeen (Tues-Sun). The second service to Aberdeen has already been organised and is awaiting authorisation to commence the service. There is also a possibility of an overnight service to Aberdeen in the future. The third train is likely to be a multi-user service. DRS Traffic Update (contd) KM informed that Asda are reasonably comfortable with engineering works required on the Dundee to Aberdeen route if the durations do not exceed 29hrs. Anglo-Scottish TC stated that Stobart are hoping to start 6 day running of services on the WCML as soon as possible. Asda are also looking to run services 7 days a week. John G Russell traffic - currently running 5 days a week but are expecting to run 1 and probably 2 round trip services on Saturdays. SO informed that the there will be a third service from Daventry to Coatbridge (originating from Barking) due to growing demand for domestic intermodal for John G Russell. The north bound path for this service had remained in the timetable in anticipation of awarding a contract for this service (dep Daventry 2230hrs – arr Coatbridge 0630hrs). There is an issue of timing for the south bound service which DRS are currently examining further (dep Coatbridge 1330hrs – arr Daventry 2330hrs). The expected start date of this service is now 21 July 2008. |
| 1 | Review of Scotland 2009 TTY Plan The 2009 TTY Access Summary was reviewed. The principal focus of the meeting was seeking resolutions for the outstanding issues prior to the publication of RotR V.5. Where disruption has been previously discussed and agreed with DRS, these items of works and week nos. are not highlighted in these minutes. Period A Week 39 & 40 Stirling to Perth Hilton Jn S&C [Mainlines - 0130hrs Thurs 25/12/08 to 0510hrs Mon 29/12/08] DRS confirmed dates of operation would be 27th & 28th December 2008. Aberdeen (2 services) - Asda service to be cancelled - Tesco service is to divert via Stirling – Alloa Route (W9 capability) and Tay Bridge (W7 capability) Inverness (1 service) - Possibility of diverting service via Elgin or top n tail at Dundee then via Perth to Inverness. TC to further discuss diversion options with Stobart. Week 41 Dundee to Aberdeen (54hrs) Possession Ref: 994612 Craigo to Carmont (2355 Fri 2 Jan to 0530 Mon 5 Jan) SO advised that ASDA’s 2 services each Sat in Weeks 41-44 will require to be transported by road as there is no diversion route available by rail. ASDA’s Sunday services will now be changed to the Monday during Weeks 41-44. GU appreciated having this information of disruption to services this far in advance however, Saturday is the busiest day of the week for Stobart & ASDA. JD informed that the ASDA service from Daventry to Grangemouth is a key link to the service that is delivered to Aberdeen later that day, effectively being a same day service. ASDA are concerned with the costs of transporting their Saturday services from rail to road in Week 41-44. Further discussions required. ACTION : AMacK to investigate feasibility of Network Rail providing some financial compensation as a consequence of having to provide road transport for these specific weeks. Week 42 Dundee to Aberdeen (54hrs) Possession Ref: 994622 Craigo to Carmont (2355 Fri 9 Jan to 0530 Mon 12 Jan) As week 41 Week 43 Dundee to Aberdeen (54hrs) Possession Ref: 1059193 Inverkeilor to Montrose (0030 Sat 17 Jan to 0545 Mon 19 Jan) Possession Ref: 1057836 Newton Hill to Craiginches (0030 Sat 17 Jan to 0505 Mon 19 Jan) As week 41 YD093 Kirkton of Craig - CivilsAdditional site in Weeks 43 & 44 (54hrs) piggybacking existing 54hr access. Week 44 Dundee to Aberdeen (54hrs) Possession Ref: 986509 Carnoustie to Arbroath (0035 Sat 24 Jan to 0550 Mon 26 Jan) Possession Ref: 1059423 Inverkeilor to Montrose (0030 Sat 24 Jan to 0545 Mon 26 Jan) Possession Ref: 1064539 Newtonhill to Aberdeen (0130 Sat 24 Jan to 0500 Mon 26 Jan) As week 41 Week 44 (contd) YD093 Kirkton of Craig - Civils As Week 43 |
| 2 | Period B Week 47 Stirling to Dundee Auchterarder & Ninewells track renewals (29hrs) Possession Ref: 994588 Blackford to Hilton Jn (0110 Sun 15 Feb to 0515 Mon 16 Feb) Possession Ref: 994647 Longforgan to Dundee (0100 Sun 15 Feb to 0620 Mon 16 Feb) SO confirmed that ASDA’s Sunday service will run on the Monday. Stobart/Tesco traffic is unaffected. PMcF advised that these items will be removed from dispute for publication of RotR. Version 5. Week 48 Perth to Dundee Ninewells track renewals (29hrs) Possession Ref: 994647 Longforgan to Dundee (0100 Sun 22 Feb to 0620 Mon 23 Feb) As week 47 PMcF advised that this item will be removed from dispute for publication of RotR. Version 5. |
| 3 | Week 02 – 04 (incl Easter 2009) Stirling Middle S&C – ITEM DEFERRED Possession Ref: 995458 Plean to Dunblane (0035hrs Fri 10/4/09 to 0510hrs Mon 20/4/09) DK advised that due to the complexity of the design and related signalling issues Stirling Middle S&C has been deferred to Week 53 2010TTY. However, 1 no. 29hr possession is required in Week 4 (0030 Sun 19 Apr to 0500 Mon 20 Apr) for interim works associated with the Up Loop connection and earthworks. PMcF asked if DRS would like to see the removal of Stirling Middle possession in Week 2, 3 & 4 changed to 29hr possession in Week 4 only, in RotR.v5 or wait until DPPP timescales. DRS requested the above changes be shown in RotR v.5. Week 02 – 04 (contd) Carmuirs West to East (Up) – Track renewal (29hrs) Possession Ref: 999252 Carmuirs to Larbert (0030 Sun 12 Apr to 0500 Mon 13 Apr) Due to the deferral of Stirling Middle S&C (244hrs), Carmuirs track renewal has now changed from Week 3 to Week 4 (0030 Sun 19 Apr to 0500 Mon 20 Apr). GU to investigate availability of equipment for diverting via ECML southbound. ASDA have agreed to change their Sunday service to Monday in Week 4. Stobart/Tesco Sunday services to Aberdeen/Inverness will be top n’ tailed departing Grangemouth and diverting via Dalmeny. PMcF advised that these items will be removed from dispute for publication of RotR. Version 5. Week 04 Stirling Middle S&C Renewal – Interim works (29hrs) Up loop (including Earthworks) See Week 2 Carmuirs West to East (Up) – Track renewal (29hrs) See Week 2. The 4M30 service on Sun night will divert via Dalmeny (top n’ tailed) Week 05 Carmuirs East Jn S&C (54hrs) GU informed that the Tesco Saturday service to Aberdeen will divert via the Forth Bridge. GU informed that all Stobart boxes are 8ft 6in. These lower height boxes enable increased flexibility for diversionary routes with restricted gauge clearances. ASDA do not want to use alternative facilities at Mossend. The 4S49 service on Fri night & Sun will divert on the ECML via Millerhill / Winchburgh / E&G & reverse at Grangemouth Jn (top n’tail) ASDA also to consider option of hiring smaller boxes (8ft 6) from Stobart Rail in order to divert Sat/Sun Grangemouth to Aberdeen services via the Forth Bridge or change 4A11 Sunday service to Monday. DRS/ASDA to consider options further and confirm decision. Week 06 Carmuirs East Jn S&C (78hrs) Possession Ref: 101176 Carmuirs to Larbert (0045 Sat 2 May to 0500 Tues 5 May) See Week 5 Tesco Saturday & Monday services to Aberdeen will divert via the Forth Bridge. ASDA do not want to use alternative facilities at Mossend, 4S49 service on Fri night & Sun will divert on the ECML via Millerhill / Winchburgh / E&G & reverse at Grangemouth Jn. No ASDA service on Monday. ASDA to consider option of hiring smaller boxes (8ft 6) from Stobart Rail in order to divert Sat/Sun Aberdeen services via the Forth Bridge. DRS/ASDA to consider options further and confirm decision. The 4S49 service to pass on Tues morn as possession finish time is 0500 Tues in Week 6. TC advised that the Elderslie service on Monday would need to be cancelled. SO stated that 4S43 Stobart service from Daventry will not run on Bank holiday Mon Week 6 as other disruptive possessions are usually planned. If there are no other disruptions to the Daventry service on Mon Week 6, GU may consider running Daventry service via the ECML and Forth Bridge. PMcF advised that this item will be removed from dispute for publication of RotR. Version 5. Week 07 UB 132/021D Polmaise Jn structure renewal Possession Ref: 1025542 Plean to Stirling (0030 Sun 10 May to 0445 Mon 11 May) ASDA will change 4A11 Sunday service Grangemouth to Aberdeen to run on Monday. PMcF advised that this item will be removed from dispute for publication of RotR. Version 5. Carmuirs East Jn S&C Follow-up Welding & Stressing (18hrs) Possession Ref: 995493 Plean to Stirling (0045 Sun 10 May to 1845 Sun 10 May) ASDA will no longer require to use alternative loading terminal at Mossend as the 4A11 Sunday service Grangemouth to Aberdeen will now run on Monday. PMcF advised that this item will be removed from dispute for publication of RotR. Version 5. Week 08 Auchterarder (Dn) – Track Renewal (29hrs) Possession Ref: 995512 Larbert to Hilton (0020 Sun 17 May to 0510 Mon 18 May) ASDA will change 4A11 Sunday service Grangemouth to Aberdeen to run on Monday. PMcF advised that this item will be removed from dispute for publication of RotR. Version 5. |
| 4 | Period D1 Week 09 Carmuirs West Jn to Greenhill Lower Jn (Bonnymuir track renewal) 4M30 2224hrs Grangemouth to Daventry to be passed through possession over Up Line at 2300hrs Week 10 Carmuirs West Jn to Greenhill Lower Jn (Bonnymuir track renewal) 4M30 2224hrs Grangemouth to Daventry to be passed through possession over Up Line at 2300hrs Week 11 Carmuirs West Jn to Greenhill Lower Jn (Bonnymuir track renewal) 4M30 2224hrs Grangemouth to Daventry to be passed through possession over Up Line at 2300hrs |
| 5 | Period D2 Week 19 Burnhouse track renewals (29hrs) Stobart/ Tesco 4S43 on the Saturday should be unaffected. 4M48 expected to be diverted. Route to be agreed. Week 20 Burnhouse track renewals (29hrs) Stobart/ Tesco 4S43 on the Saturday should be unaffected. 4M48 expected to be diverted. Route to be agreed. Week 21 Mossend East Curve track renewal (29hrs) Stobart/ Tesco 4S43 on the Saturday should be unaffected. 4M48 expected to be diverted. Route to be agreed. Week 22 Mossend East Curve track renewal (29hrs) Stobart/ Tesco 4S43 on the Saturday should be unaffected. 4M48 expected to be diverted. Route to be agreed. Lenziemill track renewal (Cumbernauld route) 29hrs DRS confirmed diversion of 4M30 Daventry traffic via Larbert / Dalmeny/ Waverley/ Edinburgh Suburban route and the WCML. Stobart/Tesco 4M48 expected to be diverted. Route to be agreed. Week 23 Lenziemill track renewal (Cumbernauld route) 29hrs DRS confirmed diversion of 4M30 Daventry traffic via Stepps and Cowlairs. Stobart/Tesco 4M48 expected to be diverted. Route to be agreed. Barnhill Signalling Works Possession Ref: 1085223 Perth to Dundee ( 0115 Sun 30 Aug to 0610 Mon 31 Aug) ASDA do no want to change the Sunday service to Aberdeen to a Monday as this is a bank holiday. DRS/Asda will investigate the possibility of smaller containers to allow diversion via Forth and Tay Bridges. Week 23 Whifflet S&C renewal (78hrs) This work was previously planned in 2008TTY Whifflet So. Jn to Langloan Jn & Coatbridge Jn (0545 Sat 29/08/09 to 0630 Tues 1/09/09 – extends to include Coatbridge Jn from 0545 Sat to 1500 Sat then 1000 Mon to 0630 Tues) TC advised that the 4S49 Fri night/Sat morn can run before the possession starts. TC advised that the 6th day additional service will be running by this time. The Sat 4M50 service can depart from Grangemouth travelling south bound via Polmadie (this will increase the journey time by approximately 30mins). The north bound service from Daventry on Saturday can divert via Polmadie. Sun night 4M30 can also run via Polmadie. Week 23 (contd) Whifflet S&C renewal (78hrs) While Coatbridge Jn is blocked 1000 Mon to 0630 Tue, the two eastbound Elderslie services are unaffected. On the Monday the 2 Elderslie west bound services are affected. DRS will look to running 4R77 in its old path which will get it through before the block. 4N72 will have to be retimed to depart Elderslie earlier and NR's cooperation will be appreciated with this. The services should be back to normal on the Tuesday. Mon services: - 4S43 service will run WCML to Edinburgh round via the Sub and reverse at Grangemouth. - 4M48 service Stobart service running south bound will run round the Sub to Edinburgh and divert via WCML. - 4M30 service will run south bound round the Sub to Edinburgh and divert via WCML. Tues services: - 4S49 service will delay departure for 1hr 30mins to pass after possession ends to avoid diverting traffic. Week 24 Whifflet S&C - Follow up Tamp (29hrs) 4S49 service will be unaffected. 4M30 South bound will run round the Sub to Edinburgh and divert via WCML. ACTION : PMcF/DK to enquire whether 4M30 can pass through FUT to avoid diverting service. Cumbernauld route (Garnqueen North track renewal) 29hrs 4M30 Daventry traffic via Stepps and Cowlairs. Barnhill Signalling Works Possession Ref: 1085224 Perth to Dundee (0115 Sun 6 Sep to 0610 Mon 7 Sep) ASDA Sun service to Aberdeen to run on Monday. PMcF advised that this item will be removed from dispute for publication of RotR. Version 5. |
| 6 | Period E Week 33 Perth – Inverness (54hrs) Possession Ref: 997233 Perth to Inverness (0045 Sat 7 Nov to 0530 Mon 9 Nov) Week 33 Perth – Inverness (contd) Tesco – 2 services to Inverness on Sat (possible increase to 3 services). GU stated that given this advance notification of these works there will be sufficient time to make suitable alternative arrangements. Week 34 Perth – Inverness (54hrs) Possession Ref: 997242 Perth to Dunkeld (0001 Sat 14 Nov to 0645 Mon 16 Nov) Possession Ref: 997239 Carrbridge to Culloden (0045 Sat 14 Nov to 0645 16 Nov) Tesco – 2 services to Inverness on Sat (possible increase to 3 services). ). GU stated that given this advance notification of these works there will be sufficient time to make suitable alternative arrangements. ACTION : SO to provide DRS Customers with a summary of the agreements made at 19/6 meeting in relation to outstanding issues for 2009TTY RotR V.4 |
| 7 | Overview of 2010TTY Plan DK provided the meeting with an overview of the 2010TTY plan in its early stages in order to give DRS and their customers an indication of the disruptive access required for engineering works. Evolution 1 of the 2010TTY plan will be published to T/FOCs on Friday 4th July 2008. This will only include Blockades (disruptive access which affects a normal working day i.e Mon-Fri) and possessions required on Bank holidays. Key points of the 2010TTY plan are: Weeks 38 to 40 WCML Track Renewals & Civils works (3no. 27hrs) EEA compliance will ensure that there will be a maximum 27hr possession on WCML between Carlisle and Carstairs. Although the optimal time for the 27hr possession over a weekend is still to be consulted with T/FOCs. Weeks 41 to 44 Dundee – Aberdeen Combination of PLTR, S&C renewals and Civils works (4no. 54hrs). GU suggested moving 2no. 54hr weekends from Weeks 43 & 44 to Weeks 39 & 40 during Christmas & New Year as Stobart always have drivers available on 29th Dec. This would make less of an impact on services in January. DK advised that all works have been taken into consideration before making this decision and it is the most critical works that are undertaken during Christmas & New Year in order to create minimal impact to services. Week 53 (2009TTY) to Week 2 (2010TTY) Stirling Middle S&C Renewal – 244hrs (0035 Fri 2/4/10 to 0510 Mon 12/04/10) This item has been deferred from Weeks 2-4 2009TTY. Disruptions to services to be discussed further at next meeting. Weeks 2 to 6 WCML PLTR and S&C renewals - DRS concerns regarding Daventry traffic during WCML blocks. DRS investigating possibility of diverting via ECML (W8). ACTION : AMacK to clarify gauge on the City Union line for diversionary route purposes Weeks 12 & 13 Stirling Middle S&C Welding & Stressing (2no.16hrs) - These possessions do not affect the mainlines, S&D lines, Plat 6 & 9 and Up loop only. Weeks 33 & 34 Perth – Inverness (2no.54hrs) Civils works – Rock stabilisation and Timber Deck Renewal at Kincraig. |

| 8 | Next Meeting: Time: 0900-1230hrs Date: Tuesday, 16 September 2008 Room: TBC Venue: Buchanan House, Glasgow |
| --- | --- |