## Access response by TOC
Page | Para | Year | Period | Week | Response | Operator | Network Rail response
8 | 5.2 | 2011 | J | 35 | Not acceptable to Freightliner. Freightliner object to these possessions as they block access to/from Birch Coppice Sdgs, we have 3 services into Birch Coppice on Saturdays and two out (including a light engine). There is nowhere else for these services to go and cancelling them is not an option. Freightliner has asked for this possession to be done over a Bank Holiday (Week 22) as this would not affect our services on Saturday afternoon, Sunday & Monday. | FLIM | I can advise that Network Rail is not in a position to reduce the level of access required for this commissioning. Given that we have cut access back in week 34 weekend and midweek, we cannot deliver the work content needed to commission the new signalling if this access is reduced. Under separate cover, I have supplied detail of the work being delivered. We have also examined the dating of this commissioning in some depth. August Bank Holiday 2011 (week 22) was an option at early stages of planning the project; however in meetings NR was requested by Operators to move this to October and then to November 2011. Network Rail does not now wish to further redate this commissioning as it would compromise national testing resource plans and increase project risk to an unacceptable level.