SOLE SUBMISSION TO TIMETABLING PANEL

By

NETWORK RAIL INFRASTRUCTURE LIMITED

TTP Reference 444 & 450

(Decision Documentation – LNE CPPP 9-12 & 13-16)

(Specific Restriction of Use – Decision Document –

RoU for ECML (London-Peterborough/Cambridge)

Weeks 9 to16 Sundays 27th June to 15th July 2012)

28th February 2012

- 1	Details of parties

- 1.1	The names and addresses of the parties to the reference are as follows:-

    - First Capital Connect Limited. (Company number 5281077) whose Registered Office is at 50 Eastbourne Terrace, Paddington, London W2 6LG (“FCC” - "the Claimant"); and

    - Network Rail Infrastructure Limited (Company number 2904597) whose Registered Office is at ‘Kings Place’, 90 York Way, London N1 9AG ("Network Rail” - "the Defendant").

    - FCC contact details are Paul French, Head of Planning, Hertford House, 1 Cranwood Street, London EC1V 9QS

    - Network Rail contact details are Toby Patrick-Bailey, Lead Access Planner LNE, Engineering Access Planning, 500 Station House, Elder Gate, Milton Keynes Central MK9 1BB

- 1.2	Third parties that may be affected by the Panel’s finding in any of the ways sought and determined under Section 8 are as follows:

    - East Coast

    - Hull Trains

    - Grand Central

    - Freightliner Group

    - GBRf

    - DB Schenker

- 2	The Defendant’s right to CONTEST this reference

- 2.1	This matter is referred to a Timetabling Panel ("the Panel") for determination in accordance with Condition D3.5 and D5 of the Network Code.

- 2.2	The contractual provisions which entitle Network Rail to facilitate this Restriction of Use in Weeks 9-16 on the ECML are detailed in Network Code Part D, clause 3.4 and Section 3 of the National Timetable Planning Rules ‘Procedure for Altering the Engineering Access Statement or Timetable Planning Rules other than through the Twice-Yearly Process’.

2.3	Network Code Part D clause D3.4.16 allows for any Timetable Participant that is dissatisfied with Network Rail’s decision to appeal in accordance with Network Code Part D, clause D5. Network Rail accepts that First Capital Connect Limited is entitled to raise this dispute.

- 3	Contents of reference

- 3.1	This Response to the Claimant’s Sole Reference includes:-

    - The subject matter of the dispute in Section 4;

    - A summary of the issues in dispute in Section 5;

    - A detailed explanation of those issues in dispute prepared by the claimant in Section 6;

    - In Section 7, the decision sought from the Panel;

    - Appendices and other supporting material.

- 4	subject matter of dispute

- 4.1	The matter in dispute is Network Rail’s decision to plan possessions on Sunday mornings in Weeks 9 to 16 (Appendix A) to carry out enhancement work at Finsbury Park, Alexandra Palace, Hertford North, Stevenage and Hitchin, as well as S&C renewals work at Cambridge Jn .

- 4.2	The focus of FCCs dispute appears to be Network Rail’s decision to take access for these works simultaneously on Sunday mornings. Therefore the dispute centres on Network Rail’s application of the Decision Criteria (Network Code, Part D clause D4.6).

- 4.3	Network Rail notes that FCC is not disputing Network Rail’s application of the Network Code, Part D, in terms of its compliance with Part D clause 3.4.

- 5	summary of dispute

- 5.1	Enhancement work at Finsbury Park and Alexandra Palace was originally proposed (in Version 1 of the 2012 Engineering Access Statement) to take place in an 80 hour possession in Week 39, and a 54 hour possession in Week 40. A number of Train Operators (including FCC) disputed this proposal and as a result Network Rail looked to revisit the possession plan to negate the need for possessions of such duration and impact. Working with stakeholders, a possession plan supported by the industry was drafted.  Having reached the decision that the access contained within the Engineering Access Statement was not suitable, Network Rail is consulting the re-plan of this project using application of the Network Code, Part D, in compliance with Timetable Planning Rules clause 3.3. Changes were initially required post-CPPP to deliver the first stages of the project over Christmas 2011, with later weeks able to meet the single co-ordinated document (DPPP).  The development of Network Rail’s access plan for the Finsbury Park and Alexandra Palace has been an iterative process, with frequent stakeholder meetings to determine how best to deliver the enhancement and facilitate a near full service at all times.

  - Enhancement work at Hitchin was not included within Version 1 of the 2012 Engineering Access Statement, as Network Rail had not drafted a suitable access plan for the works in time to meet the publication.  Network Rail continues to develop and consult access for this scheme in line with planning principles supported by stakeholders using application of the Network Code, Part D, in compliance with Part D clause 3.4.

  - Enhancement work at Hertford North and Stevenage, and S&C renewal works at Cambridge Jn were included within Version 1 of the 2012 Engineering Access Statement, and have either remained as originally proposed or had some level of reduction in the disruptive access footprint.

  - The access footprint to deliver Cambridge Jn S&C renewals required 1x54 hour possession and 2x 30 hour possessions.  Such an RoU is best dated on bank holiday weekends when there is a lesser demand for passenger services, and a reduced level of freight services.  Dating these renewals in Spring took advantage of Week 2 (Easter) and Week 6 (May Day), but requires a suite of follow up access which prevents a route for services North of Stevenage (Weeks 7-16).  Network Rail has reduced the access footprint for this work in all weeks but Week 10 – this week will see delivery of a tandem tamp on the new S&C, which will withdraw the Up Fast, Up Slow and Up Cambridge Temporary Speed Restriction (TSR).  Without similarly disrupting FCC services or utilising intrusive midweek access, this will not be possible until Week 16 by which point the speed restrictions on all up lines will have been in place for 10 weeks. Daily inspections would be needed to ensure safety of the line, with potential for any remedial work required to be undertaken intrusively.

  - The access footprint for the Hitchin Grade Separation is suitably optimised with the Cambridge Jn S&C renewal possessions and causes no further detriment to services.

  - The access footprint for the Finsbury Park and Alexandra Palace footprint is driven by the engineering need of meeting;

    - the December timetable change and expectation of 12 car services on the ECML which requires RoU of the down lines

    - the need to undertake preparatory and enabling works before the Christmas shutdown and the associated infrastructure changes that will occur which requires RoU of the up lines.

  - Network Rail have shared proposals for further RoUs in Weeks 25-30 (Sundays 16th September to 21st October) which will be utilised to begin overhead line infrastructure changes (Alexandra Palace) and continue platform extensions (Finsbury Park).  Should Network Rail not be in a position to complete the structural alterations to support the platform extensions, or the installation of masts and portals for the overhead line changes planned in the RoUs for Weeks 9-16, this access can similarly not be utilised, and Network Rail will not be in a position meet the two key milestones at the end of 2012. Network Rail is not in a position to shorten or re-date the RoU at Finsbury Park and Alexandra Palace in Weeks 9-16 without loss of this work unless access of greater duration is taken, requiring FCC, East Coast, Grand Central and Hull Trains to provide rail replacement services on Saturday night or through to midday Sunday.

  - The access footprint for the Hertford North Integration Facility and Stevenage Estates work remain as published in Version 2 of the Engineering Access Statement, and are intentionally optimised such that the restriction of platforms at Stevenage is undertaken in a period when Hertford services are withdrawn. Neither RoU restricts the route in/out of London or to/from Peterborough and Cambridge.

  - Network Rail consulted the combination of RoU through the DPPP process, at which point FCC stated they could not support the level of disruption on Sunday morning (an example of which is shown in Appendix B).  Network Rail and FCC subsequently agreed to meet to discuss the proposals on 1st December to discuss the reasoning behind the proposals and the possible options in resolving FCC concerns for Sunday morning services.  Regrettably due to diary constraints this meeting could not take place until after the point at which Network Rail was required to publish a decision (CPPP) in compliance with Clause 3.4 of the Train Planning Rules. As such, Network Rail published a decision applying the decision criteria to the information provided by FCC and with knowledge of the possible alternative access strategies.

  - During the meeting on the 1st December, Network Rail outlined its alternative strategies;

    - delivering S&C renewal activities at Cambridge Jn midweek nights

    - withdrawing Alexandra Palace and Finsbury Park enhancements

    - re-planning Alexandra Palace and Finsbury Park enhancements into fewer instances of longer possessions

  - FCC counter proposed that Network Rail should continue to deliver access on Sunday mornings to prevent disruption to midweek services, but should seek to provide a service between Cambridge and New Barnet from 0700 Sunday, thus supporting the Alexandra Palace and Finsbury Park disruption between 0130 and 0830 Sunday and the Stevenage to Biggleswade disruption between 0120 and 0700 Sunday, which Network Rail agreed to review against the requirements of the Cambridge Jn S&C renewals.

  - During this review, on the 6th of December FCC identified two events at Knebworth (Weeks 13 and 15, Sunday 24th June and 08th July) which would likely require a full and/or strengthened service between London and Cambridge to manage additional demand (appendix C). Network Rail informally communicated on the 14th December that the services for these events could be facilitated (appendix D), but doing so would likely render the Cambridge Jn S&C renewal work undeliverable without utilising midweek access.

  - Network Rail formally confirmed its response to FCCs counter proposal on 17th January (appendix E) confirming that FCCs proposed compromise could not be facilitated without loss of the Cambridge Jn renewal work, taking cognisance of easements required to facilitate a full FCC service in Weeks 13 and 15 due to the Knebworth events, and clarified further its interpretation of the decision criteria as to balancing weekend access against midweek access on the 1st February (appendices F and G).

  - On the 14th February Network Rail communicated in detail the engineering work within the Finsbury Park and Alexandra Palace enhancement RoU (appendix H), and where possible without detriment to work delivery, demonstrated easements to accommodate FCCs service.

  - On the 16th February Network Rail communicated in detail the engineering work within the Cambridge Jn S&C renewals RoU (appendix I), and where possible without detriment to work delivery, demonstrated easements to accommodate FCCs service.

  - Since its original decision, Network Rail has re-packaged its work and been able to accommodate FCC expectations in 7 out of 8 weeks originally disputed.  Network Rail s still to receive any counter proposal to its access strategy.

- 6	explanation from the Defendant’s perspective of each issue in dispute

- 6.1	Issues where the Defendant Accepts the Claimant’s Case

- 6.1.1	Network Rail accepts the claim by First Capital Connect Limited (FCC sole submission clause 5.3) that appropriate responses have been made ‘in order to best protect its service’.  However this highlights the lack of provision of information on how such access has a detrimental affect on their business, and the lack of provision of an alternative counter proposal (as required in Timetable Planning Rules 3.4.1.2) save the expectation that work be removed to facilitate FCCs services.

- 6.1.2	Network Rail accepts the claim by First Capital Connect Limited (FCC sole submission clause 6.3) that the published access footprint requires rail replacements at expense of utilising railway stock.  However Network Rail believe that referral to Criterion (j) in this matter is not applicable, and that this criterion is worded to assist in timetable capacity allocation

- 6.1.3	Network Rail accepts the claim by First Capital Connect (FCC sole submission clause 5.2) that the access within the Engineering Access Statement could be considered ‘disparate’. FCC are aware that these possessions were withdrawn due to operator objection (including FCC), with the work contained within (renewal of S&C and plain line between Finsbury Park and Ferme Park) moved into the Christmas shutdown at expense of the overhead line alterations at Alexandra Palace, which was moved into possessions of shorter durations in Weeks 9-16 and Weeks 25-30.

- 6.2 	Issues where the Defendant qualifies or refutes the Claimant’s Case

- 6.2.1	Network Rail find the passenger information provided by First Capital Connect Limited (FCC sole submission clause 5.2) confusing.  There is no differentiation made between how FCC would manage passengers between 0130 and 0730 Sunday (supported levels of disruption) and the total disruption on the route (until 0830 Sunday).  FCC have not provided information as to which location the passenger count is performed or the sample date. The disruption between 0730 and 0830 is concentrated between 1C32 and 1T37 on the Down.  Network Rail would suggest 1T37 start from Stevenage with minor flexing, which maintains 85% of station calls (12/14) in the busiest service.   In the Up, it is concentrated between 1C82 and 1C83, with the latter being able to run with moderate retiming serving all stations on route.

- 6.2.2	Network Rail notes First Capital Connect Limited expectation (FCC sole submission clause 6.1) that services should be made available to/from London King’s Cross, though without specification as to origin/destination from circa 0730 to 0830 Sunday.  This is a direct contradiction to its proposed compromise of a service between New Barnet and Cambridge from 0700 Sunday in support of the Finsbury Park and Alexandra Palace RoU.  FCC have not shared passenger information within the consultation period or post decision on verbal challenge, and note that the information annexed to the submission is done so selectively without consideration of the alternative access footprints Network Rail has discussed.  It does not support the proposed compromise tabled by FCC or its interpretation of Criterion (h).

    - Network Rail does not accept the claims by First Capital Connect Limited (FCC sole submission clause 6.2) that it has failed to optimise the disruptive RoU’s.  Network Rail has demonstrated its application of the decision criteria in reaching its decision to take access as published within the respective CPPPs. FCC have not fully comprehended the recommendations within the LNE Route Utilisation Strategy (appendix J) detailing the volume and significance of the enhancement projects planned for the East Coast Main Line in Control Period 4, and as such Network Rail contest FCCs view that Criterion (b) is incorrect.  It is apparent that FCC support access planned in constraints utilised over previous years when lesser volumes of work exist, without regard for volume of work planned or the impact of alternative access strategies on train services.

    - Network Rail notes First Capital Connect Ltd (FCC sole submission clause 6.3) interpretation of Criterion (c) is contradictory.  FCC compromise and support for access proposals results in support for access either at the North or South end of the route.  This similarly results in Service Level Commitment services requiring part rail replacement and journey time extension, thus Network Rail contend application of this criterion is not applicable, particularly given the adherence to 3.4 of the Train Planning Rules in the consultation of this access.

    - Network Rail would welcome FCCs clarification of their interpretation of “Network Rail’s commercial interests” (FCC sole submission clause 5.9 and 6.3).  Network Rail contend that by taking more possessions of shorter duration, and avoiding intrusive midweek RoU it is demonstrating its commitment to running rail services at expense of its commercial interests, and contributes to meeting the licence obligation that the ORR has placed on Network Rail to deliver its Possession Disruption Index CP4 target.   Network Rail note that FCC fail to make reference in its interpretation of Criteria (d) and (e) that the ‘modest adjustment’ proposed to access will render the enhancement and renewal work undeliverable.

    - Network Rail notes that First Capital Connect Limited (FCC sole submission clause 6.3) have failed to demonstrate a wider application of the decision criteria, demonstrating no consideration of the alternative access footprints or impact on train services beyond its own interests.  This is particularly evidenced in FCCs response to Network Rail’s application of Criterion (l), as an alternative access strategy of midweek RoU or of fewer, longer weekend possessions would result in greater number of passengers and services being affected and a loss of route for freight (midweek) or long distance rail replacement for intercity services that would be additionally affected (weekend). In doing so, its conclusions in its application of Criterion (f) are flawed – FCCs own passenger information for Sunday demonstrating a vastly more populated service later into the morning.

    - Network Rail notes that First Capital Connect Limited (FCC sole submission clause 6.3) demonstrates contradicting expectations in its interpretation of the decision criteria between Criteria (h) and (m).  FCC appear to expect a service to/from London King’s Cross from 0730 Sunday, but the ‘slight limitation’ proposed to Network Rail as alluded to in reference to Network Rail’s application of Criterion (m) supports this route being blocked until 0830 Sunday.  Network Rail contends that FCCs application of Criterion (h) is not applicable.

    - Network Rail does not accept the claims by First Capital Connect Ltd (FCC sole submission clause 5.7 and 6.4) regarding its position of support for the individual projects concerned.  Network Rail have shared the impact that FCCs expectations will have on work delivery in detail, and demonstrated that any further easement will result in loss of work delivery.  FCC have stated that they will not support alternative access footprints for any ‘extraneous work’ caused by any such access relaxation, and can therefore only be interpreted as expecting this work to be withdrawn at detriment to the individual projects concerned.

- 6.3	Issues not addressed by the Claimant that the Defendant considers should be taken into account as material to the determination

- 6.3.1	At no point within the consultation period, or as part of the dialogue held after the CPPP publication have FCC provided any information to inform Network Rail’s decision making, or evidence as to the benefit that the proposed compromise of running a service ‘in part’ from 0700 Sunday will have. Network Rail note that FCC append passenger information for a service running in full between London and Cambridge, but do not articulate how the proposed alteration to access will affect these passenger figures or information on how engineering work advertised in advance affects passenger numbers.

- 6.3.2	Network Rail notes First Capital Connect Ltd (FCC sole submission clause 7.2) identifying that where engineering work has allowed, a route has been returned for FCC to run a ‘reasonable’ service (Weeks 9 and 11-16).  The remaining week in contention (Week 10 – June 03rd 2012) is a Bank Holiday weekend – no information is provided by FCC through consultation or in its submission on the effect of bank holidays on passenger demand.

- 6.4	Why the arguments raised in 6.1 to 6.3 taken together favour the position of the Defendant

- 6.4.1 	Network Rail has balanced its application of the Decision Criteria to support disruption on Sunday morning periods, focussing its most disruptive footprint in a bank holiday weekend.  This enables a greater number of services (conveying a greater number of passengers) midweek and on Saturday to run without need for rail replacement.  This also applies to services from 0830 Sunday. In doing so it has prioritised Decision Criteria (a), (b), and (e).

- 6.4.2 	It is Network Rail’s view that it would be unreasonable of FCC to constrain RoU in Weeks 9-16 to run a service in/out of London between 0130 and 0830 Sunday when FCC have stated that they do not support the viable alternative access strategy which retains work delivery for this to occur.

- 6.4.3	Network Rail contend that FCCs application of the decision criteria is both incorrect in its weighting of passenger services between 0700 and 0830 Sunday over midweek night and later Sunday services, and flawed in recommending a decision that prevents an RoU from being utilised for the intended work.

- 6.4.4	Network Rail summarise its application of the decision criteria for these works as a single access package as follows;

| Decision Criterion | Evidence | NR Opinion | Weighting |
| --- | --- | --- | --- |
| (a) sharing the capacity, and securing the development, of the Network for the carriage of passengers and goods in the most efficient and economical manner in the interests of all users of railway services having regard, in particular, to safety, the effect on the environment of the provision of railway services and the proper maintenance, improvement and enlargement of the Network; | Replacing midweek night services to/from Cambridge affects a greater number of services and passengers, as well as a potential loss of midweek night route for freight. Access beyond 0830 Sunday on the ECML affects heavier loaded FCC services and includes busy intercity services on Sunday morning, particularly in the Down direction. Remaining issue in Week 10 is a Bank Holiday, and is not believed to be an extremely busy traffic period. FCC are able to run a service between New Barnet and Stevenage. | That the access strategy in place in Weeks 9-16 is the least disruptive combination to deliver the work required (constrained periods of heavy disruption on Sunday morning to maintain a route on Saturday, Sunday afternoon and midweek on the ECML.) FCC support the delivery of all works within the RoU, but do not support alternative access strategies. Network Rail apply criterion (a) with consideration of the work within RoU as a package with cognisance of the impact of alternative access strategies. | In favour of NR |
| (b) seeking consistency with any current Route Utilisation Strategy which is either (i) published by the Strategic Rail Authority or the Department for Transport before 31 May 2006, or (ii) established by Network Rail in accordance with its Network Licence | Provision of enhancements at Finsbury Park and Alexandra Palace are included within the recommendations from the ECML RUS for delivery within CP4. Not undertaking access in Weeks 9-16, or constraining access to an 0700 finish will not enable on time completion. | That the revised access strategy consulted for the enhancement projects over the original EAS submission is in consistency with delivering enhancement schemes within the control period. | in favour of NR |
| (c) enabling a Bidder to comply with any contract to which it is party (including any contracts with their customers and, in the case of a Bidder who is a franchisee or franchise operator, including the franchise agreement to which it is a party), in each case to the extent that Network Rail is aware or has been informed of such contracts | Network Rail have consulted and published this access in line with Clause 3.4 of the Train Planning Rules. | SLCs and TAAs with Network Rail are specifically framed to allow TOCs to remove services where this is required by NR Restrictions of Use and therefore TOCs will not be penalised under the terms of their Franchise Agreements. It is recognised that the withdrawal of a through service to/from Cambridge pre 0830 Sunday results in journey times beyond FCC SLC, though Network Rail notes that in-part rail replacement of this service is acceptable with similar result. | In favour of NR |
| (d) maintaining and improving the levels of service reliability | n/a | n/a | n/a |
| (e) maintaining, renewing and carrying out other necessary work on or in relation to the Network | The work driving this access is the remaining S&C renewals at Cambridge Jn and enhancement work at Finsbury Park and Alexandra Palace | FCCs proposed constraints result in either the withdrawal of the S&C renewals or the imposition of significant speed restrictions for a significant period of time. If enhancement work is constrained, this will render 12 car benefits for December 12 undeliverable, and the provision of a 3rd up line at Alexandra Palace to be delayed for 1 year. | In favour of NR |
| (f) maintaining and improving connections between railway passenger services | n/a | n/a | n/a |
| (g) avoiding material deterioration of the service patterns of operators of trains (namely the train departure and arrival frequencies, stopping patterns, intervals between departures and journey times) which those operators possess at the time of the application of these criteria | Midweek passenger services, and heavier loaded weekend services will be able to run unimpeded by these works. | This disruption extends for 1 hour beyond FCCs supported level of disruption, and that this access strategy is the least disruptive in delivering all works required. | In favour of NR |
| (h) ensuring that, where the demand of passengers to travel between two points is evenly spread over a given period, the overall pattern of rail services should be similarly spread over that period | n/a | n/a | n/a |
| (i) ensuring that where practicable appropriate provision is made for reservation of capacity to meet the needs of Bidders whose businesses require short term flexibility where there is a reasonable likelihood that this capacity will be utilised during the currency of the timetable in question | n/a | n/a | n/a |
| (j) enabling operators of trains to utilise their railway assets efficiently and avoiding having to increase the numbers of railway assets which the operators require to maintain their service patterns | n/a | n/a | n/a |
| (k) facilitating new commercial opportunities, including promoting competition in final markets and ensuring reasonable access to the Network by new operators of trains | n/a | n/a | n/a |
| (l) avoiding wherever practicable frequent timetable changes, in particular for railway passenger services | A consistent journey opportunity can be advertised for all Weeks between 9 and 16, but an opportunity exists to run services in part in different weekends | Rail replacement and availability of train service is slightly different in each week. | In favour of FCC |
| (m) encouraging the efficient use of capacity by considering a Bidder’s previous level of utilisation of Train Slots | n/a | n/a | n/a |
| (n) avoiding, unless absolutely necessary, changes to provisional International Paths following issue of the applicable Rules of the Plan | n/a | n/a | n/a |
| (o) taking into account the commercial interests of Network Rail and existing and potential operators of trains in a manner compatible with the foregoing | n/a | n/a | n/a |

- 7	decision sought from the PANEL

  - Network Rail seeks the following outcome from the Panel’s Determination:

    - That Network Rail’s decision on access on Sunday mornings between London and Peterborough/Cambridge in weeks 9 to 16 shall stand.

- 8	Appendices and Annexes

Appendix “A” 	CPPP for Weeks 9-12 and 13-16

Appendix “B” 	Extract of FCC consultation response

Appendix “C”	FCC request to Network Rail for further easement

Appendix “D”	Extract from Minutes of TOC liaison meeting, 16th December

Appendix “E” 	Network Rail response to FCC compromise

Appendix “F” 	Network Rail application of decision criteria (weekend/midweek RoU)

Appendix “G” 	FCC response to declination of compromise and criteria application

Appendix “H”	Network Rail clarification of enhancement work

Appendix “I”	Network Rail clarification of renewal work

Appendix “J”	ECML Route Utilisation Strategy recommendation summary

Appendix “K”	Finsbury Park & Alexandra Palace enhancement plan

Appendix “L”	Cambridge Jn renewals plan

- 9	signatures

Network Rail confirms that it has complied with Rule H21 of the Access Dispute Resolution Rules, which requires that

- the relevant extracts of contractual Documents containing the provision(s) under which the referral to the Timetabling Panel arises and/or provisions associated provision(s) associated with the substance of the dispute; and

- [the relevant extracts of] any other Documents referred to in the reference”.  [Rule H21(b) (I)]

|  | The Defendant |
| --- | --- |
|  | For and on behalf of Network Rail Infrastructure Limited ___________________________________ Signed ----------------------------------------------------------- Print Name Toby Patrick-Bailey Position Lead Access Planner LNE, Network Rail ___________________________________ |