## Sheet1
Outline Timeline for the Development of the December 2006
ECML Timetable and relationship of events.
Timetable Development Schedule | 4.1 2007 Base TT, Commencing Dec 2006 | 4.2 Achieved? | 4.3 Key Dates in relation to TTT96.
Formal Notification of Process Dates | 2005-10-17 | Achieved
Preliminary ROTP Proposal | 2005-10-21 | Achieved
Notificationof provisional International paths | 2005-10-21 | N/A
Development Commencement Date | 2005-10-24 | Achieved
TOC Rules of the Plan Comments | 2005-11-14 | Achieved
Final Rules of the Plan | 2005-12-16 | Achieved
Preliminary ROTR proposal | 2006-01-20 | Achieved
Submission of 'aspirational' bid | 2006-02-01 | Achieved
Start of Drafting Period | 2006-02-06 | No
Timetable conference | 7 and 08/02/2006 | Achieved
Priority Date | 2006-02-09 | Achieved
TOC ROTR Comments | 2006-02-17 | Achieved
Timetable Change Assessment Group | 2006-03-03 | Achieved
Final ROTR | 2006-03-17 | Achieved
|  |  | 2006-03-23 | ORR Decision paper issued detailing rights to be approved. (full document issued on the 6th April 2006)
|  |  | 2006-03-30 | Network Rail issue letter setting out the process and timeline for developing the December 2006 TT.
|  |  | 2006-04-25 | ECML Capacity Progress Meeting 1
Capacity Request Deadline | 2006-04-28 | Achieved
|  |  | 2006-05-12 | ECML Capacity Progress Meeting 2
Draft Timetable Issue | 2006-05-19 | Achieved
Start of Finalisation Period | 2006-05-22 | Achieved
|  |  | 2006-06-06 | ECML Capacity Progress Meeting 3
|  |  | 2006-06-23 | ECML Capacity Progress Meeting 4
Timetable Offer Date | 2006-07-07 | Achieved
Start of Supplmental Period | 2006-07-10 | Achieved
Appeal Period End | 2006-07-21 | Achieved
NRT upload Complete (T16) | 2006-08-18 | Achieved
Timetable Briefing Process complete (T15) | 2006-08-25 | Achieved
CIF Electronic Data Available (T12) | 2006-09-15
Timetable Commencement Date | 2006-12-10